## START HERE
WORKLOAD & PROFIT PLAN - START HERE
Click any sheet name to jump straight to it. Blue-text cells anywhere in this workbook are inputs you can change; green text is pulled from another sheet; black is calculated.
1 - WHERE YOU ENTER DATA | What you put there | How often
TS Ahmed | Paste Ahmed's monthly timesheet export into cell A4 | Monthly
TS Osama | Paste Osama's monthly timesheet export into cell A4 | Monthly
TS Kirolos | Paste Kirolos's monthly timesheet export into cell A4 | Monthly
Deliverables | Progress: step reached, credit %, status date, engineer % split | Monthly
Deliverable Actuals | Real milestone dates - submitted, comments received, resubmitted, completed (blue block W:AB) | Monthly
Support Plan | Bengaluru and draftsman support: planned, delivered, office shift date and reason | When resourcing changes
Profit Plan | Expected hours to finish each deliverable (column K) and the planning assumptions at the top | When re-planning
Phasing | Planned MM overrides only (the block from row 93). Actual MM is now calculated from the timesheet - do not type in it. | Rarely
Inputs | Project master data: budget MM, start and end dates, team availability | When a project is added
Work Calendar | Working week, public holidays, engineer name patterns, hours per day | Rarely
2 - WHERE YOU READ THE OUTPUT | What it answers
Delivery Sequence | In what order should we deliver, and where does the year-end profit land?
Profit Plan | What does the rest of the year look like, and is the plan credible?
Dashboard | Portfolio KPIs for any year or quarter: planned, actual, earned, CPI, utilisation
Mgmt Review | Team performance, plan adherence, and dependency on draftsmen and Bengaluru
Timesheet Daily | Who charged what on every date: project, proposal, absence, overtime, idle or leave
Deliverable Actuals | Real start and finish dates, dormant days, stoppages, activity spells
Proposals | Proposal effort by real proposal number and by year
Engineer KPIs | Per-engineer performance measures
Scorecard | Summary scoring view
Team Member | Individual workload detail
Analysis | Quarterly efficiency and profitability by project
Timesheet Raw | Consolidated timesheet - read only, builds itself from the three TS sheets
3 - HOW THE WORKBOOK FLOWS
The three TS sheets feed Timesheet Raw, which feeds Timesheet Daily (day-by-day) and Deliverable Actuals (deliverable-by-deliverable).
Deliverable Actuals plus the Deliverables register feed the Profit Plan, which ranks the remaining work and produces the Delivery Sequence.
Support Plan feeds the dependency section of Mgmt Review. Proposals feeds the proposal rows of the register.
Inputs and Phasing feed Analysis, which feeds the Dashboard. Phasing actual MM is now calculated from the timesheet, so the Dashboard and Analysis move as soon as you paste.
4 - MONTHLY ROUTINE
Step 1. Paste each engineer's export into TS Ahmed, TS Osama and TS Kirolos (cell A4, after deleting the old rows).
Step 2. Open Work Calendar and check the DATA CHECK block: row count, date range, and that no rows are unmatched.
Step 3. Update progress on the Deliverables register and milestone dates on Deliverable Actuals.
Step 4. Nothing to retype for actual MM - Phasing now reads it from the timesheet. Just check the Dashboard and Analysis have moved.
Step 5. Read the result on Delivery Sequence, Profit Plan and Mgmt Review.
5 - TAB COLOUR GUIDE
Tabs are ordered and coloured by role, left to right.
Purple | Guide and glossary | START HERE, Definitions
Blue | Reports - read these | Dashboard, Mgmt Review, Engineer KPIs, Team Member, Scorecard, Delivery Sequence
Green | Plan and enter data here | Inputs, Deliverables, Profit Plan, Support Plan, Proposals, Phasing, Analysis
Amber | Reference tables - change rarely | Project Types, Rules of Credit, Work Calendar
Grey | Engine and raw paste targets | Deliverable Actuals, Timesheet Daily, Timesheet Raw, TS Ahmed / Osama / Kirolos

## Definitions
FIELD DEFINITIONS — HOW TO READ THE DASHBOARD
All effort in Man-Months (MM). The Current column below is live and follows the Dashboard filter, showing: Full year 2026
SECTION 1 — THE THREE CORE MEASURES (everything else is built from these)
Field | Where it appears | What it actually means | How it is calculated | Current | How to read it
Planned MM | Selected Period band | The effort we SAID we would spend in this period. It comes from each project's budget spread across the months between its start and end date, so a 12 MM project running 2 years contributes 1.5 MM to each quarter. | Straight-line spread of Budget across the project's start-to-end window, summed for every project touching the period. Overridable per project per quarter on the Phasing sheet. | 44.8292 | This is the yardstick, not an achievement. It answers: how much work was this period supposed to absorb?
Actual MM | Selected Period band | The effort we REALLY spent in this period — the man-months your team actually booked against projects in those three months (or that year). | Sum of the quarterly actuals grid on Phasing, for the quarters inside the selected period, across all projects and all three engineers. | 17.9081 | The only hard fact of the three. If this is blank, nobody logged time — the period is unmeasurable, not efficient.
Earned MM | Selected Period band | The VALUE we delivered in this period, expressed in man-months of budget. If a project is 70% complete on a 26 MM budget, 18.2 MM of value has been earned regardless of how long it took. | Budget x % Complete for each project, then spread across quarters in proportion to when the time was actually booked. | 14.1861 | This is what the client is effectively paying for. Compare it with Actual MM to see whether effort is converting into progress.
SECTION 2 — PERIOD METRICS (flow: what happened inside the chosen window)
Field | Where it appears | What it actually means | How it is calculated | Current | How to read it
Profit / (Loss) in period | Selected Period band | Value delivered less effort burned, in this period only. Positive means you got more budget-value out than man-months you put in. | Earned MM less Actual MM. | -3.722 | A performance score for the period, NOT money in the bank. It says nothing about whether the project will finish in profit.
Capacity MM | Selected Period band | How much the team could deliver in this period if fully applied to projects. | Each person's availability % for that year x 3 months per quarter (x4 for a full year), summed across the team. | 24.163 | The ceiling. Actual MM above this means overtime or the data is wrong; far below means the team was on other work.
Utilisation | Selected Period band | How busy the team was: how much of the available capacity was actually booked to projects. | Actual MM divided by Capacity MM. | 74.11% | Low utilisation usually means unlogged time or non-project work, not idleness. Check before drawing conclusions.
Plan Adherence | Selected Period band | Did we burn the effort we said we would this period? | Actual MM divided by Planned MM. | 54.73% | Below 100% means the plan assumed more effort than was spent — either you are behind, or the phasing dates need correcting.
Efficiency (CPI) — in period | Selected Period band | Value delivered per man-month spent, IN THIS PERIOD ONLY. Above 1.00 means the period converted effort into progress well. | Earned MM in period divided by Actual MM in period. | 0.79216 | A snapshot of recent performance. Volatile — one quarter with little logged time can swing it wildly.
SECTION 3 — READING EFFICIENCY CORRECTLY
There is now one efficiency figure on the dashboard: Earned MM divided by Actual MM, for the period you selected. It answers a single question — did the effort spent in this window convert into delivered value? Above 1.00 is good. The traps below are the reason it sometimes looks wrong.
What you see |  | Why it happens |  | What to do about it
Reads n/a, or a dash |  | No time was booked to any project in the period, so there is nothing to divide. |  | Treat the period as unmeasured, not efficient. Check the actuals grid on Phasing for those quarters.
Far above 1.00 (say over 2.00x) |  | A project is marked well advanced on very little booked time, so earned value dwarfs actual effort. |  | Almost always missing actuals or an overstated budget. Compare Actual to Date against Budget in Project Detail.
Below 1.00 |  | More effort has been spent than value delivered. This is a genuine overrun. |  | Real signal. Look at Cost at Completion versus Budget per project in Project Detail to find which contract is causing it.
Swings hard between quarters |  | Period figures are volatile by nature — one quarter of light logging moves them a long way. |  | Switch the filter to Year, or scan several quarters, before concluding anything about a trend.
For the period currently selected (Full year 2026) efficiency reads 0.79x, from 14.19 MM of value delivered against 17.91 MM of effort booked.
SECTION 4 — BEFORE YOU TRUST ANY OF THESE NUMBERS
1. Efficiency is only as good as the logged time. A project marked 100% complete with almost no booked MM will show an impossibly high CPI and flatter the portfolio. Check Actual to Date against Budget on the Inputs sheet before believing a number above about 2.00x.
2. Planned MM depends entirely on the Start and End dates. If a date is wrong, that project's effort lands in the wrong quarters and Plan Adherence becomes meaningless.
3. % Complete drives Earned MM and Forecast at Completion. It is a judgement you type in — if it is stale, both the efficiency and the forecast loss are stale too.
4. Effort booked before quarterly tracking began sits in the Opening column on Phasing. It counts toward a project's total booked time but falls inside no quarter, so it never appears in any period figure.

## Dashboard
PROJECT PORTFOLIO DASHBOARD
All effort in Man-Months (MM) ¦ 9 projects in scope of 40 ¦ Team of 3 ¦ Reported 01 Sep 2026
PERIOD FILTER — choose how you want to look at the portfolio
View by: | Year | Year: | 2026 | Quarter: | Q1 | Showing: | Full year 2026
Resolved period → | Q1-26 | from | 2026-01-01 | to | 2026-12-31 | As at: | 2026-09-01 | Elapsed: | 67.12% | Planned to date: | 32.7222
SELECTED PERIOD — PERFORMANCE IN THE PERIOD YOU CHOSE ABOVE
| Planned MM (full period) | Actual MM | Earned MM | Profit / (Loss) | Capacity to Date | Utilisation | Plan Adherence to Date | Efficiency (CPI) | Projects Active
| 44.8292 | 17.9081 | 14.1861 | -3.722 | 24.163 | 74.11% | 54.73% | 0.79216 | 16
| full period plan | what we actually burned | value delivered | earned minus actual | pro-rated to 01 Sep | actual vs capacity to date | vs 32.72 MM planned to date | above 1.00 is good | live in this period
WHAT IS ACTUALLY BEING WORKED — PORTFOLIO BY STATUS
Status | Projects | Budget | Planned in Period | Actual in Period | Remaining on Hand | Cost at Compl. | Profit / (Loss) | In Scope?
Active | 6 | 35.55 | 28.3152 | 14.1662 | 48.5682 | 68.2141 | -32.6641 | Yes
Not Started | 1 | 5 | 1.2585 | 0 | 5 | 5 | 0 | Yes
On Hold | 7 | 18.4 | 9.5972 | 1.3541 | 26.7723 | 35.7939 | -17.3939 | No
Finalized | 2 | 9 | 5.6581 | 1.9473 | 0 | 4.8905 | 4.1095 | No
Proposal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No
Cancelled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No
ALL LIVE IN PERIOD | 16 | 67.95 | 44.8292 | 17.4676 | 80.3405 | 113.8986 | -45.9486
IN DELIVERY SCOPE | 7 | 40.55 | 29.5738 | 14.1662 | 53.5682 | 73.2141 | -32.6641
PROJECT DETAIL — only projects live in the selected period
Project | Budget | Start | End | Status | % Compl. | Actual to Date | Cost at Compl. | Remaining | Profit / (Loss) | Planned in Period | Actual in Period | % of Period Plan
N25178-0100D | 2.4 | 2026-07-01 | 2026-09-30 | Active | 65% | 0 | 2.4 | 2.4 | 0 | 2.4 | 0 | 5.354%
E26084-0100D | 3 | 2025-07-01 | 2026-09-30 | Active | 16.25% | 0.22568 | 1.3888 | 1.1631 | 1.6112 | 1.7921 | 0.22568 | 3.998%
N25185-0100D | 26 | 2025-10-01 | 2026-12-31 | Active | 31.6% | 18.5162 | 58.5956 | 40.0794 | -32.5956 | 20.7659 | 13.5176 | 46.32%
D26058-0100D | 5 | 2026-07-01 | 2028-06-30 | Not Started | 0% | 0 | 5 | 5 | 0 | 1.2585 | 0 | 2.807%
AN23207-0500D | 1.15 | 2026-01-01 | 2026-03-31 | On Hold | 65% | 0 | 1.15 | 1.15 | 0 | 1.15 | 0 | 2.565%
AN23276-0100D | 5 | 2024-07-01 | 2026-09-30 | On Hold | 90% | 0.88919 | 0.98799 | 0.098799 | 4.012 | 1.6606 | 0 | 3.704%
AN24073-0100D | 1.25 | 2025-07-01 | 2026-09-30 | On Hold | 90% | 0.92432 | 1.027 | 0.1027 | 0.22297 | 0.74672 | 0 | 1.666%
AN24140-0100R | 1.5 | 2025-03-01 | 2026-09-30 | Active | 10% | 0.5027 | 5.027 | 4.5243 | -3.527 | 0.70725 | 0.021622 | 1.578%
CS24035-0100D | 4 | 2025-10-01 | 2026-12-31 | On Hold | 85% | 3.1324 | 3.6852 | 0.55278 | 0.31479 | 3.1947 | 0.57027 | 7.126%
Q25008-0100D | 5 | 2026-01-01 | 2026-08-01 | Finalized | 100% | 1.9297 | 1.9297 | 0 | 3.0703 | 5 | 1.8135 | 11.15%
AN24185-0100R | 4 | 2024-10-01 | 2026-03-31 | Finalized | 100% | 2.9608 | 2.9608 | 0 | 1.0392 | 0.65814 | 0.13378 | 1.468%
AN24135-0100R | 4 | 2024-10-01 | 2027-03-31 | On Hold | 10% | 1.8311 | 18.3108 | 16.4797 | -14.3108 | 1.6009 | 0 | 3.571%
AN23108-0100R | 2 | 2025-02-01 | 2027-06-30 | On Hold | 10% | 0.82703 | 8.2703 | 7.4432 | -6.2703 | 0.82955 | 0.68514 | 1.85%
TA24246-0200R | 1 | 2025-02-01 | 2027-06-30 | On Hold | 60% | 1.4176 | 2.3626 | 0.94505 | -1.3626 | 0.41477 | 0.098649 | 0.9252%
Chargable Proposals 26 | 2.25 | 2026-01-01 | 2026-12-31 | Active | 50% | 0.33108 | 0.66216 | 0.33108 | 1.5878 | 2.25 | 0.33108 | 5.019%
Proposals 26 | 0.4 | 2026-01-01 | 2026-12-31 | Active | 50% | 0.07027 | 0.14054 | 0.07027 | 0.25946 | 0.4 | 0.07027 | 0.8923%
TOTAL — 16 project(s) live in period | 67.95 |  |  |  | 46.67% | 33.5581 | 113.8986 | 80.3405 | -45.9486 | 44.8292 | 17.4676 | 100%
RESOURCE DETAIL — BY ENGINEER (selected period)
Metric | Ahmed | Osama | Kirolos | Total
Actual MM booked in period | 5.7216 | 5.9946 | 6.1919 | 17.9081
Share of team time in period | 31.95% | 33.47% | 34.58% | 100%
Remaining on hand allocated (MM) | 22.9617 | 24.4405 | 6.1659 | 53.5682
Capacity in period (MM) | 12 | 12 | 12 | 36
Utilisation in period | 47.68% | 49.95% | 51.6% | 49.74%
Years of work outstanding | 1.9135 | 2.0367 | 0.51382 | 1.488
Chart data — by quarter
Quarter | Planned MM | Actual MM | Earned MM
Q1-24 | 6.1517 | 3.7365 | 13.9042
Q2-24 | 21.2783 | 3.4824 | 13.4847
Q3-24 | 16.6909 | 5.9311 | 16.0518
Q4-24 | 11.2439 | 8.0784 | 14.1571
Q1-25 | 9.4582 | 7.2338 | 7.5015
Q2-25 | 11.2763 | 5.9608 | 11.6317
Q3-25 | 15.3366 | 8.7851 | 13.166
Q4-25 | 9.5617 | 8.1784 | 5.7658
Q1-26 | 12.8015 | 6.6446 | 6.3798
Q2-26 | 11.1155 | 7.7986 | 5.5491
Q3-26 | 12.8585 | 3.4649 | 2.2572
Q4-26 | 8.0538 | 0 | 0
Q1-27 | 4.3985 | 0 | 0
Q2-27 | 4.0482 | 0 | 0
Q3-27 | 3.7791 | 0 | 0
Q4-27 | 3.7791 | 0 | 0
Q1-28 | 1.2449 | 0 | 0
Q2-28 | 1.2449 | 0 | 0
Q3-28 | 0.62927 | 0 | 0
Q4-28 | 0.62927 | 0 | 0
Chart data — by year
Year | Planned MM | Actual MM | Capacity MM
2024 | 55.3647 | 21.2284 | 28.2
2025 | 45.6329 | 30.1581 | 36
2026 | 44.8292 | 17.9081 | 36
2027 | 16.0049 | 0 | 36
2028 | 3.7483 | 0 | 36
Filter helper — resolves which projects are live in the selected period. Do not edit.
Code | Budget | Start | End | Status | % Compl. | Actual to Date | Cost at Compl. | Remaining | Profit | Planned in Period | Actual in Period | Live? | Rank | Earned in Period | Planned to Date in Period
N25178-0100D | 2.4 | 46204 | 46295 | Active | 0.65 | 0 | 2.4 | 2.4 | 0 | 2.4 | 0 | 1 | 1 | 0 | 1.6435
E26084-0100D | 3 | 45839 | 46295 | Active | 0.1625 | 0.22568 | 1.3888 | 1.1631 | 1.6112 | 1.7921 | 0.22568 | 1 | 2 | 0.4875 | 1.6018
N25185-0100D | 26 | 45931 | 46387 | Active | 0.316 | 18.5162 | 58.5956 | 40.0794 | -32.5956 | 20.7659 | 13.5176 | 1 | 3 | 5.998 | 13.8818
AN22137-0100D | 5 | 46388 | 47118 | Not Started | 0 | 1.4014 | 5 | 3.5986 | 0 | 0 | 0 | 0 |  | 0 | 0
D26058-0100D | 5 | 46204 | 46934 | Not Started | 0 | 0 | 5 | 5 | 0 | 1.2585 | 0 | 1 | 4 | 0 | 0.43092
AD24217-0100D | 3 | 45809 | 45870 | Finalized | 1 | 2.6 | 2.6 | 0 | 0.4 | 0 | 0 | 0 |  | 0 | 0
AN23207-0500D | 1.15 | 46023 | 46112 | On Hold | 0.65 | 0 | 1.15 | 1.15 | 0 | 1.15 | 0 | 1 | 5 | 0 | 1.15
AN23276-0100D | 5 | 45474 | 46295 | On Hold | 0.9 | 0.88919 | 0.98799 | 0.098799 | 4.012 | 1.6606 | 0 | 1 | 6 | 0 | 1.4842
AN24073-0100D | 1.25 | 45839 | 46295 | On Hold | 0.9 | 0.92432 | 1.027 | 0.1027 | 0.22297 | 0.74672 | 0 | 1 | 7 | 0 | 0.6674
AN24140-0100R | 1.5 | 45717 | 46295 | Active | 0.1 | 0.5027 | 5.027 | 4.5243 | -3.527 | 0.70725 | 0.021622 | 1 | 8 | 0.0064516 | 0.63212
CS24035-0100D | 4 | 45931 | 46387 | On Hold | 0.85 | 3.1324 | 3.6852 | 0.55278 | 0.31479 | 3.1947 | 0.57027 | 1 | 9 | 0.61898 | 2.1357
E24181-0100D | 0.5 | 45505 | 45505 | Finalized | 1 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | 0 | 0
J23152-0100D | 0.5 | 45292 | 45382 | Finalized | 1 | 0.11081 | 0.11081 | 0 | 0.38919 | 0 | 0 | 0 |  | 0 | 0
Q25008-0100D | 5 | 46023 | 46235 | Finalized | 1 | 1.9297 | 1.9297 | 0 | 3.0703 | 5 | 1.8135 | 1 | 10 | 4.6989 | 4.7632
S24014-0101D | 21.27 | 45383 | 45505 | Finalized | 1 | 2.4419 | 2.4419 | 0 | 18.8281 | 0 | 0 | 0 |  | 0 | 0
S24014-0102D | 7.62 | 45536 | 45930 | Finalized | 1 | 2.6554 | 2.6554 | 0 | 4.9646 | 0 | 0 | 0 |  | 0 | 0
S24014-0103D | 6.36 | 45536 | 45930 | Finalized | 1 | 4.35 | 4.35 | 0 | 2.01 | 0 | 0 | 0 |  | 0 | 0
S24014-0104D | 12.03 | 45536 | 45930 | Finalized | 1 | 1.2162 | 1.2162 | 0 | 10.8138 | 0 | 0 | 0 |  | 0 | 0
S22058-0700D | 6 | 45474 | 45930 | Finalized | 1 | 5.1162 | 5.1162 | 0 | 0.88378 | 0 | 0 | 0 |  | 0 | 0
AN24185-0100R | 4 | 45566 | 46112 | Finalized | 1 | 2.9608 | 2.9608 | 0 | 1.0392 | 0.65814 | 0.13378 | 1 | 11 | 0.18074 | 0.65814
AN24135-0100R | 4 | 45566 | 46477 | On Hold | 0.1 | 1.8311 | 18.3108 | 16.4797 | -14.3108 | 1.6009 | 0 | 1 | 12 | 0 | 1.0702
AN23232-0100D | 3 | 45292 | 45565 | Finalized | 1 | 3.3027 | 3.3027 | 0 | -0.3027 | 0 | 0 | 0 |  | 0 | 0
AN23108-0100R | 2 | 45689 | 46568 | On Hold | 0.1 | 0.82703 | 8.2703 | 7.4432 | -6.2703 | 0.82955 | 0.68514 | 1 | 13 | 0.16569 | 0.55455
TA24246-0200R | 1 | 45689 | 46568 | On Hold | 0.6 | 1.4176 | 2.3626 | 0.94505 | -1.3626 | 0.41477 | 0.098649 | 1 | 14 | 0.041754 | 0.27727
S22058-0900D | 0.25 | 45383 | 45565 | Cancelled | 1 | 0.095946 | 0.095946 | 0 | 0.15405 | 0 | 0 | 0 |  | 0 | 0
S22058-0400D | 0.5 | 45292 | 45382 | Finalized | 1 | 0.040541 | 0.040541 | 0 | 0.45946 | 0 | 0 | 0 |  | 0 | 0
Proposals 25 | 1.9 | 45658 | 46022 | Finalized | 1 | 2.0838 | 2.0838 | 0 | -0.18378 | 0 | 0 | 0 |  | 0 | 0
Chargable Proposals 25 | 3 | 45839 | 45930 | Finalized | 1 | 3.9432 | 3.9432 | 0 | -0.94324 | 0 | 0 | 0 |  | 0 | 0
AD23051-0101D | 0.5 | 45292 | 45382 | Cancelled | 1 | 0.14189 | 0.14189 | 0 | 0.35811 | 0 | 0 | 0 |  | 0 | 0
AN21146-0100R | 3 | 45352 | 45565 | Finalized | 1 | 0.51892 | 0.51892 | 0 | 2.4811 | 0 | 0 | 0 |  | 0 | 0
N23106-0100D | 5 | 45352 | 45565 | Finalized | 1 | 3.3216 | 3.3216 | 0 | 1.6784 | 0 | 0.44054 | 0 |  | 0.66314 | 0
OM23030-0100D | 0.25 | 45352 | 45473 | Finalized | 1 | 0.1473 | 0.1473 | 0 | 0.1027 | 0 | 0 | 0 |  | 0 | 0
Chargable Proposals 24 | 2.25 | 45292 | 45657 | Finalized | 1 | 1.8541 | 1.8541 | 0 | 0.39595 | 0 | 0 | 0 |  | 0 | 0
Proposals 24 | 1.1 | 45292 | 45657 | Finalized | 1 | 0.53649 | 0.53649 | 0 | 0.56351 | 0 | 0 | 0 |  | 0 | 0
S23204-0100D | 1.5 | 45292 | 45382 | Finalized | 1 | 0.045946 | 0.045946 | 0 | 1.4541 | 0 | 0 | 0 |  | 0 | 0
S24100-0100D | 3 | 45474 | 45657 | Finalized | 1 | 1.0054 | 1.0054 | 0 | 1.9946 | 0 | 0 | 0 |  | 0 | 0
TA23011-0100R | 0.1 | 45292 | 45382 | Finalized | 1 | 0.054054 | 0.054054 | 0 | 0.045946 | 0 | 0 | 0 |  | 0 | 0
AL25148-0100D | 10 | 46388 | 46752 | Not Started | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 |  | 0 | 0
Chargable Proposals 26 | 2.25 | 46023 | 46387 | Active | 0.5 | 0.33108 | 0.66216 | 0.33108 | 1.5878 | 2.25 | 0.33108 | 1 | 15 | 1.125 | 1.5041
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Proposals 26 | 0.4 | 46023 | 46387 | Active | 0.5 | 0.07027 | 0.14054 | 0.07027 | 0.25946 | 0.4 | 0.07027 | 1 | 16 | 0.2 | 0.2674
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Formulas:
Actual MM = IF([Status]="","",INDEX(C173:C252,MATCH(ROW()-25,N173:N252,0)))
Earned MM = IF([Status]="","",INDEX(D173:D252,MATCH(ROW()-25,N173:N252,0)))
Note on B6: Ahmed Mitwally: Quarter key used to match the quarter column headers on the Analysis and Phasing sheets.

## Mgmt Review
MANAGEMENT REVIEW — TEAM PERFORMANCE
Viewing: Full year 2026 ¦ All effort in Man-Months (MM) ¦ Reported 01 Sep 2026
To change the period, use the View by / Year / Quarter selectors at the top of the Dashboard sheet — this sheet follows them automatically.
As at 01 Sep 2026 — 67.1% of the selected period has elapsed. Capacity and plan adherence are pro-rated accordingly, so a part-finished year is not compared against a full year of capacity.
PERFORMANCE IN THE SELECTED PERIOD
Team totals | Planned MM (full period) | Actual MM | Earned MM | Profit / (Loss) | Capacity to Date | Utilisation | Plan Adherence to Date | Efficiency (CPI) | Projects Active
| 44.8292 | 17.9081 | 14.1861 | -3.722 | 24.163 | 74.11% | 54.73% | 0.79216 | 16
| what we said we would burn | what we actually burned | value delivered | earned minus actual | pro-rated to 01 Sep | actual vs capacity | vs 32.72 MM planned to date | above 1.00 is good | live in this period
TEAM KPIs BY ENGINEER — SELECTED PERIOD
KPI | Ahmed | Osama | Kirolos | Team Total
Actual MM booked | 5.7216 | 5.9946 | 6.1919 | 17.9081
Planned MM to date (by allocation) | 12.2282 | 9.3574 | 11.1366 | 32.7222
Earned MM (by allocation) | 5.1198 | 3.7813 | 5.285 | 14.1861
Profit / (Loss) contribution | -0.60181 | -2.2133 | -0.9069 | -3.722
Capacity MM to date | 8.0543 | 8.0543 | 8.0543 | 24.163
Utilisation vs capacity to date | 0.71038 | 0.74427 | 0.76876 | 0.74114
Plan adherence to date | 0.4679 | 0.64063 | 0.556 | 0.54728
Efficiency (CPI) | 0.89482 | 0.63079 | 0.85353 | 0.79216
Share of team time booked | 0.3195 | 0.33474 | 0.34576 | 1
Remaining on hand allocated | 22.9617 | 24.4405 | 6.1659 | 53.5682
TYPE-WEIGHTED VIEW — PERSONAL SCORING ONLY (never applied to project financials)
Type-weighted Earned MM (KPI only) | 4.7903 | 3.8375 | 4.5318 | 13.1596
Type-weighted Efficiency (CPI, KPI only) | 0.83722 | 0.64016 | 0.7319 | 0.73484
Average type factor of work delivered | 0.93563 | 1.0149 | 0.85749 | 0.92764
TEAM PERFORMANCE DEPENDENCY - DRAFTSMEN AND BENGALURU
Cairo hours come from the timesheet. Bengaluru and draftsman hours are entered per deliverable on the Support Plan sheet. Until those are filled in, delivery reads as 100% Cairo.
DELIVERY MIX | Hours | Share | Man-months
Cairo team (from timesheet) | 11970 | 100% | 64.7027
Bengaluru support | 0 | 0% | 0
Draftsman support | 0 | 0% | 0
Total delivered | 11970 | 100% | 64.7027
BENGALURU: PLAN VERSUS REALITY
Planned Bengaluru hours | 0
Actual Bengaluru hours | 0
Shortfall absorbed by Cairo (hours) | 0
Shortfall absorbed by Cairo (man-months) | 0
As a share of Cairo capacity left this year | 0%
Deliverables shifted away from the planned office | 0
DRAFTSMAN DEPENDENCY
Planned draftsman hours | 0
Actual draftsman hours | 0
Draftsman share of delivery | 0%
Deliverables relying on a draftsman | 0
VERDICT | No support plan entered yet - fill the blue columns on the Support Plan sheet and this section becomes live.
Chart data
Engineer | Actual MM | Capacity to Date
Ahmed | 5.7216 | 8.0543
Osama | 5.9946 | 8.0543
Kirolos | 6.1919 | 8.0543
Engineer | Planned MM | Actual MM | Earned MM
Ahmed | 12.2282 | 5.7216 | 5.1198
Osama | 9.3574 | 5.9946 | 3.7813
Kirolos | 11.1366 | 6.1919 | 5.285
Engineer | Utilisation | Plan Adherence
Ahmed | 71.04% | 46.79%
Osama | 74.43% | 64.06%
Kirolos | 76.88% | 55.6%

## Engineer KPIs
ENGINEER KPIs — SELECTED PERIOD
Viewing: Full year 2026 ¦ All effort in Man-Months (MM) ¦ Reported 01 Sep 2026
Period is controlled from the Dashboard sheet. This sheet and the Management Review sheet both follow it.
As at 01 Sep 2026 — 67.1% of the selected period has elapsed. Capacity and plan adherence are pro-rated accordingly.
KPI SUMMARY BY ENGINEER
KPI | Ahmed | Osama | Kirolos | Team Total
Actual MM booked | 5.7216 | 5.9946 | 6.1919 | 17.9081
Planned MM to date (by allocation) | 12.2282 | 9.3574 | 11.1366 | 32.7222
Earned MM (by allocation) | 5.1198 | 3.7813 | 5.285 | 14.1861
Profit / (Loss) contribution | -0.60181 | -2.2133 | -0.9069 | -3.722
Capacity MM to date | 8.0543 | 8.0543 | 8.0543 | 24.163
Utilisation vs capacity to date | 71.04% | 74.43% | 76.88% | 74.11%
Plan adherence to date | 46.79% | 64.06% | 55.6% | 54.73%
Efficiency (CPI) | 0.89482 | 0.63079 | 0.85353 | 0.79216
Share of team time booked | 31.95% | 33.47% | 34.58% | 100%
Remaining on hand allocated | 22.9617 | 24.4405 | 6.1659 | 53.5682
Projects worked in period | 6 | 4 | 7 | 11
Average MM per project worked | 0.9536 | 1.4986 | 0.88456 | 1.628
Months of work outstanding | 22.9617 | 24.4405 | 6.1659 | 17.8561
WHO WORKED ON WHAT — ACTUAL MM IN THE SELECTED PERIOD
Project | Status | Ahmed | Osama | Kirolos | Total
E26084-0100D | Active | 0 | 0.22568 | 0 | 0.22568
N25185-0100D | Active | 5.1 | 5.4189 | 2.9986 | 13.5176
AN24140-0100R | Active | 0 | 0 | 0.021622 | 0.021622
CS24035-0100D | On Hold | 0.10676 | 0 | 0.46351 | 0.57027
Q25008-0100D | Finalized | 0.14595 | 0 | 1.6676 | 1.8135
AN24185-0100R | Finalized | 0 | 0 | 0.13378 | 0.13378
AN23108-0100R | On Hold | 0 | 0 | 0.68514 | 0.68514
TA24246-0200R | On Hold | 0 | 0.098649 | 0 | 0.098649
N23106-0100D | Finalized | 0.18919 | 0.25135 | 0 | 0.44054
Chargable Proposals 26 | Active | 0.10946 | 0 | 0.22162 | 0.33108
Proposals 26 | Active | 0.07027 | 0 | 0 | 0.07027
TOTAL — 11 project(s) with time booked |  | 5.7216 | 5.9946 | 6.1919 | 17.9081
Helper — actual MM by project and engineer for the selected period. Do not edit.
Code | Status | Ahmed | Osama | Kirolos | Total | Rank
N25178-0100D | Active | 0 | 0 | 0 | 0
E26084-0100D | Active | 0 | 0.22568 | 0 | 0.22568 | 1
N25185-0100D | Active | 5.1 | 5.4189 | 2.9986 | 13.5176 | 2
AN22137-0100D | Not Started | 0 | 0 | 0 | 0
D26058-0100D | Not Started | 0 | 0 | 0 | 0
AD24217-0100D | Finalized | 0 | 0 | 0 | 0
AN23207-0500D | On Hold | 0 | 0 | 0 | 0
AN23276-0100D | On Hold | 0 | 0 | 0 | 0
AN24073-0100D | On Hold | 0 | 0 | 0 | 0
AN24140-0100R | Active | 0 | 0 | 0.021622 | 0.021622 | 3
CS24035-0100D | On Hold | 0.10676 | 0 | 0.46351 | 0.57027 | 4
E24181-0100D | Finalized | 0 | 0 | 0 | 0
J23152-0100D | Finalized | 0 | 0 | 0 | 0
Q25008-0100D | Finalized | 0.14595 | 0 | 1.6676 | 1.8135 | 5
S24014-0101D | Finalized | 0 | 0 | 0 | 0
S24014-0102D | Finalized | 0 | 0 | 0 | 0
S24014-0103D | Finalized | 0 | 0 | 0 | 0
S24014-0104D | Finalized | 0 | 0 | 0 | 0
S22058-0700D | Finalized | 0 | 0 | 0 | 0
AN24185-0100R | Finalized | 0 | 0 | 0.13378 | 0.13378 | 6
AN24135-0100R | On Hold | 0 | 0 | 0 | 0
AN23232-0100D | Finalized | 0 | 0 | 0 | 0
AN23108-0100R | On Hold | 0 | 0 | 0.68514 | 0.68514 | 7
TA24246-0200R | On Hold | 0 | 0.098649 | 0 | 0.098649 | 8
S22058-0900D | Cancelled | 0 | 0 | 0 | 0
S22058-0400D | Finalized | 0 | 0 | 0 | 0
Proposals 25 | Finalized | 0 | 0 | 0 | 0
Chargable Proposals 25 | Finalized | 0 | 0 | 0 | 0
AD23051-0101D | Cancelled | 0 | 0 | 0 | 0
AN21146-0100R | Finalized | 0 | 0 | 0 | 0
N23106-0100D | Finalized | 0.18919 | 0.25135 | 0 | 0.44054 | 9
OM23030-0100D | Finalized | 0 | 0 | 0 | 0
Chargable Proposals 24 | Finalized | 0 | 0 | 0 | 0
Proposals 24 | Finalized | 0 | 0 | 0 | 0
S23204-0100D | Finalized | 0 | 0 | 0 | 0
S24100-0100D | Finalized | 0 | 0 | 0 | 0
TA23011-0100R | Finalized | 0 | 0 | 0 | 0
AL25148-0100D | Not Started | 0 | 0 | 0 | 0
Chargable Proposals 26 | Active | 0.10946 | 0 | 0.22162 | 0.33108 | 10
|  | 0 | 0 | 0 | 0
Proposals 26 | Active | 0.07027 | 0 | 0 | 0.07027 | 11
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
Chart data — do not edit
Quarter | Ahmed | Osama | Kirolos
Q1-24 | 2.8959 | 0.84054 | 0
Q2-24 | 2.3378 | 1.1446 | 0
Q3-24 | 2.7392 | 1.9243 | 1.2676
Q4-24 | 2.773 | 3.0054 | 2.3
Q1-25 | 2.2243 | 2.5622 | 2.4473
Q2-25 | 2.0716 | 2.1459 | 1.7432
Q3-25 | 2.2554 | 3.2473 | 3.2824
Q4-25 | 2.7081 | 2.7649 | 2.7054
Q1-26 | 2.2689 | 2.1378 | 2.2378
Q2-26 | 2.7554 | 2.5378 | 2.5054
Q3-26 | 0.6973 | 1.3189 | 1.4486
Q4-26 | 0 | 0 | 0
Q1-27 | 0 | 0 | 0
Q2-27 | 0 | 0 | 0
Q3-27 | 0 | 0 | 0
Q4-27 | 0 | 0 | 0
Q1-28 | 0 | 0 | 0
Q2-28 | 0 | 0 | 0
Q3-28 | 0 | 0 | 0
Q4-28 | 0 | 0 | 0
Engineer | Actual MM
Ahmed | 5.7216
Osama | 5.9946
Kirolos | 6.1919
Engineer | Earned MM
Ahmed | 5.1198
Osama | 3.7813
Kirolos | 5.285
Engineer | Remaining on Hand
Ahmed | 22.9617
Osama | 24.4405
Kirolos | 6.1659
Engineer | Planned MM to Date
Ahmed | 12.2282
Osama | 9.3574
Kirolos | 11.1366
Engineer | Actual MM | Capacity to Date | Remaining on Hand
Ahmed | 5.7216 | 8.0543 | 22.9617
Osama | 5.9946 | 8.0543 | 24.4405
Kirolos | 6.1919 | 8.0543 | 6.1659

## Team Member
PERSONAL PERFORMANCE REPORT — AHMED ¦ 2025
All effort in Man-Months (MM). Choose your name and the year below — this sheet is independent of the Dashboard filter.
Team member: | Ahmed | Year: | 2025 | As at: | 2026-09-01 |  | 1
As at 01 Sep 2026, 100.0% of 2025 has elapsed. Capacity and plan targets below are pro-rated to that point, not to 31 December. | [6 empty] | 1
12
YOUR NUMBERS FOR THE YEAR
Metric | Value | What it means
Actual MM you booked | 9.2595 | time you actually logged in 2025
Planned MM to date (your allocation) | 22.7617 | what the plan expected of you by 01 Sep
Earned MM (value you delivered) | 20.0156 | budget value earned on your share of the work
Capacity MM to date | 12 | your available time up to 01 Sep
Utilisation vs capacity to date | 77.16% | within capacity
Plan adherence to date | 40.68% | behind the plan
Efficiency (CPI) | 2.1616 | delivering more value than time spent
Projects you worked on | 20 | projects with time booked in the year
Average MM per project | 0.46297 | average effort per project
Remaining workload allocated to you | 31.1209 | still to do on projects assigned to you
QUARTER BY QUARTER
Metric | Q1-25 | Q2-25 | Q3-25 | Q4-25 | Year
Your actual MM | 2.2243 | 2.0716 | 2.2554 | 2.7081 | 9.2595
Your capacity to date | 3 | 3 | 3 | 3 | 12
Elapsed of quarter | 100% | 100% | 100% | 100% | 100%
Utilisation vs capacity to date | 74.14% | 69.05% | 75.18% | 90.27% | 77.16%
Your earned MM (value delivered) | 2.1625 | 7.8548 | 7.5314 | 2.4669 | 20.0156
Your efficiency (CPI) | 0.97223 | 3.7916 | 3.3393 | 0.91092 | 2.1616
Your contribution to team MM | 30.75% | 34.75% | 25.67% | 33.11% | 30.7%
YOUR PROJECTS THIS YEAR
Project | Status | Your MM | Share of your time | Planned to date | Your allocation %
N25185-0100D | Active | 1.6284 | 17.59% | 5.2341 | 41.58%
AD24217-0100D | Finalized | 0.25946 | 2.802% | 3 | 40%
AN23276-0100D | On Hold | 0.010811 | 0.1168% | 2.2202 | 40%
AN24073-0100D | On Hold | 0.010811 | 0.1168% | 0.50328 | 10%
AN24140-0100R | Active | 0.0054054 | 0.05838% | 0.79275 | 10%
CS24035-0100D | On Hold | 1.0338 | 11.16% | 0.80525 | 50%
J23152-0100D | Finalized | 0.016216 | 0.1751% | 0 | 100%
Q25008-0100D | Finalized | 0.078378 | 0.8465% | 0 | 20%
S24014-0102D | Finalized | 2.2365 | 24.15% | 5.2665 | 70%
S24014-0104D | Finalized | 0.67162 | 7.253% | 8.3144 | 100%
S22058-0700D | Finalized | 0.90541 | 9.778% | 3.5842 | 15%
AN24185-0100R | Finalized | 0.010811 | 0.1168% | 2.6691 | 5%
AN24135-0100R | On Hold | 0.025676 | 0.2773% | 1.6009 | 5%
AN23232-0100D | Finalized | 0.041892 | 0.4524% | 0 | 75%
AN23108-0100R | On Hold | 0.097297 | 1.051% | 0.75909 | 10%
TA24246-0200R | On Hold | 0.085135 | 0.9194% | 0.37955 | 10%
S22058-0900D | Cancelled | 0.074324 | 0.8027% | 0 | 100%
S22058-0400D | Finalized | 0.010811 | 0.1168% | 0 | 100%
Proposals 25 | Finalized | 1.0716 | 11.57% | 1.9 | 80%
Chargable Proposals 25 | Finalized | 0.98514 | 10.64% | 3 | 40%
TOTAL — 20 project(s) |  | 9.2595 | 100% | 40.0294
Project | Your MM
|  | Planned in Year | Earned in Year | Your Actual MM | Your Allocation % | Rank | Planned to Date in Year
N25178-0100D | Active | 0 | 0 | 0 | 100% |  | 0
E26084-0100D | Active | 1.2079 | 0 | 0 | 15% |  | 1.2079
N25185-0100D | Active | 5.2341 | 2.218 | 1.6284 | 41.58% | 1 | 5.2341
AN22137-0100D | Not Started | 0 | 0 | 0 | 60% |  | 0
D26058-0100D | Not Started | 0 | 0 | 0 | 60% |  | 0
AD24217-0100D | Finalized | 3 | 3 | 0.25946 | 40% | 2 | 3
AN23207-0500D | On Hold | 0 | 0 | 0 | 20% |  | 0
AN23276-0100D | On Hold | 2.2202 | 0.53343 | 0.010811 | 40% | 3 | 2.2202
AN24073-0100D | On Hold | 0.50328 | 1.125 | 0.010811 | 10% | 4 | 0.50328
AN24140-0100R | Active | 0.79275 | 0.12339 | 0.0054054 | 10% | 5 | 0.79275
CS24035-0100D | On Hold | 0.80525 | 2.7458 | 1.0338 | 50% | 6 | 0.80525
E24181-0100D | Finalized | 0 | 0 | 0 | 100% |  | 0
J23152-0100D | Finalized | 0 | 0.073171 | 0.016216 | 100% | 7 | 0
Q25008-0100D | Finalized | 0 | 0.30112 | 0.078378 | 20% | 8 | 0
S24014-0101D | Finalized | 0 | 0 | 0 | 100% |  | 0
S24014-0102D | Finalized | 5.2665 | 7.62 | 2.2365 | 70% | 9 | 5.2665
S24014-0103D | Finalized | 4.3956 | 0 | 0 | 50% |  | 4.3956
S24014-0104D | Finalized | 8.3144 | 6.6432 | 0.67162 | 100% | 10 | 8.3144
S22058-0700D | Finalized | 3.5842 | 5.187 | 0.90541 | 15% | 11 | 3.5842
AN24185-0100R | Finalized | 2.6691 | 2.2912 | 0.010811 | 5% | 12 | 2.6691
AN24135-0100R | On Hold | 1.6009 | 0.29727 | 0.025676 | 5% | 13 | 1.6009
AN23232-0100D | Finalized | 0 | 0.038052 | 0.041892 | 75% | 14 | 0
AN23108-0100R | On Hold | 0.75909 | 0.034314 | 0.097297 | 10% | 15 | 0.75909
TA24246-0200R | On Hold | 0.37955 | 0.55825 | 0.085135 | 10% | 16 | 0.37955
S22058-0900D | Cancelled | 0 | 0.19366 | 0.074324 | 100% | 17 | 0
S22058-0400D | Finalized | 0 | 0.13333 | 0.010811 | 100% | 18 | 0
Proposals 25 | Finalized | 1.9 | 1.9 | 1.0716 | 80% | 19 | 1.9
Chargable Proposals 25 | Finalized | 3 | 3 | 0.98514 | 40% | 20 | 3
AD23051-0101D | Cancelled | 0 | 0 | 0 | 100% |  | 0
AN21146-0100R | Finalized | 0 | 0 | 0 | 40% |  | 0
N23106-0100D | Finalized | 0 | 0.04882 | 0 | 60% |  | 0
OM23030-0100D | Finalized | 0 | 0 | 0 | 100% |  | 0
Chargable Proposals 24 | Finalized | 0 | 0 | 0 | 40% |  | 0
Proposals 24 | Finalized | 0 | 0 | 0 | 80% |  | 0
S23204-0100D | Finalized | 0 | 0 | 0 | 100% |  | 0
S24100-0100D | Finalized | 0 | 0 | 0 | 25% |  | 0
TA23011-0100R | Finalized | 0 | 0 | 0 | 100% |  | 0
AL25148-0100D | Not Started | 0 | 0 | 0 | 60% |  | 0
Chargable Proposals 26 | Active | 0 | 0 | 0 | 60% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
Proposals 26 | Active | 0 | 0 | 0 | 100% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
|  | 0 | 0 | 0 | 0% |  | 0
Chart data — do not edit
Quarter | Your Actual MM | Your Earned MM | Your Capacity to Date
Q1-25 | 2.2243 | 2.1625 | 3
Q2-25 | 2.0716 | 7.8548 | 3
Q3-25 | 2.2554 | 7.5314 | 3
Q4-25 | 2.7081 | 2.4669 | 3
Project | Your MM
N25185-0100D | 1.6284
AD24217-0100D | 0.25946
AN23276-0100D | 0.010811
AN24073-0100D | 0.010811
AN24140-0100R | 0.0054054
CS24035-0100D | 1.0338
J23152-0100D | 0.016216
Q25008-0100D | 0.078378
S24014-0102D | 2.2365
S24014-0104D | 0.67162
S22058-0700D | 0.90541
AN24185-0100R | 0.010811
AN24135-0100R | 0.025676
AN23232-0100D | 0.041892
AN23108-0100R | 0.097297
TA24246-0200R | 0.085135
S22058-0900D | 0.074324
S22058-0400D | 0.010811
Proposals 25 | 1.0716
Chargable Proposals 25 | 0.98514
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A

## Scorecard
TEAM SCORECARD — WEIGHTED RANKING
Viewing: Full year 2026 ¦ Weights below are yours to set — change them and the ranking updates.
SCORING FACTORS — edit the blue cells
Factor | Weight | Direction | Target | How it is scored
Efficiency (CPI, type-weighted) | 30% | Higher is better |  | Best performer scores 100; others in proportion. Earned MM is weighted by project type factor — scoring only.
Utilisation vs capacity | 20% | Target band | 1 | 100 when exactly on target; falls away as it deviates either side.
Plan adherence | 15% | Target band | 1 | 100 when exactly on plan; over- and under-running both lose points.
Earned MM delivered (type-weighted) | 20% | Higher is better |  | Rewards absolute value delivered, weighted by project type factor — scoring only.
Actual MM contributed | 10% | Higher is better |  | Rewards volume of effort carried.
Projects worked | 5% | Higher is better |  | Rewards breadth across the portfolio.
TOTAL WEIGHT | 100% | OK
RAW VALUES FOR THE SELECTED PERIOD
Factor | Ahmed | Osama | Kirolos | Best
Efficiency (CPI, type-weighted) | 0.83722 | 0.64016 | 0.7319 | 0.83722
Utilisation vs capacity | 71.04% | 74.43% | 76.88% | 76.88%
Plan adherence | 46.79% | 64.06% | 55.6% | 64.06%
Earned MM delivered (type-weighted) | 4.7903 | 3.8375 | 4.5318 | 4.7903
Actual MM contributed | 5.7216 | 5.9946 | 6.1919 | 6.1919
Projects worked | 6 | 4 | 7 | 7
NORMALISED SCORES (0 = worst, 100 = best)
Factor | Ahmed | Osama | Kirolos | Weight
Efficiency (CPI, type-weighted) | 100 | 76.4628 | 87.4202 | 30%
Utilisation vs capacity | 71.0377 | 74.4268 | 76.8764 | 20%
Plan adherence | 46.7902 | 64.0627 | 55.5995 | 15%
Earned MM delivered (type-weighted) | 100 | 80.1108 | 94.6054 | 20%
Actual MM contributed | 92.4051 | 96.8136 | 100 | 10%
Projects worked | 85.7143 | 57.1429 | 100 | 5%
WEIGHTED SCORE | 84.7523 | 75.9943 | 83.8624
RANK | 1 | 3 | 2
RANKING
Rank | Engineer | Weighted Score | Strongest factor | Weakest factor | idx
1 | Ahmed | 84.7523 | Efficiency (CPI, type-weighted) | Plan adherence | 1
2 | Kirolos | 83.8624 | Actual MM contributed | Plan adherence | 3
3 | Osama | 75.9943 | Actual MM contributed | Projects worked | 2
Chart data — do not edit
Engineer | Weighted Score
Ahmed | 84.7523
Osama | 75.9943
Kirolos | 83.8624

## Delivery Sequence
DELIVERY SEQUENCE — THE PLAN IN ORDER
Read top to bottom: this is the order to deliver in. Everything above the capacity line is in this year's plan; everything below it needs capacity the team does not have. To change the plan, type expected hours in column K of the Profit Plan sheet — this list re-sorts itself.
THE PLAN AT A GLANCE |  |  | TEAM EARNINGS UNDER THIS SEQUENCE
Capacity left (MM) |  | 11.9 | Engineer | Hours in plan | MM in plan | Earned MM (pro-rata on hours) | Hours available to year end | Load | Check
Capacity left (hrs) |  | 2201.5 | Ahmed | 775.0375 | 4.1894 | 9.4679 | 733.8333 | 105.6% | OVER by 41 hrs
Deliverables to do |  | 27 | Osama | 729.6 | 3.9438 | 8.9128 | 733.8333 | 99.42% | within capacity
MM committed |  | 11.8139 | Kirolos | 680.925 | 3.6807 | 8.3182 | 733.8333 | 92.79% | within capacity
Hours committed |  | 2185.5625 | Unassigned | 0 | 0 | 0 |  |  | -
Value to be earned (MM) |  | 26.699 | Total | 2185.5625 | 11.8139 | 26.699
Profit added (MM) |  | 14.8851
Year-end profit (MM) |  | 11.1632
Deferred to next year |  | 5
Value deferred (MM) |  | 17.1125
Implied CPI of this plan |  | 2.26 | NOT CREDIBLE - implied 2.26x is above the 2.00x ceiling; expected hours are too optimistic
DELIVERY SEQUENCE — RANKED BY VALUE EARNED PER MAN-MONTH
# | Project | Deliverable / Phase | Decision | Hours to finish | MM to finish | Value earned (MM) | Profit added (MM) | Cumulative MM | Capacity used | Start month | Finish month | Ahmed hrs | Osama hrs | Kirolos hrs | Year-end profit after this item (MM) | src row
1 | N25185-0100D | Final Design - Apapa Berth 12 | DO | 50 | 0.27027 | 0.936 | 0.66573 | 0.27027 | 2.271% | Oct 26 | Oct 26 | 12.5 | 0 | 37.5 | -3.0562 | 23
2 | N25185-0100D | Final Design - Apapa Berth 13 | DO | 50 | 0.27027 | 0.936 | 0.66573 | 0.54054 | 4.542% | Oct 26 | Oct 26 | 12.5 | 0 | 37.5 | -2.3905 | 24
3 | N25185-0100D | Final Design - Apapa Berth 14 | DO | 50 | 0.27027 | 0.936 | 0.66573 | 0.81081 | 6.814% | Oct 26 | Oct 26 | 12.5 | 0 | 37.5 | -1.7248 | 25
4 | D26058-0100D | Concept Design | DO | 50 | 0.27027 | 0.75 | 0.47973 | 1.0811 | 9.085% | Oct 26 | Oct 26 | 30 | 20 | 0 | -1.2451 | 27
5 | N25185-0100D | Final Design - Tin Can Berth 5 | DO | 12 | 0.064865 | 0.156 | 0.091135 | 1.1459 | 9.63% | Oct 26 | Oct 26 | 5.4 | 5.4 | 1.2 | -1.1539 | 9
6 | N25185-0100D | Final Design - Tin Can Berth 6 | DO | 12 | 0.064865 | 0.156 | 0.091135 | 1.2108 | 10.17% | Oct 26 | Oct 26 | 5.4 | 5.4 | 1.2 | -1.0628 | 10
7 | N25185-0100D | Final Design - Tin Can Berth 7 | DO | 12 | 0.064865 | 0.156 | 0.091135 | 1.2757 | 10.72% | Oct 26 | Oct 26 | 5.4 | 5.4 | 1.2 | -0.97165 | 11
8 | N25185-0100D | Final Design - Tin Can Berth 8 | DO | 12 | 0.064865 | 0.156 | 0.091135 | 1.3405 | 11.27% | Oct 26 | Oct 26 | 5.4 | 5.4 | 1.2 | -0.88051 | 12
9 | AN22137-0100D | Schematic Design | DO | 400 | 2.1622 | 5 | 2.8378 | 3.5027 | 29.43% | Oct 26 | Nov 26 | 240 | 160 | 0 | 1.9573 | 26
10 | N25185-0100D | Final Design - Tin Can Berth 9 | DO | 80 | 0.43243 | 0.936 | 0.50357 | 3.9351 | 33.07% | Nov 26 | Nov 26 | 32 | 48 | 0 | 2.4609 | 13
11 | N25185-0100D | Final Design - Tin Can Berth 10 | DO | 80 | 0.43243 | 0.936 | 0.50357 | 4.3676 | 36.7% | Nov 26 | Nov 26 | 32 | 48 | 0 | 2.9645 | 14
12 | N25185-0100D | Final Design - Tin Can Berth 1 | DO | 90 | 0.48649 | 1.04 | 0.55351 | 4.8541 | 40.79% | Nov 26 | Nov 26 | 13.5 | 54 | 22.5 | 3.518 | 5
13 | N25185-0100D | Final Design - Tin Can Berth 2 | DO | 90 | 0.48649 | 1.04 | 0.55351 | 5.3405 | 44.88% | Nov 26 | Nov 26 | 13.5 | 54 | 22.5 | 4.0715 | 6
14 | N25185-0100D | Final Design - Tin Can Berth 3 | DO | 90 | 0.48649 | 1.04 | 0.55351 | 5.827 | 48.97% | Nov 26 | Nov 26 | 13.5 | 54 | 22.5 | 4.625 | 7
15 | N25185-0100D | Final Design - Tin Can Berth 4 | DO | 90 | 0.48649 | 1.04 | 0.55351 | 6.3135 | 53.05% | Nov 26 | Dec 26 | 13.5 | 54 | 22.5 | 5.1785 | 8
16 | N25185-0100D | Final Design - Apapa Berth 4 | DO | 90 | 0.48649 | 1.04 | 0.55351 | 6.8 | 57.14% | Dec 26 | Dec 26 | 13.5 | 22.5 | 54 | 5.732 | 15
17 | N25185-0100D | Final Design - Apapa Berth 5 | DO | 90 | 0.48649 | 1.04 | 0.55351 | 7.2865 | 61.23% | Dec 26 | Dec 26 | 13.5 | 22.5 | 54 | 6.2855 | 16
18 | N25185-0100D | Final Design - Apapa Berth 6 | DO | 90 | 0.48649 | 1.04 | 0.55351 | 7.773 | 65.32% | Dec 26 | Dec 26 | 13.5 | 22.5 | 54 | 6.8391 | 17
19 | N25185-0100D | Final Design - Apapa Berth 7 | DO | 90 | 0.48649 | 1.04 | 0.55351 | 8.2595 | 69.41% | Dec 26 | Dec 26 | 13.5 | 22.5 | 54 | 7.3926 | 18
20 | N25185-0100D | Final Design - Apapa Berth 8 | DO | 90 | 0.48649 | 1.04 | 0.55351 | 8.7459 | 73.5% | Dec 26 | Dec 26 | 13.5 | 22.5 | 54 | 7.9461 | 19
21 | N25185-0100D | Final Design - Apapa Berth 9 | DO | 90 | 0.48649 | 1.04 | 0.55351 | 9.2324 | 77.58% | Dec 26 | Jan 27 | 13.5 | 22.5 | 54 | 8.4996 | 20
22 | N25185-0100D | Final Design - Apapa Berth 10 | DO | 90 | 0.48649 | 1.04 | 0.55351 | 9.7189 | 81.67% | Jan 27 | Jan 27 | 13.5 | 22.5 | 54 | 9.0531 | 21
23 | N25185-0100D | Final Design - Apapa Berth 11 | DO | 90 | 0.48649 | 1.04 | 0.55351 | 10.2054 | 85.76% | Jan 27 | Jan 27 | 13.5 | 22.5 | 54 | 9.6066 | 22
24 | D26058-0100D | Schematic Design | DO | 90 | 0.48649 | 1 | 0.51351 | 10.6919 | 89.85% | Jan 27 | Jan 27 | 54 | 36 | 0 | 10.1201 | 28
25 | Chargable Proposals 26 | Proposals | DO | 104.0625 | 0.5625 | 1.125 | 0.5625 | 11.2544 | 94.57% | Jan 27 | Jan 27 | 62.4375 | 0 | 41.625 | 10.6826 | 63
26 | Proposals 26 | Proposals | DO | 18.5 | 0.1 | 0.2 | 0.1 | 11.3544 | 95.42% | Jan 27 | Jan 27 | 18.5 | 0 | 0 | 10.7826 | 64
27 | N25178-0100D | Concept Design | DO | 85 | 0.45946 | 0.84 | 0.38054 | 11.8139 | 99.28% | Jan 27 | Jan 27 | 85 | 0 | 0 | 11.1632 | 1
28 | D26058-0100D | Final Design | DEFER | 400 | 2.1622 | 3.25 |  | 13.976 | 117.4% | - | - |  |  |  | 11.1632 | 29
29 | E26084-0100D | Final Design | DEFER | 300 | 1.6216 | 2.25 |  | 15.5976 | 131.1% | - | - |  |  |  | 11.1632 | 3
30 | AL25148-0100D | Concept Design | DEFER | 1850 | 10 | 10 |  | 25.5976 | 215.1% | - | - |  |  |  | 11.1632 | 62
31 | AN24140-0100R | Design Review | DEFER | 356.7857 | 1.9286 | 1.35 |  | 27.5262 | 231.3% | - | - |  |  |  | 11.1632 | 55
32 | E26084-0100D | Schematic Design | DEFER | 100 | 0.54054 | 0.2625 |  | 28.0667 | 235.9% | - | - |  |  |  | 11.1632 | 2
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
[10 empty] | - | -
The red line is the capacity limit. Rows above it fit inside the 12.00 MM left this year; rows below need capacity the team does not have. Hours, months and engineer split all follow the Expected Hours you type in column K of the Profit Plan sheet.
Formulas:
Start month = IF([Decision]<>"DO","-",TEXT(EOMONTH('Profit Plan'!$B7,INT(([Cumulative MM]-[MM to finish])/'Profit Plan'!$B8))+1,"mmm yy"))
Finish month = IF([Decision]<>"DO","-",TEXT(EOMONTH('Profit Plan'!$B7,MAX(0,CEILING([Cumulative MM]/'Profit Plan'!$B8,1)-1))+1,"mmm yy"))

## Inputs
INPUTS — PROJECT REGISTER & TEAM
Blue cells are inputs. Add a project by filling the next blank row (up to row 24) — every downstream sheet picks it up automatically. All effort in Man-Months (MM).
PROJECT REGISTER | [14 empty] | CALCULATED — do not type here
Number | Project Name | Budget (MM) | Start | End | Status | % Complete | CAC Override | Ahmed % | Osama % | Kirolos % | Check | In Scope | Notes | Manual % (fallback) | Actual MM | Cost at Compl. | Remaining on Hand | Earned MM | Profit / (Loss) | CPI | Type Factor (KPI only) | Engineer 1 % (manual fallback) | Engineer 2 % (manual fallback) | Engineer 3 % (manual fallback)
[6 empty] | 65% |  | 100% | 0% | 0% | 100% | 1 |  |  | 0 | 2.4 | 2.4 | 1.56 | 0 |  | 1.1
[6 empty] | 16.25% |  | 15% | 85% | 0% | 100% | 1 |  |  | 0.22568 | 1.3888 | 1.1631 | 0.4875 | 1.6112 | 2.1602 | 1.025
[6 empty] | 31.6% |  | 41.58% | 51.27% | 7.152% | 100% | 1 |  |  | 18.5162 | 58.5956 | 40.0794 | 8.216 | -32.5956 | 0.44372 | 1.016
[6 empty] | 0% |  | 60% | 40% | 0% | 100% | 1 |  |  | 1.4014 | 5 | 3.5986 | 0 | 0 | 0 | 1.1
[6 empty] | 0% |  | 60% | 40% | 0% | 100% | 1 |  |  | 0 | 5 | 5 | 0 | 0 |  | 1.1
[6 empty] | 100% |  | 40% | 20% | 40% | 100% | 0 |  |  | 2.6 | 2.6 | 0 | 3 | 0.4 | 1.1538 | 1.1
[6 empty] | 65% |  | 20% | 0% | 80% | 100% | 0 |  |  | 0 | 1.15 | 1.15 | 0.7475 | 0 |  | 1.1
[6 empty] | 90% |  | 40% | 0% | 60% | 100% | 0 |  |  | 0.88919 | 0.98799 | 0.098799 | 4.5 | 4.012 | 5.0608 | 1.1
[6 empty] | 90% |  | 10% | 20% | 70% | 100% | 0 |  |  | 0.92432 | 1.027 | 0.1027 | 1.125 | 0.22297 | 1.2171 | 1.1
[6 empty] | 10% |  | 10% | 20% | 70% | 100% | 1 |  |  | 0.5027 | 5.027 | 4.5243 | 0.15 | -3.527 | 0.29839 | 0.75
[6 empty] | 85% |  | 50% | 0% | 50% | 100% | 0 |  |  | 3.1324 | 3.6852 | 0.55278 | 3.4 | 0.31479 | 1.0854 | 1
[6 empty] | 100% |  | 100% | 0% | 0% | 100% | 0 |  |  | 0 | 0.5 | 0.5 | 0.5 | 0 |  | 1.2
[6 empty] | 100% |  | 100% | 0% | 0% | 100% | 0 |  |  | 0.11081 | 0.11081 | 0 | 0.5 | 0.38919 | 4.5122 | 0.85
[6 empty] | 100% |  | 20% | 0% | 80% | 100% | 0 |  |  | 1.9297 | 1.9297 | 0 | 5 | 3.0703 | 2.591 | 0.85
[6 empty] | 100% |  | 100% | 0% | 0% | 100% | 0 |  |  | 2.4419 | 2.4419 | 0 | 21.27 | 18.8281 | 8.7105 | 1.2
[6 empty] | 100% |  | 70% | 20% | 10% | 100% | 0 |  |  | 2.6554 | 2.6554 | 0 | 7.62 | 4.9646 | 2.8696 | 1.1
[6 empty] | 100% |  | 50% | 25% | 25% | 100% | 0 |  |  | 4.35 | 4.35 | 0 | 6.36 | 2.01 | 1.4621 | 1.1
[6 empty] | 100% |  | 100% | 0% | 0% | 100% | 0 |  |  | 1.2162 | 1.2162 | 0 | 12.03 | 10.8138 | 9.8913 | 1.2
[6 empty] | 100% |  | 15% | 50% | 35% | 100% | 0 |  |  | 5.1162 | 5.1162 | 0 | 6 | 0.88378 | 1.1727 | 1.1
[6 empty] | 100% |  | 5% | 30% | 65% | 100% | 0 |  |  | 2.9608 | 2.9608 | 0 | 4 | 1.0392 | 1.351 | 0.75
[6 empty] | 10% |  | 5% | 0% | 95% | 100% | 0 |  |  | 1.8311 | 18.3108 | 16.4797 | 0.4 | -14.3108 | 0.21845 | 0.75
[6 empty] | 100% |  | 75% | 25% | 0% | 100% | 0 |  |  | 3.3027 | 3.3027 | 0 | 3 | -0.3027 | 0.90835 | 1.1
[6 empty] | 10% |  | 10% | 0% | 90% | 100% | 0 |  |  | 0.82703 | 8.2703 | 7.4432 | 0.2 | -6.2703 | 0.24183 | 0.75
[6 empty] | 60% |  | 10% | 90% | 0% | 100% | 0 |  |  | 1.4176 | 2.3626 | 0.94505 | 0.6 | -1.3626 | 0.42326 | 0.75
[6 empty] | 100% |  | 100% | 0% | 0% | 100% | 0 |  |  | 0.095946 | 0.095946 | 0 | 0.25 | 0.15405 | 2.6056 | 1.1
[6 empty] | 100% |  | 100% | 0% | 0% | 100% | 0 |  |  | 0.040541 | 0.040541 | 0 | 0.5 | 0.45946 | 12.3333 | 1.1
[6 empty] | 100% |  | 80% | 10% | 10% | 100% | 0 |  |  | 2.0838 | 2.0838 | 0 | 1.9 | -0.18378 | 0.9118 | 0.7
[6 empty] | 100% |  | 40% | 30% | 30% | 100% | 0 |  |  | 3.9432 | 3.9432 | 0 | 3 | -0.94324 | 0.7608 | 0.7
[6 empty] | 100% |  | 100% | 0% | 0% | 100% | 0 |  |  | 0.14189 | 0.14189 | 0 | 0.5 | 0.35811 | 3.5238 | 1.1
[6 empty] | 100% |  | 40% | 0% | 60% | 100% | 0 |  |  | 0.51892 | 0.51892 | 0 | 3 | 2.4811 | 5.7812 | 0.75
[6 empty] | 100% |  | 60% | 30% | 10% | 100% | 0 |  |  | 3.3216 | 3.3216 | 0 | 5 | 1.6784 | 1.5053 | 1.1
[6 empty] | 100% |  | 100% | 0% | 0% | 100% | 0 |  |  | 0.1473 | 0.1473 | 0 | 0.25 | 0.1027 | 1.6972 | 0.85
[6 empty] | 100% |  | 40% | 30% | 30% | 100% | 0 |  |  | 1.8541 | 1.8541 | 0 | 2.25 | 0.39595 | 1.2136 | 0.7
[6 empty] | 100% |  | 80% | 10% | 10% | 100% | 0 |  |  | 0.53649 | 0.53649 | 0 | 1.1 | 0.56351 | 2.0504 | 0.7
[6 empty] | 100% |  | 100% | 0% | 0% | 100% | 0 |  |  | 0.045946 | 0.045946 | 0 | 1.5 | 1.4541 | 32.6471 | 1.1
[6 empty] | 100% |  | 25% | 30% | 45% | 100% | 0 |  |  | 1.0054 | 1.0054 | 0 | 3 | 1.9946 | 2.9839 | 1.1
[6 empty] | 100% |  | 100% | 0% | 0% | 100% | 0 |  |  | 0.054054 | 0.054054 | 0 | 0.1 | 0.045946 | 1.85 | 0.75
[6 empty] | 0% |  | 60% | 0% | 40% | 100% | 1 |  |  | 0 | 10 | 10 | 0 | 0 |  | 1.1
[6 empty] | 50% |  | 60% | 0% | 40% | 100% | 1 |  |  | 0.33108 | 0.66216 | 0.33108 | 1.125 | 1.5878 | 3.398 | 0.7
0
[6 empty] | 50% |  | 100% | 0% | 0% | 100% | 1 |  |  | 0.07027 | 0.14054 | 0.07027 | 0.2 | 0.25946 | 2.8462 | 0.7
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
TOTAL |  | 165.58 | [9 empty] | 9 |  |  | 70.5419 | 164.981 | 94.4391 | 114.341 | 0.59898 | 1.6209
TEAM AVAILABILITY — % of time available for project delivery
Engineer | 2024 | 2025 | 2026 | 2027 | 2028
Engineer 1 | 100% | 100% | 100% | 100% | 100%
Engineer 2 | 100% | 100% | 100% | 100% | 100%
Engineer 3 | 35% | 100% | 100% | 100% | 100%
Months per quarter | 3 | months — 1 engineer at 100% availability delivers 3.00 MM per quarter
As-at date (for to-date comparisons) | 2026-09-01 | Overwrite with a fixed date to freeze the report; leave as =TODAY() to always compare against today.
Note on H5: Ahmed Mitwally: Optional. Enter a Cost at Completion here to override the calculated forecast for this project. Leave blank to let the model calculate it.
Note on L5: Ahmed Mitwally: Must total 100% for any project with a budget. Turns red if it does not.
Note on M5: Ahmed Mitwally: 1 = counts toward delivery capacity and in-hand workload. Active and Not Started are in scope.
Note on R5: Ahmed Mitwally: Cost at Completion less actual MM booked, floored at zero. This is the work genuinely still to do.
Note on S5: Ahmed Mitwally: Budget x % Complete. The value delivered so far.
Note on U5: Ahmed Mitwally: Earned MM divided by actual MM. Above 1.00 means more value delivered than time burned.
Note on V5: Ahmed Mitwally: Weighted-average portfolio weight of this project's deliverable types. Used for personal scoring only — never applied to project financials.
Note on G6: Ahmed Mitwally: Driven by the Deliverables register (rules-of-credit progress). If a project has no deliverables logged, it falls back to the manual % in column O.
Note on I6: Ahmed Mitwally: Driven by the Deliverables register: each person's share of the deliverables actually earned on this project. Falls back to the manual % in column W when no resource split has been entered.

## Deliverables
DELIVERABLE REGISTER — INPUT SHEET | [15 empty] | PROJECT ROLL-UP — calculated
One row per deliverable. Blue cells are inputs. Pick the project, type, phase weight (% of that project's scope), the step reached, and who worked on it (Ahmed / Osama / Kirolos must total 100% per row). Credit %, progress and the person split feeding Inputs are all calculated. | [15 empty] | Weights must total 100% per project before the progress figure is meaningful.
KPI weighting only — never applied to financials
Project Number | Project Name | Deliverable / Phase | Type Code | Phase Weight % | Step No. | Step Name (status) | Credit % | Weighted Progress | Status Date | Engineer 1 % | Engineer 2 % | Engineer 3 % | Split Check | Notes | Type Factor (KPI only) | Project Number | Deliverables | Sum of Weights | Weight Check | Progress (Rules of Credit) | Type Factor (weighted avg) | Ahmed share | Osama share | Kirolos share | Share Basis | Actual start (timesheet) | Last activity (timesheet) | Actual hours to date | Dormant working days | Activity status
| Consultancy Services for The Feasibility Studies, Masterplan and Concept Design for IJEBU-ODE and MONIYA Ports Terminals. |  |  |  |  | Option selected and frozen | 65% | 65% |  |  |  |  | OK |  | 1.1 | N25178-0100D | 1 | 100% | OK | 65% | 1.1 | 100% | 0% | 0% | earned progress | 0 | 0 | 0 | 0 | Never charged
| Ras Al Hekma – Landscape Design Consultancy Services [RIBA Stage 1-4] for Promenade Beach Area and Sea Wall |  |  |  |  | Option selected and frozen | 65% | 16.25% |  |  |  |  | OK |  | 1.1 | E26084-0100D | 2 | 100% | OK | 16.25% | 1.025 | 15% | 85% | 0% | earned progress | 0 | 0 | 0 | 0 | Never charged
| Ras Al Hekma – Landscape Design Consultancy Services [RIBA Stage 1-4] for Promenade Beach Area and Sea Wall | [11 empty] | OK |  | 1 | N25185-0100D | 22 | 100% | OK | 31.6% | 1.016 | 41.58% | 51.27% | 7.152% | earned progress | 0 | 0 | 0 | 0 | Never charged
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports |  |  |  |  | Client acceptance | 100% | 16% |  |  |  |  | OK |  | 1.1 | AN22137-0100D | 1 | 100% | OK | 0% | 1.1 | 60% | 40% | 0% | scope weight | 2025-10-01 | 2026-03-18 | 1650.75 | 11 | Dormant since 2026-03-18
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports | [11 empty] | OK |  | 1 | D26058-0100D | 3 | 100% | OK | 0% | 1.1 | 60% | 40% | 0% | scope weight | 2026-03-24 | 2026-08-16 | 0 | 11 | Active
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports | [11 empty] | OK |  | 1 | AD24217-0100D | 1 | 100% | OK | 100% | 1.1 | 40% | 20% | 40% | earned progress | 2026-03-24 | 2026-08-16 | 0 | 11 | Active
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports | [11 empty] | OK |  | 1 | AN23207-0500D | 1 | 100% | OK | 65% | 1.1 | 20% | 0% | 80% | earned progress | 2026-03-24 | 2026-08-16 | 0 | 11 | Active
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports | [11 empty] | OK |  | 1 | AN23276-0100D | 1 | 100% | OK | 90% | 1.1 | 40% | 0% | 60% | earned progress | 2026-03-24 | 2026-08-16 | 0 | 11 | Active
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports |  |  |  |  | Transmitted to client (IFA/IFC) | 85% | 3.4% |  |  |  |  | OK |  | 1 | AN24073-0100D | 1 | 100% | OK | 90% | 1.1 | 10% | 20% | 70% | earned progress | 2026-03-24 | 2026-08-16 | 197.1944 | 11 | Active
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports |  |  |  |  | Transmitted to client (IFA/IFC) | 85% | 3.4% |  |  |  |  | OK |  | 1 | AN24140-0100R | 1 | 100% | OK | 10% | 0.75 | 10% | 20% | 70% | earned progress | 2026-03-24 | 2026-08-16 | 197.1944 | 11 | Active
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports |  |  |  |  | Transmitted to client (IFA/IFC) | 85% | 3.4% |  |  |  |  | OK |  | 1 | CS24035-0100D | 1 | 100% | OK | 85% | 1 | 50% | 0% | 50% | earned progress | 2026-03-24 | 2026-08-16 | 197.1944 | 11 | Active
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports |  |  |  |  | Transmitted to client (IFA/IFC) | 85% | 3.4% |  |  |  |  | OK |  | 1 | E24181-0100D | 1 | 100% | OK | 100% | 1.2 | 100% | 0% | 0% | earned progress | 2026-03-24 | 2026-08-16 | 197.1944 | 11 | Active
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports |  |  |  |  | Design started | 10% | 0.4% |  |  |  |  | OK |  | 1 | J23152-0100D | 1 | 100% | OK | 100% | 0.85 | 100% | 0% | 0% | earned progress | 2026-03-24 | 2026-08-16 | 197.1944 | 11 | Active
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports |  |  |  |  | Design started | 10% | 0.4% |  |  |  |  | OK |  | 1 | Q25008-0100D | 1 | 100% | OK | 100% | 0.85 | 20% | 0% | 80% | earned progress | 2026-03-24 | 2026-08-16 | 197.1944 | 11 | Active
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports | [11 empty] | OK |  | 1 | S24014-0101D | 1 | 100% | OK | 100% | 1.2 | 100% | 0% | 0% | earned progress | 2026-03-24 | 2026-08-16 | 0 | 11 | Active
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports | [11 empty] | OK |  | 1 | S24014-0102D | 1 | 100% | OK | 100% | 1.1 | 70% | 20% | 10% | earned progress | 2026-03-24 | 2026-08-16 | 0 | 11 | Active
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports | [11 empty] | OK |  | 1 | S24014-0103D | 1 | 100% | OK | 100% | 1.1 | 50% | 25% | 25% | earned progress | 2026-03-24 | 2026-08-16 | 0 | 11 | Active
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports | [11 empty] | OK |  | 1 | S24014-0104D | 1 | 100% | OK | 100% | 1.2 | 100% | 0% | 0% | earned progress | 2026-03-24 | 2026-08-16 | 0 | 11 | Active
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports | [11 empty] | OK |  | 1 | S22058-0700D | 1 | 100% | OK | 100% | 1.1 | 15% | 50% | 35% | earned progress | 2026-03-24 | 2026-08-16 | 0 | 11 | Active
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports | [11 empty] | OK |  | 1 | AN24185-0100R | 1 | 100% | OK | 100% | 0.75 | 5% | 30% | 65% | earned progress | 2026-03-24 | 2026-08-16 | 0 | 11 | Active
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports | [11 empty] | OK |  | 1 | AN24135-0100R | 1 | 100% | OK | 10% | 0.75 | 5% | 0% | 95% | earned progress | 2026-03-24 | 2026-08-16 | 0 | 11 | Active
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports | [11 empty] | OK |  | 1 | AN23232-0100D | 1 | 100% | OK | 100% | 1.1 | 75% | 25% | 0% | earned progress | 2026-03-24 | 2026-08-16 | 0 | 11 | Active
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports |  |  |  |  | Design started | 10% | 0.4% |  |  |  |  | OK |  | 1 | AN23108-0100R | 1 | 100% | OK | 10% | 0.75 | 10% | 0% | 90% | earned progress | 2026-03-24 | 2026-08-16 | 197.1944 | 11 | Active
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports |  |  |  |  | Design started | 10% | 0.4% |  |  |  |  | OK |  | 1 | TA24246-0200R | 1 | 100% | OK | 60% | 0.75 | 10% | 90% | 0% | earned progress | 2026-03-24 | 2026-08-16 | 197.1944 | 11 | Active
| Consultancy Services for Port Modernization Infrastructure and Reconstruction Works for Nigerian Port Authority (NPA) in TINCAN and APAPA Ports |  |  |  |  | Design started | 10% | 0.4% |  |  |  |  | OK |  | 1 | S22058-0900D | 1 | 100% | OK | 100% | 1.1 | 100% | 0% | 0% | earned progress | 2026-03-24 | 2026-08-16 | 197.1944 | 11 | Active
| Construction of Dry Docks Permanent Terminal and Construction of Shipyard in Luanda Port | [11 empty] | OK |  | 1.1 | S22058-0400D | 1 | 100% | OK | 100% | 1.1 | 100% | 0% | 0% | earned progress | 2024-04-30 | 2024-08-29 | 0 | 62 | Dormant since 2024-08-29
| AMI Stormwater Collection System – Private Outfall | [11 empty] | OK |  | 1.1 | Proposals 25 | 1 | 100% | OK | 100% | 0.7 | 80% | 10% | 10% | earned progress | 0 | 0 | 0 | 0 | Never charged
| AMI Stormwater Collection System – Private Outfall | [11 empty] | OK |  | 1.1 | Chargable Proposals 25 | 1 | 100% | OK | 100% | 0.7 | 40% | 30% | 30% | earned progress | 0 | 0 | 0 | 0 | Never charged
| AMI Stormwater Collection System – Private Outfall | [11 empty] | OK |  | 1.1 | AD23051-0101D | 1 | 100% | OK | 100% | 1.1 | 100% | 0% | 0% | earned progress | 0 | 0 | 0 | 0 | Never charged
| Yas Canal Community - Lead Design Consultancy Services |  |  |  |  | Client acceptance | 100% | 100% |  |  |  |  | OK |  | 1.1 | AN21146-0100R | 1 | 100% | OK | 100% | 0.75 | 40% | 0% | 60% | earned progress | 2025-03-05 | 2025-09-28 | 363.75 | 106 | Dormant since 2025-09-28
| Assessing the Quay Wall Capacity Under Loading Effect of STS Crane Offloading at Damietta Port |  |  |  |  | Comments closed | 100% | 100% |  |  |  |  | OK |  | 1.2 | N23106-0100D | 1 | 100% | OK | 100% | 1.1 | 60% | 30% | 10% | earned progress | 0 | 0 | 0 | 0 | Never charged
| J23152-0100D - Consultancy Services for PV Projects at APC |  |  |  |  | Tender queries and addenda closed | 100% | 100% |  |  |  |  | OK |  | 0.85 | OM23030-0100D | 1 | 100% | OK | 100% | 0.85 | 100% | 0% | 0% | earned progress | 2023-11-07 | 2023-11-12 | 17.5 | 2 | Dormant since 2023-11-12
| Lead Consultant Services for Simaisma Development Project |  |  |  |  | Tender queries and addenda closed | 100% | 100% |  |  |  |  | OK |  | 0.85 | Chargable Proposals 24 | 1 | 100% | OK | 100% | 0.7 | 40% | 30% | 30% | earned progress | 2025-01-28 | 2026-08-05 | 357 | 349 | Active
| The Line Hidden Marina Project Management, Project Controls, BIM & GIS Requirements |  |  |  |  | Comments closed | 100% | 100% |  |  |  |  | OK |  | 1.2 | Proposals 24 | 1 | 100% | OK | 100% | 0.7 | 80% | 10% | 10% | earned progress | 2024-02-26 | 2024-07-07 | 451.75 | 23 | Dormant since 2024-07-07
| The Line Hidden Marina, The Line Engineering Tasks - Part 1 |  |  |  |  | Client acceptance | 100% | 100% |  |  |  |  | OK |  | 1.1 | S23204-0100D | 1 | 100% | OK | 100% | 1.1 | 100% | 0% | 0% | earned progress | 2025-04-09 | 2025-09-24 | 491.25 | 49 | Dormant since 2025-09-24
| The Line Hidden Marina - Design of Wharf - Temporary Works |  |  |  |  | Client acceptance | 100% | 100% |  |  |  |  | OK |  | 1.1 | S24100-0100D | 1 | 100% | OK | 100% | 1.1 | 25% | 30% | 45% | earned progress | 2024-09-02 | 2024-12-17 | 804.75 | 11 | Dormant since 2024-12-17
| The Line Hidden Marina Project Management, Project Controls, BIM & GIS Requirements |  |  |  |  | Comments closed | 100% | 100% |  |  |  |  | OK |  | 1.2 | TA23011-0100R | 1 | 100% | OK | 100% | 0.75 | 100% | 0% | 0% | earned progress | 2024-09-04 | 2025-09-03 | 225 | 187 | Dormant since 2025-09-03
| JCDC Detailed Masterplan & Engineering - PHASE 2 - Infrastructure |  |  |  |  | Client acceptance | 100% | 100% |  |  |  |  | OK |  | 1.1 | AL25148-0100D | 1 | 100% | OK | 0% | 1.1 | 60% | 0% | 40% | scope weight | 2024-05-13 | 2025-11-06 | 946.5 | 294 | Dormant since 2025-11-06
| Construction of the Offshore Import and Export System of Cabinda Refinery |  |  |  |  | Comment closeout confirmed | 100% | 100% |  |  |  |  | OK |  | 0.75 | Chargable Proposals 26 | 1 | 100% | OK | 50% | 0.7 | 60% | 0% | 40% | earned progress | 2024-10-20 | 2026-03-31 | 547.75 | 301 | Dormant since 2026-03-31
| Abu Dhabi Ports - Development of Unicargas Port in Luanda |  |  |  |  | Client acceptance | 100% | 100% |  |  |  |  | OK |  | 1.1 | [10 empty] | 2023-11-20 | 2024-06-23 | 403.75 | 102 | Dormant since 2024-06-23
| JCD Detailed Master Planning and Engineering – Infrastructure |  |  |  |  | Client acceptance | 100% | 100% |  |  |  |  | OK |  | 1.1 | Proposals 26 | 1 | 100% | OK | 50% | 0.7 | 100% | 0% | 0% | earned progress | 2023-12-19 | 2025-04-29 | 7.5 | 349 | Dormant since 2025-04-29
| Proposals of 2025 |  |  |  |  | Proposal submitted | 100% | 100% |  |  |  |  | OK |  | 0.7 | [10 empty] | 2025-02-19 | 2025-12-11 | 385.5 | 212 | Dormant since 2025-12-11
| Chargable Proposals of 2025 |  |  |  |  | Proposal submitted | 100% | 100% |  |  |  |  | OK |  | 0.7 | [10 empty] | 2025-01-02 | 2025-09-08 | 729.5 | 178 | Dormant since 2025-09-08
| Construction of the Oceanic Terminal of Barra do Dande (TOBD) |  |  |  |  | Comment closeout confirmed | 100% | 100% |  |  |  |  | OK |  | 0.75 | [10 empty] | 2024-05-14 | 2024-09-29 | 96 | 81 | Dormant since 2024-09-29
| Consultancy Services For Front End Engineering Design (Feed) For The Proposed Brass Island Shipyard Located At Brass Lga Bayelsa State |  |  |  |  | Client acceptance | 100% | 100% |  |  |  |  | OK |  | 1.1 | [10 empty] | 2024-05-28 | 2026-03-08 | 217.75 | 428 | Dormant since 2026-03-08
| Development of Waterfront Action Areas in Khawr AL Batah |  |  |  |  | Tender queries and addenda closed | 100% | 100% |  |  |  |  | OK |  | 0.85 | [10 empty] | 2024-02-12 | 2024-02-25 | 27.25 | 0 | Dormant since 2024-02-25
| Chargable Proposals of 2024 |  |  |  |  | Proposal submitted | 100% | 100% |  |  |  |  | OK |  | 0.7 | [10 empty] | 2024-02-01 | 2024-12-30 | 343 | 238 | Dormant since 2024-12-30
| Proposals of 2024 |  |  |  |  | Proposal submitted | 100% | 100% |  |  |  |  | OK |  | 0.7 | [10 empty] | 2024-02-05 | 2024-12-18 | 99.25 | 228 | Dormant since 2024-12-18
| Al Farshah Island (AFI) Pre-Infrastructure Design |  |  |  |  | Client acceptance | 100% | 100% |  |  |  |  | OK |  | 1.1 | [10 empty] | 2024-01-31 | 2024-01-31 | 8.5 | 0 | Dormant since 2024-01-31
| Shushah Island - KUARTZ Tower Design Services - RBTA |  |  |  |  | Client acceptance | 100% | 100% |  |  |  |  | OK |  | 1.1 | [10 empty] | 2024-06-25 | 2024-10-16 | 186 | 60 | Dormant since 2024-10-16
| Design Review Services of a Fishing Harbour At Kilwa Masoko – Lindi Region |  |  |  |  | Comment closeout confirmed | 100% | 100% |  |  |  |  | OK |  | 0.75 | [10 empty] | 2023-12-18 | 2024-01-04 | 10 | 11 | Dormant since 2024-01-04
| Construction of the Offsite Works for the Multifunctional Conference Center |  |  |  |  | Option selected and frozen | 65% | 65% |  |  |  |  | OK |  | 1.1 | [10 empty] | 0 | 0 | 0 | 0 | Never charged
| Construction of the Port Terminal for the Free Zone of the Integrated Development of Barra do Dande (ZFDIBD) |  |  |  |  | Concept report and drawings issued | 90% | 90% |  |  |  |  | OK |  | 1.1 | [10 empty] | 2024-06-13 | 2025-04-10 | 164.5 | 200 | Dormant since 2025-04-10
| Requalification of the Corimba Coastline - Praia da Areia Branca |  |  |  |  | Concept report and drawings issued | 90% | 90% |  |  |  |  | OK |  | 1.1 | [10 empty] | 2025-07-28 | 2025-10-01 | 171 | 18 | Dormant since 2025-10-01
| Rehabilitation of the Main Piers of the Terminal Port at Kwanda Base |  |  |  |  | Documents received and logged | 10% | 10% |  |  |  |  | OK |  | 0.75 | [10 empty] | 2024-12-05 | 2026-02-04 | 93 | 293 | Dormant since 2026-02-04
| Comoros Inter-Island connectivity - Expansion works of the BOINGOMA port in Mohéli |  |  |  |  | Transmitted to client (IFA/IFC) | 85% | 85% |  |  |  |  | OK |  | 1 | [10 empty] | 2025-10-27 | 2026-06-25 | 568.5 | 118 | Dormant since 2026-06-25
| Requalification of Luanda Naval Base |  |  |  |  | Documents received and logged | 10% | 10% |  |  |  |  | OK |  | 0.75 | [10 empty] | 2024-10-15 | 2025-10-15 | 338.75 | 211 | Dormant since 2025-10-15
| Construction of Fertilizer Complex in Soyo |  |  |  |  | Documents received and logged | 10% | 10% |  |  |  |  | OK |  | 0.75 | [10 empty] | 2025-02-05 | 2026-07-12 | 153 | 347 | Dormant since 2026-07-12
| Consultancy Services for Design Review for The Development of Kisiwa / MGAO Port in Mtwara. |  |  |  |  | Review complete internally | 60% | 60% |  |  |  |  | OK |  | 0.75 | [10 empty] | 2025-04-15 | 2026-04-06 | 262.25 | 212 | Dormant since 2026-04-06
| JCDC Detailed Masterplan & Engineering - MBS Bay - Urban Development |  |  |  |  | Client acceptance | 100% | 100% |  |  |  |  | OK |  | 1.1 | [10 empty] | 0 | 0 | 0 | 0 | Never charged
| Waterfront Villas Development, Plot P2, Sector Qasr AI Mugheirah, Zone AI Marfa, AI Dhafra Region, Abu Dhabi, UAE |  |  |  |  | Client acceptance | 100% | 100% |  |  |  |  | OK |  | 1.1 | [10 empty] | 0 | 0 | 0 | 0 | Never charged
| AOR/EOR & Engineering Services Sazan Development | [11 empty] | OK |  | 1.1 | [10 empty] | 0 | 0 | 0 | 0 | Never charged
| Chargable Proposals of 2026 |  |  |  |  | Proposal in preparation | 50% | 50% |  |  |  |  | OK |  | 0.7 | [10 empty] | 2026-02-25 | 2026-05-14 | 61.25 | 57 | Dormant since 2026-05-14
| Proposals of 2026 |  |  |  |  | Proposal in preparation | 50% | 50% |  |  |  |  | OK |  | 0.7 | [10 empty] | 2026-01-19 | 2026-03-12 | 13 | 39 | Dormant since 2026-03-12
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Actual start (timesheet) = IF([Project Number]="","",IFERROR('Deliverable Actuals'!$[Engineer 1 %],""))
Last activity (timesheet) = IF([Project Number]="","",IFERROR('Deliverable Actuals'!$[Engineer 2 %],""))

## Profit Plan
PROFIT PLAN — OPTIMUM DELIVERY SEQUENCE FOR THE PLAN YEAR
Objective: maximise Earned MM less Actual MM. Every open deliverable is ranked by value earned per man-month spent, then capacity is filled from the top. Under a single capacity constraint that ranking is the profit-maximising order. Blue cells are inputs.
1 — ASSUMPTIONS |  |  | 2 — POSITION THIS YEAR SO FAR (follows the Dashboard filter) |  |  |  | 3 — THE OPTIMUM PLAN FOR THE REST OF THE YEAR |  |  | 5 — NEXT FOUR MONTHS: HOW THE HOURS AND THE RESULT SPLIT
Hours per man-month | 185 |  | Dashboard period shown | Full year 2026 |  |  | Deliverables to do | 27 |  |  | 1 | 2 | 3 | 4
Plan year | 2026 |  | Actual MM booked | 17.9081 |  |  | MM committed | 11.8139 |  | Month | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | TOTAL
As-at date | 2026-09-01 |  | Earned MM delivered | 14.1861 |  |  | Hours committed | 2185.5625 |  | Hours planned | 555 | 555 | 555 | 520.5625 | 2185.5625
Team capacity per month (MM) | 3 |  | Profit / (Loss) so far (MM) | -3.722 |  |  | Capacity used | 99.28% |  | MM planned | 3 | 3 | 3 | 2.8139 | 11.8139
Full-year capacity (MM) | 36 |  | Efficiency (CPI) so far | 0.79216 |  |  | Value to be earned (MM) | 26.699 |  | Capacity MM | 3 | 3 | 3 | 3 | 12
Capacity elapsed to date (MM) | 24.1 |  | Filter check | OK - matches plan year |  |  | Profit added by the plan (MM) | 14.8851 |  | Utilisation | 100% | 100% | 100% | 93.8% | 98.45%
Capacity left this year (MM) | 11.9 | [5 empty] | Projected year-end profit (MM) | 11.1632 |  | Value earned in month (MM) | 2.1811 | 2.1 | 2.1 | 3.1147 | 9.4958
Capacity left this year (hours) | 2201.5 |  | Implied CPI of this plan | 2.26 |  |  | vs target | 11.1632 |  | Profit in month (MM) | -0.81892 | -0.9 | -0.9 | 0.30088 | -2.318
Default CPI when a project has no history | 1 |  | Credibility check | NOT CREDIBLE - implied 2.26x is above the 2.00x ceiling; expected hours are too optimistic |  |  | Verdict | Target met with the work available |  | Year profit at month end (MM) | -4.5409 | -5.4409 | -6.3409 | -6.04
Target profit for the year (MM) | 0 | [8 empty] | Deliverables finished in month | 8 | 6 | 6 | 7 | 27
Lowest CPI allowed in the plan | 0.7 |  | REALITY CHECK - SAME CAPACITY AT HISTORICAL CPI |  |  |  | HOURS BY ENGINEER
Highest CPI allowed in the plan | 2 |  | Value earned on remaining capacity (MM) | 9.4267 |  |  | Ahmed | 775.0375 |  | HOURS BY ENGINEER PER MONTH
|  |  | Profit / (loss) added (MM) | -2.4733 |  |  | Osama | 729.6 |  | Ahmed | 273.3 | 165.1 | 83.25 | 253.3875 | 775.0375
HOW TO READ THIS AND HOW TO CLOSE THE GAP |  |  | Projected year-end profit (MM) | -6.1952 |  |  | Kirolos | 680.925 |  | Osama | 164.4 | 314.4 | 159.05 | 91.75 | 729.6
The best plan available uses 11.81 of the 11.90 MM left this year (2,186 hours), adds 14.89 MM of profit and leaves the year at 11.16 MM. |  |  | CPI needed just to break even for the year | 1.3128 |  |  | Unassigned (no split entered) | 0 |  | Kirolos | 117.3 | 75.5 | 312.7 | 175.425 | 680.925
Do this one first: Final Design - Apapa Berth 12 on N25185-0100D - 3.46 MM earned per MM spent, 50 hours. | [9 empty] | Unassigned (no split entered) | 1.1369e-13 | 0 | 0 | 0 | 1.1369e-13
Profit here is earned value less man-months spent, so a deliverable only adds profit where its project's assumed CPI is above 1.00x. Finishing work on an overrunning project still costs more than it earns — it protects the client relationship, not this year's number. | [6 empty] | DEFERRED TO NEXT YEAR |  |  | Hours per person available | 185 | 185 | 185 | 185 | 740
Lever 1 - override the estimate in hours. Where you know the real effort still needed, type the hours in column K (Expected Hours). That replaces the CPI-derived figure, re-ranks the plan and re-flows the monthly loading and each engineer's hours instantly. | [6 empty] | Deliverables deferred | 5 |  | Overload check (busiest person) | OVER by 88 hrs | OVER by 129 hrs | OVER by 128 hrs | OVER by 68 hrs
Lever 2 — fix missing actuals. An understated CPI (unlogged time on Phasing) makes profitable work look unprofitable and pushes it down the ranking. Check the projects reading at the 2.00x ceiling first. | [6 empty] | MM required | 16.2529 |  | Hours are loaded in rank order against the team's monthly capacity, so a deliverable straddling a month boundary is split across both months. Columns X:AA in the table show each deliverable's hours per month.
Lever 3 — only the deferred list can add more. Anything marked DEFER needs capacity you do not have this year; winning new work will not help the profit figure until it earns credit. | [6 empty] | Value left on the table (MM) | 17.1125
4 — DELIVERABLE PLAN (one row per register entry; ranked by value earned per man-month) | [22 empty] | 1 | 2 | 3 | 4
Project | Deliverable / Phase | Type | Status now | Project Status | Credit now | Credit left | Deliverable Budget MM | Earned to Date MM | Remaining Value MM | Expected Hours (override) | MM to Finish | Hours to Finish | Value per MM | Priority Score | Rank | Cumulative MM | Decision | Profit Contribution MM | Ahmed hrs | Osama hrs | Kirolos hrs | Assumed CPI (clamped) | Oct 26 hrs | Nov 26 hrs | Dec 26 hrs | Jan 27 hrs
N25178-0100D | Concept Design | CD | Option selected and frozen | Active | 65% | 35% | 2.4 | 1.56 | 0.84 | 85 | 0.45946 | 85 | 1.8282 | 1.8282 | 27 | 11.8139 | DO | 0.38054 | 85 | 0 | 0 | 1 | 0 | 0 | 0 | 85
E26084-0100D | Schematic Design | CD | Option selected and frozen | Active | 65% | 35% | 0.75 | 0.4875 | 0.2625 | 100 | 0.54054 | 100 | 0.48562 | 0.4856 | 32 | 28.0667 | DEFER |  |  |  |  | 2
E26084-0100D | Final Design | DD |  | Active | 0% | 100% | 2.25 | 0 | 2.25 | 300 | 1.6216 | 300 | 1.3875 | 1.3875 | 29 | 15.5976 | DEFER |  |  |  |  | 2
N25185-0100D | Concept Design | CD | Client acceptance | Active | 100% | 0% | 4.16 | 4.16 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 0.7
N25185-0100D | Final Design - Tin Can Berth 1 | DD |  | Active | 0% | 100% | 1.04 | 0 | 1.04 | 90 | 0.48649 | 90 | 2.1378 | 2.1377 | 12 | 4.8541 | DO | 0.55351 | 13.5 | 54 | 22.5 | 0.7 | 0 | 90 | 0 | 0
N25185-0100D | Final Design - Tin Can Berth 2 | DD |  | Active | 0% | 100% | 1.04 | 0 | 1.04 | 90 | 0.48649 | 90 | 2.1378 | 2.1377 | 13 | 5.3405 | DO | 0.55351 | 13.5 | 54 | 22.5 | 0.7 | 0 | 90 | 0 | 0
N25185-0100D | Final Design - Tin Can Berth 3 | DD |  | Active | 0% | 100% | 1.04 | 0 | 1.04 | 90 | 0.48649 | 90 | 2.1378 | 2.1377 | 14 | 5.827 | DO | 0.55351 | 13.5 | 54 | 22.5 | 0.7 | 0 | 90 | 0 | 0
N25185-0100D | Final Design - Tin Can Berth 4 | DD |  | Active | 0% | 100% | 1.04 | 0 | 1.04 | 90 | 0.48649 | 90 | 2.1378 | 2.1377 | 15 | 6.3135 | DO | 0.55351 | 13.5 | 54 | 22.5 | 0.7 | 0 | 32 | 58 | 0
N25185-0100D | Final Design - Tin Can Berth 5 | DD | Transmitted to client (IFA/IFC) | Active | 85% | 15% | 1.04 | 0.884 | 0.156 | 12 | 0.064865 | 12 | 2.405 | 2.405 | 5 | 1.1459 | DO | 0.091135 | 5.4 | 5.4 | 1.2 | 0.7 | 12 | 0 | 0 | 0
N25185-0100D | Final Design - Tin Can Berth 6 | DD | Transmitted to client (IFA/IFC) | Active | 85% | 15% | 1.04 | 0.884 | 0.156 | 12 | 0.064865 | 12 | 2.405 | 2.405 | 6 | 1.2108 | DO | 0.091135 | 5.4 | 5.4 | 1.2 | 0.7 | 12 | 0 | 0 | 0
N25185-0100D | Final Design - Tin Can Berth 7 | DD | Transmitted to client (IFA/IFC) | Active | 85% | 15% | 1.04 | 0.884 | 0.156 | 12 | 0.064865 | 12 | 2.405 | 2.405 | 7 | 1.2757 | DO | 0.091135 | 5.4 | 5.4 | 1.2 | 0.7 | 12 | 0 | 0 | 0
N25185-0100D | Final Design - Tin Can Berth 8 | DD | Transmitted to client (IFA/IFC) | Active | 85% | 15% | 1.04 | 0.884 | 0.156 | 12 | 0.064865 | 12 | 2.405 | 2.405 | 8 | 1.3405 | DO | 0.091135 | 5.4 | 5.4 | 1.2 | 0.7 | 12 | 0 | 0 | 0
N25185-0100D | Final Design - Tin Can Berth 9 | DD | Design started | Active | 10% | 90% | 1.04 | 0.104 | 0.936 | 80 | 0.43243 | 80 | 2.1645 | 2.1645 | 10 | 3.9351 | DO | 0.50357 | 32 | 48 | 0 | 0.7 | 0 | 80 | 0 | 0
N25185-0100D | Final Design - Tin Can Berth 10 | DD | Design started | Active | 10% | 90% | 1.04 | 0.104 | 0.936 | 80 | 0.43243 | 80 | 2.1645 | 2.1645 | 11 | 4.3676 | DO | 0.50357 | 32 | 48 | 0 | 0.7 | 0 | 80 | 0 | 0
N25185-0100D | Final Design - Apapa Berth 4 | DD |  | Active | 0% | 100% | 1.04 | 0 | 1.04 | 90 | 0.48649 | 90 | 2.1378 | 2.1377 | 16 | 6.8 | DO | 0.55351 | 13.5 | 22.5 | 54 | 0.7 | 0 | 0 | 90 | 0
N25185-0100D | Final Design - Apapa Berth 5 | DD |  | Active | 0% | 100% | 1.04 | 0 | 1.04 | 90 | 0.48649 | 90 | 2.1378 | 2.1377 | 17 | 7.2865 | DO | 0.55351 | 13.5 | 22.5 | 54 | 0.7 | 0 | 0 | 90 | 0
N25185-0100D | Final Design - Apapa Berth 6 | DD |  | Active | 0% | 100% | 1.04 | 0 | 1.04 | 90 | 0.48649 | 90 | 2.1378 | 2.1377 | 18 | 7.773 | DO | 0.55351 | 13.5 | 22.5 | 54 | 0.7 | 0 | 0 | 90 | 0
N25185-0100D | Final Design - Apapa Berth 7 | DD |  | Active | 0% | 100% | 1.04 | 0 | 1.04 | 90 | 0.48649 | 90 | 2.1378 | 2.1377 | 19 | 8.2595 | DO | 0.55351 | 13.5 | 22.5 | 54 | 0.7 | 0 | 0 | 90 | 0
N25185-0100D | Final Design - Apapa Berth 8 | DD |  | Active | 0% | 100% | 1.04 | 0 | 1.04 | 90 | 0.48649 | 90 | 2.1378 | 2.1377 | 20 | 8.7459 | DO | 0.55351 | 13.5 | 22.5 | 54 | 0.7 | 0 | 0 | 90 | 0
N25185-0100D | Final Design - Apapa Berth 9 | DD |  | Active | 0% | 100% | 1.04 | 0 | 1.04 | 90 | 0.48649 | 90 | 2.1378 | 2.1377 | 21 | 9.2324 | DO | 0.55351 | 13.5 | 22.5 | 54 | 0.7 | 0 | 0 | 47 | 43
N25185-0100D | Final Design - Apapa Berth 10 | DD |  | Active | 0% | 100% | 1.04 | 0 | 1.04 | 90 | 0.48649 | 90 | 2.1378 | 2.1377 | 22 | 9.7189 | DO | 0.55351 | 13.5 | 22.5 | 54 | 0.7 | 0 | 0 | 0 | 90
N25185-0100D | Final Design - Apapa Berth 11 | DD |  | Active | 0% | 100% | 1.04 | 0 | 1.04 | 90 | 0.48649 | 90 | 2.1378 | 2.1377 | 23 | 10.2054 | DO | 0.55351 | 13.5 | 22.5 | 54 | 0.7 | 0 | 0 | 0 | 90
N25185-0100D | Final Design - Apapa Berth 12 | DD | Design started | Active | 10% | 90% | 1.04 | 0.104 | 0.936 | 50 | 0.27027 | 50 | 3.4632 | 3.4632 | 1 | 0.27027 | DO | 0.66573 | 12.5 | 0 | 37.5 | 0.7 | 50 | 0 | 0 | 0
N25185-0100D | Final Design - Apapa Berth 13 | DD | Design started | Active | 10% | 90% | 1.04 | 0.104 | 0.936 | 50 | 0.27027 | 50 | 3.4632 | 3.4632 | 2 | 0.54054 | DO | 0.66573 | 12.5 | 0 | 37.5 | 0.7 | 50 | 0 | 0 | 0
N25185-0100D | Final Design - Apapa Berth 14 | DD | Design started | Active | 10% | 90% | 1.04 | 0.104 | 0.936 | 50 | 0.27027 | 50 | 3.4632 | 3.4631 | 3 | 0.81081 | DO | 0.66573 | 12.5 | 0 | 37.5 | 0.7 | 50 | 0 | 0 | 0
AN22137-0100D | Schematic Design | CD |  | Not Started | 0% | 100% | 5 | 0 | 5 | 400 | 2.1622 | 400 | 2.3125 | 2.3124 | 9 | 3.5027 | DO | 2.8378 | 240 | 160 | 0 | 0.7 | 307 | 93 | 0 | 0
D26058-0100D | Concept Design | CD |  | Not Started | 0% | 100% | 0.75 | 0 | 0.75 | 50 | 0.27027 | 50 | 2.775 | 2.7749 | 4 | 1.0811 | DO | 0.47973 | 30 | 20 | 0 | 1 | 50 | 0 | 0 | 0
D26058-0100D | Schematic Design | CD |  | Not Started | 0% | 100% | 1 | 0 | 1 | 90 | 0.48649 | 90 | 2.0556 | 2.0555 | 24 | 10.6919 | DO | 0.51351 | 54 | 36 | 0 | 1 | 0 | 0 | 0 | 90
D26058-0100D | Final Design | CD |  | Not Started | 0% | 100% | 3.25 | 0 | 3.25 | 400 | 2.1622 | 400 | 1.5031 | 1.5031 | 28 | 13.976 | DEFER |  |  |  |  | 1
AD24217-0100D | Concept Design | CD | Client acceptance | Finalized | 100% | 0% | 3 | 3 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 1.1538
E24181-0100D | Report | SA | Comments closed | Finalized | 100% | 0% | 0.5 | 0.5 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 1
J23152-0100D | Specifications | TD | Tender queries and addenda closed | Finalized | 100% | 0% | 0.5 | 0.5 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 2
Q25008-0100D | Tender Design | TD | Tender queries and addenda closed | Finalized | 100% | 0% | 5 | 5 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 2
S24014-0101D | Report | SA | Comments closed | Finalized | 100% | 0% | 21.27 | 21.27 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 2
S24014-0102D | Concept Design | CD | Client acceptance | Finalized | 100% | 0% | 7.62 | 7.62 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 2
S24014-0103D | Concept Design | CD | Client acceptance | Finalized | 100% | 0% | 6.36 | 6.36 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 1.4621
S24014-0104D | Report | SA | Comments closed | Finalized | 100% | 0% | 12.03 | 12.03 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 2
S22058-0700D | Concept Design | CD | Client acceptance | Finalized | 100% | 0% | 6 | 6 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 1.1727
AN24185-0100R | Design Review | DR | Comment closeout confirmed | Finalized | 100% | 0% | 4 | 4 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 1.351
AN23232-0100D | Concept Design | CD | Client acceptance | Finalized | 100% | 0% | 3 | 3 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 0.90835
S22058-0400D | Concept Design | CD | Client acceptance | Finalized | 100% | 0% | 0.5 | 0.5 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 2
Proposals 25 | Proposals | PP | Proposal submitted | Finalized | 100% | 0% | 1.9 | 1.9 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 0.9118
Chargable Proposals 25 | Proposals | PP | Proposal submitted | Finalized | 100% | 0% | 3 | 3 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 0.7608
AN21146-0100R | Design Review | DR | Comment closeout confirmed | Finalized | 100% | 0% | 3 | 3 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 2
N23106-0100D | Concept Design | CD | Client acceptance | Finalized | 100% | 0% | 5 | 5 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 1.5053
OM23030-0100D | Tender Design | TD | Tender queries and addenda closed | Finalized | 100% | 0% | 0.25 | 0.25 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 1.6972
Chargable Proposals 24 | Proposals | PP | Proposal submitted | Finalized | 100% | 0% | 2.25 | 2.25 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 1.2136
Proposals 24 | Proposals | PP | Proposal submitted | Finalized | 100% | 0% | 1.1 | 1.1 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 2
S23204-0100D | Concept Design | CD | Client acceptance | Finalized | 100% | 0% | 1.5 | 1.5 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 2
S24100-0100D | Concept Design | CD | Client acceptance | Finalized | 100% | 0% | 3 | 3 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 2
TA23011-0100R | Design Review | DR | Comment closeout confirmed | Finalized | 100% | 0% | 0.1 | 0.1 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 1.85
AN23207-0500D | Concept Design | CD | Option selected and frozen | On Hold | 65% | 35% | 1.15 | 0.7475 | 0.4025 |  | 0.4025 | 74.4625 | 1 |  |  |  | not in scope |  |  |  |  | 1
AN23276-0100D | Concept Design | CD | Concept report and drawings issued | On Hold | 90% | 10% | 5 | 4.5 | 0.5 |  | 0.25 | 46.25 | 2 |  |  |  | not in scope |  |  |  |  | 2
AN24073-0100D | Concept Design | CD | Concept report and drawings issued | On Hold | 90% | 10% | 1.25 | 1.125 | 0.125 |  | 0.1027 | 19 | 1.2171 |  |  |  | not in scope |  |  |  |  | 1.2171
AN24140-0100R | Design Review | DR | Documents received and logged | Active | 10% | 90% | 1.5 | 0.15 | 1.35 |  | 1.9286 | 356.7857 | 0.7 | 0.69992 | 31 | 27.5262 | DEFER |  |  |  |  | 0.7
CS24035-0100D | Detailed Design | DD | Transmitted to client (IFA/IFC) | On Hold | 85% | 15% | 4 | 3.4 | 0.6 |  | 0.55278 | 102.2647 | 1.0854 |  |  |  | not in scope |  |  |  |  | 1.0854
AN24135-0100R | Design Review | DR | Documents received and logged | On Hold | 10% | 90% | 4 | 0.4 | 3.6 |  | 5.1429 | 951.4286 | 0.7 |  |  |  | not in scope |  |  |  |  | 0.7
AN23108-0100R | Design Review | DR | Documents received and logged | On Hold | 10% | 90% | 2 | 0.2 | 1.8 |  | 2.5714 | 475.7143 | 0.7 |  |  |  | not in scope |  |  |  |  | 0.7
TA24246-0200R | Design Review | DR | Review complete internally | On Hold | 60% | 40% | 1 | 0.6 | 0.4 |  | 0.57143 | 105.7143 | 0.7 |  |  |  | not in scope |  |  |  |  | 0.7
S22058-0900D | Concept Design | CD | Client acceptance | Cancelled | 100% | 0% | 0.25 | 0.25 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 2
AD23051-0101D | Concept Design | CD | Client acceptance | Cancelled | 100% | 0% | 0.5 | 0.5 | 0 |  | 0 | 0 |  |  |  |  | complete |  |  |  |  | 2
AL25148-0100D | Concept Design | CD |  | Not Started | 0% | 100% | 10 | 0 | 10 |  | 10 | 1850 | 1 | 0.99991 | 30 | 25.5976 | DEFER |  |  |  |  | 1
Chargable Proposals 26 | Proposals | PP | Proposal in preparation | Active | 50% | 50% | 2.25 | 1.125 | 1.125 |  | 0.5625 | 104.0625 | 2 | 1.9999 | 25 | 11.2544 | DO | 0.5625 | 62.4375 | 0 | 41.625 | 2 | 0 | 0 | 0 | 104.0625
Proposals 26 | Proposals | PP | Proposal in preparation | Active | 50% | 50% | 0.4 | 0.2 | 0.2 |  | 0.1 | 18.5 | 2 | 1.9999 | 26 | 11.3544 | DO | 0.1 | 18.5 | 0 | 0 | 2 | 0 | 0 | 0 | 18.5
Note on B5: Ahmed Mitwally: Agreed conversion for reporting hours. Change here and every hours figure on this sheet follows.
Note on B13: Ahmed Mitwally: How many man-months it takes to earn one man-month of budget value. 1.00 = on budget. Raise it above 1.00 to plan pessimistically. Used only where you have not typed a deliverable-specific estimate.
Note on B14: Ahmed Mitwally: 0.00 = break even for the year. Set a positive figure to plan for surplus.
Note on B15: Ahmed Mitwally: Floor on the assumed CPI. Stops a badly overrun project from demanding an absurd number of man-months to finish.
Note on B16: Ahmed Mitwally: Ceiling on the assumed CPI. The Definitions sheet warns that a CPI above about 2.00x usually means missing actuals rather than genuine efficiency, so the plan will not reward it.
Note on K26: Ahmed Mitwally: Type the hours you expect the deliverable still needs. This replaces the CPI-derived estimate and re-ranks the whole plan. Leave blank to let the CPI drive it. Hours are converted to man-months at the rate in B5.

## Support Plan
SUPPORT PLAN - BENGALURU AND DRAFTSMAN SUPPORT PER DELIVERABLE
One row per deliverable, same order as the Deliverables register. Blue cells are yours to fill. Cairo hours come from the timesheet automatically. Where the planned office and the delivered office differ, the row is flagged and the hours Cairo had to absorb are calculated - that is the capacity cost of the shift.
Project | Deliverable / Phase | PLANNED office | PLANNED Bengaluru hrs | PLANNED draftsman hrs | DELIVERED office | Office shift date | Shift reason | ACTUAL Bengaluru hrs | ACTUAL draftsman hrs | Cairo hrs (timesheet) | Total delivered hrs | Cairo share | Bengaluru share | Draftsman share | Bengaluru shortfall hrs | Shift status | SUPPORT SUMMARY
N25178-0100D | Concept Design | [8 empty] | 0 | 0 |  |  |  | 0 | not set | Deliverables with a planned office set | 0
E26084-0100D | Schematic Design | [8 empty] | 0 | 0 |  |  |  | 0 | not set | Deliverables shifted away from plan | 0
E26084-0100D | Final Design | [8 empty] | 0 | 0 |  |  |  | 0 | not set | PLANNED Bengaluru hrs | 0
N25185-0100D | Concept Design | [8 empty] | 1650.75 | 1650.75 | 100% | 0% | 0% | 0 | not set | ACTUAL Bengaluru hrs | 0
N25185-0100D | Final Design - Tin Can Berth 1 | [8 empty] | 0 | 0 |  |  |  | 0 | not set | Bengaluru shortfall hrs (absorbed by Cairo) | 0
N25185-0100D | Final Design - Tin Can Berth 2 | [8 empty] | 0 | 0 |  |  |  | 0 | not set | Shortfall in man-months | 0
N25185-0100D | Final Design - Tin Can Berth 3 | [8 empty] | 0 | 0 |  |  |  | 0 | not set | PLANNED draftsman hrs | 0
N25185-0100D | Final Design - Tin Can Berth 4 | [8 empty] | 0 | 0 |  |  |  | 0 | not set | ACTUAL draftsman hrs | 0
N25185-0100D | Final Design - Tin Can Berth 5 | [8 empty] | 197.1944 | 197.1944 | 100% | 0% | 0% | 0 | not set | Total delivered hrs | 11970
N25185-0100D | Final Design - Tin Can Berth 6 | [8 empty] | 197.1944 | 197.1944 | 100% | 0% | 0% | 0 | not set | Cairo share of delivery | 100%
N25185-0100D | Final Design - Tin Can Berth 7 | [8 empty] | 197.1944 | 197.1944 | 100% | 0% | 0% | 0 | not set | Bengaluru share of delivery | 0%
N25185-0100D | Final Design - Tin Can Berth 8 | [8 empty] | 197.1944 | 197.1944 | 100% | 0% | 0% | 0 | not set | Draftsman share of delivery | 0%
N25185-0100D | Final Design - Tin Can Berth 9 | [8 empty] | 197.1944 | 197.1944 | 100% | 0% | 0% | 0 | not set
N25185-0100D | Final Design - Tin Can Berth 10 | [8 empty] | 197.1944 | 197.1944 | 100% | 0% | 0% | 0 | not set
N25185-0100D | Final Design - Apapa Berth 4 | [8 empty] | 0 | 0 |  |  |  | 0 | not set
N25185-0100D | Final Design - Apapa Berth 5 | [8 empty] | 0 | 0 |  |  |  | 0 | not set
N25185-0100D | Final Design - Apapa Berth 6 | [8 empty] | 0 | 0 |  |  |  | 0 | not set
N25185-0100D | Final Design - Apapa Berth 7 | [8 empty] | 0 | 0 |  |  |  | 0 | not set
N25185-0100D | Final Design - Apapa Berth 8 | [8 empty] | 0 | 0 |  |  |  | 0 | not set
N25185-0100D | Final Design - Apapa Berth 9 | [8 empty] | 0 | 0 |  |  |  | 0 | not set
N25185-0100D | Final Design - Apapa Berth 10 | [8 empty] | 0 | 0 |  |  |  | 0 | not set
N25185-0100D | Final Design - Apapa Berth 11 | [8 empty] | 0 | 0 |  |  |  | 0 | not set
N25185-0100D | Final Design - Apapa Berth 12 | [8 empty] | 197.1944 | 197.1944 | 100% | 0% | 0% | 0 | not set
N25185-0100D | Final Design - Apapa Berth 13 | [8 empty] | 197.1944 | 197.1944 | 100% | 0% | 0% | 0 | not set
N25185-0100D | Final Design - Apapa Berth 14 | [8 empty] | 197.1944 | 197.1944 | 100% | 0% | 0% | 0 | not set
AN22137-0100D | Schematic Design | [8 empty] | 0 | 0 |  |  |  | 0 | not set
D26058-0100D | Concept Design | [8 empty] | 0 | 0 |  |  |  | 0 | not set
D26058-0100D | Schematic Design | [8 empty] | 0 | 0 |  |  |  | 0 | not set
D26058-0100D | Final Design | [8 empty] | 0 | 0 |  |  |  | 0 | not set
AD24217-0100D | Concept Design | [8 empty] | 363.75 | 363.75 | 100% | 0% | 0% | 0 | not set
E24181-0100D | Report | [8 empty] | 0 | 0 |  |  |  | 0 | not set
J23152-0100D | Specifications | [8 empty] | 17.5 | 17.5 | 100% | 0% | 0% | 0 | not set
Q25008-0100D | Tender Design | [8 empty] | 357 | 357 | 100% | 0% | 0% | 0 | not set
S24014-0101D | Report | [8 empty] | 451.75 | 451.75 | 100% | 0% | 0% | 0 | not set
S24014-0102D | Concept Design | [8 empty] | 491.25 | 491.25 | 100% | 0% | 0% | 0 | not set
S24014-0103D | Concept Design | [8 empty] | 804.75 | 804.75 | 100% | 0% | 0% | 0 | not set
S24014-0104D | Report | [8 empty] | 225 | 225 | 100% | 0% | 0% | 0 | not set
S22058-0700D | Concept Design | [8 empty] | 946.5 | 946.5 | 100% | 0% | 0% | 0 | not set
AN24185-0100R | Design Review | [8 empty] | 547.75 | 547.75 | 100% | 0% | 0% | 0 | not set
AN23232-0100D | Concept Design | [8 empty] | 403.75 | 403.75 | 100% | 0% | 0% | 0 | not set
S22058-0400D | Concept Design | [8 empty] | 7.5 | 7.5 | 100% | 0% | 0% | 0 | not set
Proposals 25 | Proposals | [8 empty] | 385.5 | 385.5 | 100% | 0% | 0% | 0 | not set
Chargable Proposals 25 | Proposals | [8 empty] | 729.5 | 729.5 | 100% | 0% | 0% | 0 | not set
AN21146-0100R | Design Review | [8 empty] | 96 | 96 | 100% | 0% | 0% | 0 | not set
N23106-0100D | Concept Design | [8 empty] | 217.75 | 217.75 | 100% | 0% | 0% | 0 | not set
OM23030-0100D | Tender Design | [8 empty] | 27.25 | 27.25 | 100% | 0% | 0% | 0 | not set
Chargable Proposals 24 | Proposals | [8 empty] | 343 | 343 | 100% | 0% | 0% | 0 | not set
Proposals 24 | Proposals | [8 empty] | 99.25 | 99.25 | 100% | 0% | 0% | 0 | not set
S23204-0100D | Concept Design | [8 empty] | 8.5 | 8.5 | 100% | 0% | 0% | 0 | not set
S24100-0100D | Concept Design | [8 empty] | 186 | 186 | 100% | 0% | 0% | 0 | not set
TA23011-0100R | Design Review | [8 empty] | 10 | 10 | 100% | 0% | 0% | 0 | not set
AN23207-0500D | Concept Design | [8 empty] | 0 | 0 |  |  |  | 0 | not set
AN23276-0100D | Concept Design | [8 empty] | 164.5 | 164.5 | 100% | 0% | 0% | 0 | not set
AN24073-0100D | Concept Design | [8 empty] | 171 | 171 | 100% | 0% | 0% | 0 | not set
AN24140-0100R | Design Review | [8 empty] | 93 | 93 | 100% | 0% | 0% | 0 | not set
CS24035-0100D | Detailed Design | [8 empty] | 568.5 | 568.5 | 100% | 0% | 0% | 0 | not set
AN24135-0100R | Design Review | [8 empty] | 338.75 | 338.75 | 100% | 0% | 0% | 0 | not set
AN23108-0100R | Design Review | [8 empty] | 153 | 153 | 100% | 0% | 0% | 0 | not set
TA24246-0200R | Design Review | [8 empty] | 262.25 | 262.25 | 100% | 0% | 0% | 0 | not set
S22058-0900D | Concept Design | [8 empty] | 0 | 0 |  |  |  | 0 | not set
AD23051-0101D | Concept Design | [8 empty] | 0 | 0 |  |  |  | 0 | not set
AL25148-0100D | Concept Design | [8 empty] | 0 | 0 |  |  |  | 0 | not set
Chargable Proposals 26 | Proposals | [8 empty] | 61.25 | 61.25 | 100% | 0% | 0% | 0 | not set
Proposals 26 | Proposals | [8 empty] | 13 | 13 | 100% | 0% | 0% | 0 | not set

## Proposals
PROPOSALS - REAL PROPOSAL NUMBERS FROM THE TIMESHEET
The list in column A builds itself from Timesheet Raw - every job booked under a proposal job type. It grows and shrinks with the data, so a new proposal appears automatically after each monthly paste. Yearly totals on the right feed the Proposals rows in the Deliverables register.
Proposal number | Type | 2024 | 2025 | 2026 | Total hrs | Total MM | Ahmed hrs | Osama hrs | Kirolos hrs | First charge | Last charge | YEARLY TOTALS
PAL251195C | 2-Proposals Chargeable | 0 | 0 | 20 | 20 | 0.10811 | 6.5 | 0 | 13.5 | 2026-02-25 | 2026-02-26 | Year | Proposals used | Total hrs | Total MM | Chargeable hrs
PAN221498C | 2-Proposals Chargeable | 0 | 2 | 0 | 2 | 0.010811 | 2 | 0 | 0 | 2025-04-14 | 2025-04-14 | 2024 | 10 | 442.25 | 2.3905 | 343
PAN260617C | 2-Proposals Chargeable | 0 | 0 | 34.25 | 34.25 | 0.18514 | 6.75 | 0 | 27.5 | 2026-05-12 | 2026-05-14 | 2025 | 19 | 1115 | 6.027 | 729.5
PBZ250409 | 3-Proposals Regular | 0 | 3 | 0 | 3 | 0.016216 | 3 | 0 | 0 | 2025-04-06 | 2025-04-07 | 2026 | 6 | 74.25 | 0.40135 | 61.25
PD17045 | 3-Proposals Regular | 0 | 0 | 0 | 0 | 0 | 8.5 | 0 | 0 | 2017-05-02 | 2017-05-02
PE17262 | 2-Proposals Chargeable | 0 | 0 | 0 | 0 | 0 | 152.75 | 0 | 0 | 2019-07-08 | 2019-08-25
PE240049C | 2-Proposals Chargeable | 44.75 | 0 | 0 | 44.75 | 0.24189 | 5 | 39.75 | 0 | 2024-04-15 | 2024-06-06 | REGISTER LINK - hours behind each Proposals row in the Deliverables register
PE241280C-04 | 2-Proposals Chargeable | 45.5 | 0 | 0 | 45.5 | 0.24595 | 0 | 8.75 | 36.75 | 2024-12-11 | 2024-12-26 | Register label | Year | Job type | Hours | First charge | Last charge
PE241280C-09 | 2-Proposals Chargeable | 34.5 | 164.75 | 0 | 199.25 | 1.077 | 73.25 | 68.25 | 57.75 | 2024-12-23 | 2025-01-19 | Proposals 24 | 2024 | 3-Proposals Regular | 99.25 | 2024-02-05 | 2024-12-18
PE241280C-12 | 2-Proposals Chargeable | 0 | 7.25 | 0 | 7.25 | 0.039189 | 7.25 | 0 | 0 | 2025-03-19 | 2025-03-19 | Chargable Proposals 24 | 2024 | 2-Proposals Chargeable | 343 | 2024-02-01 | 2024-12-30
PECO231523C | 2-Proposals Chargeable | 0 | 31.5 | 7 | 38.5 | 0.20811 | 144.75 | 22.75 | 0 | 2023-10-24 | 2026-03-25 | Proposals 25 | 2025 | 3-Proposals Regular | 385.5 | 2025-02-19 | 2025-12-11
PIN250656 | 3-Proposals Regular | 0 | 2 | 0 | 2 | 0.010811 | 2 | 0 | 0 | 2025-05-27 | 2025-05-27 | Chargable Proposals 25 | 2025 | 2-Proposals Chargeable | 729.5 | 2025-01-02 | 2025-09-08
PJ240530 | 3-Proposals Regular | 3 | 0 | 0 | 3 | 0.016216 | 3 | 0 | 0 | 2024-05-19 | 2024-06-06 | Proposals 26 | 2026 | 3-Proposals Regular | 13 | 2026-01-19 | 2026-03-12
PJ260118 | 3-Proposals Regular | 0 | 0 | 1 | 1 | 0.0054054 | 1 | 0 | 0 | 2026-01-19 | 2026-01-19 | Chargable Proposals 26 | 2026 | 2-Proposals Chargeable | 61.25 | 2026-02-25 | 2026-05-14
PN230795C | 2-Proposals Chargeable | 218.25 | 507 | 0 | 725.25 | 3.9203 | 221.25 | 504 | 0 | 2024-02-01 | 2025-09-08
PN250010C | 2-Proposals Chargeable | 0 | 17 | 0 | 17 | 0.091892 | 0 | 17 | 0 | 2025-01-08 | 2025-01-09
PPY250473 | 3-Proposals Regular | 0 | 3 | 0 | 3 | 0.016216 | 3 | 0 | 0 | 2025-05-22 | 2025-05-25
PQ240548 | 3-Proposals Regular | 1 | 0 | 0 | 1 | 0.0054054 | 1 | 0 | 0 | 2024-05-14 | 2024-05-14
PS20450C | 2-Proposals Chargeable | 0 | 0 | 0 | 0 | 0 | 744.75 | 0 | 0 | 2020-07-21 | 2021-11-07
PS221394 | 3-Proposals Regular | 9.25 | 0 | 0 | 9.25 | 0.05 | 0 | 9.25 | 0 | 2024-03-24 | 2024-03-24
PS231531 | 3-Proposals Regular | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2023-11-13 | 2023-11-13
PS240458 | 3-Proposals Regular | 66.25 | 0 | 0 | 66.25 | 0.35811 | 7 | 0 | 59.25 | 2024-10-14 | 2024-12-18
PS250346 | 3-Proposals Regular | 0 | 76 | 0 | 76 | 0.41081 | 76 | 0 | 0 | 2025-02-24 | 2025-03-24
QL251243 | 3-Proposals Regular | 0 | 20.5 | 0 | 20.5 | 0.11081 | 16.25 | 4.25 | 0 | 2025-09-29 | 2025-09-30
WWCG250041 | 3-Proposals Regular | 0 | 1 | 0 | 1 | 0.0054054 | 1 | 0 | 0 | 2025-02-19 | 2025-02-19
WWIQ240673 | 3-Proposals Regular | 7.75 | 0 | 0 | 7.75 | 0.041892 | 7.75 | 0 | 0 | 2024-06-06 | 2024-06-25
WWL260195 | 3-Proposals Regular | 0 | 0 | 5 | 5 | 0.027027 | 5 | 0 | 0 | 2026-02-24 | 2026-03-05
WWMZ250249 | 3-Proposals Regular | 0 | 3 | 0 | 3 | 0.016216 | 3 | 0 | 0 | 2025-03-20 | 2025-07-22
WWMZ251598 | 3-Proposals Regular | 0 | 5 | 0 | 5 | 0.027027 | 5 | 0 | 0 | 2025-12-11 | 2025-12-11
WWN260200 | 3-Proposals Regular | 0 | 0 | 6 | 6 | 0.032432 | 6 | 0 | 0 | 2026-03-02 | 2026-03-12
WWOM241095 | 3-Proposals Regular | 0 | 2.5 | 0 | 2.5 | 0.013514 | 2.5 | 0 | 0 | 2025-05-05 | 2025-05-05
WWOM250578 | 3-Proposals Regular | 0 | 1 | 0 | 1 | 0.0054054 | 1 | 0 | 0 | 2025-05-14 | 2025-05-14
WWOM250731 | 3-Proposals Regular | 0 | 202.25 | 0 | 202.25 | 1.0932 | 25.75 | 52.25 | 124.25 | 2025-06-25 | 2025-09-18
WWOM250791 | 3-Proposals Regular | 0 | 59.25 | 0 | 59.25 | 0.32027 | 52.75 | 6.5 | 0 | 2025-08-04 | 2025-08-17
WWQ240828 | 3-Proposals Regular | 1 | 0 | 0 | 1 | 0.0054054 | 1 | 0 | 0 | 2024-08-07 | 2024-08-07
WWQ250337 | 3-Proposals Regular | 0 | 2 | 0 | 2 | 0.010811 | 2 | 0 | 0 | 2025-03-27 | 2025-03-27
WWS240119
WWS240344
WWS240426
WWS240976
WWS250088
WWS250396
WWS260269
Formulas:
First charge = IF([Proposal number]="","",IFERROR(MINIFS('Timesheet Raw'!$L4:L8000,'Timesheet Raw'!$B4:B8000,[Proposal number]),""))
Last charge = IF([Proposal number]="","",IFERROR(MAXIFS('Timesheet Raw'!$L4:L8000,'Timesheet Raw'!$B4:B8000,[Proposal number]),""))

## Phasing
PHASING — PLANNED vs ACTUAL MM BY QUARTER
Year |  |  | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028
Quarter |  |  | Opening | Q1-24 | Q2-24 | Q3-24 | Q4-24 | Q1-25 | Q2-25 | Q3-25 | Q4-25 | Q1-26 | Q2-26 | Q3-26 | Q4-26 | Q1-27 | Q2-27 | Q3-27 | Q4-27 | Q1-28 | Q2-28 | Q3-28 | Q4-28 | Total
Quarter start |  |  | 1899-12-31 | 2024-01-01 | 2024-04-01 | 2024-07-01 | 2024-10-01 | 2025-01-01 | 2025-04-01 | 2025-07-01 | 2025-10-01 | 2026-01-01 | 2026-04-01 | 2026-07-01 | 2026-10-01 | 2027-01-01 | 2027-04-01 | 2027-07-01 | 2027-10-01 | 2028-01-01 | 2028-04-01 | 2028-07-01 | 2028-10-01
Quarter end |  |  | 2023-12-31 | 2024-03-31 | 2024-06-30 | 2024-09-30 | 2024-12-31 | 2025-03-31 | 2025-06-30 | 2025-09-30 | 2025-12-31 | 2026-03-31 | 2026-06-30 | 2026-09-30 | 2026-12-31 | 2027-03-31 | 2027-06-30 | 2027-09-30 | 2027-12-31 | 2028-03-31 | 2028-06-30 | 2028-09-30 | 2028-12-31
PLANNED MM — AUTO (straight-line across each project's start-to-end window)
Code | Start | End | Opening | Q1-24 | Q2-24 | Q3-24 | Q4-24 | Q1-25 | Q2-25 | Q3-25 | Q4-25 | Q1-26 | Q2-26 | Q3-26 | Q4-26 | Q1-27 | Q2-27 | Q3-27 | Q4-27 | Q1-28 | Q2-28 | Q3-28 | Q4-28 | Total
N25178-0100D | 2026-07-01 | 2026-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4
E26084-0100D | 2025-07-01 | 2026-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.60394 | 0.60394 | 0.59081 | 0.59737 | 0.60394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
N25185-0100D | 2025-10-01 | 2026-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.2341 | 5.1204 | 5.1772 | 5.2341 | 5.2341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26
AN22137-0100D | 2027-01-01 | 2028-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6156 | 0.62244 | 0.62927 | 0.62927 | 0.62244 | 0.62244 | 0.62927 | 0.62927 | 5
D26058-0100D | 2026-07-01 | 2028-06-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62927 | 0.62927 | 0.6156 | 0.62244 | 0.62927 | 0.62927 | 0.62244 | 0.62244 | 0 | 0 | 5
AD24217-0100D | 2025-06-01 | 2025-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4516 | 1.5484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
AN23207-0500D | 2026-01-01 | 2026-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.15
AN23276-0100D | 2024-07-01 | 2026-09-30 | 0 | 0 | 0 | 0.55961 | 0.55961 | 0.54745 | 0.55353 | 0.55961 | 0.55961 | 0.54745 | 0.55353 | 0.55961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
AN24073-0100D | 2025-07-01 | 2026-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25164 | 0.25164 | 0.24617 | 0.24891 | 0.25164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25
AN24140-0100R | 2025-03-01 | 2026-09-30 | 0 | 0 | 0 | 0 | 0 | 0.080311 | 0.23575 | 0.23834 | 0.23834 | 0.23316 | 0.23575 | 0.23834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5
CS24035-0100D | 2025-10-01 | 2026-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.80525 | 0.78775 | 0.7965 | 0.80525 | 0.80525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
E24181-0100D | 2024-08-01 | 2024-08-01 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
J23152-0100D | 2024-01-01 | 2024-03-31 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
Q25008-0100D | 2026-01-01 | 2026-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1127 | 2.1362 | 0.75117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
S24014-0101D | 2024-04-01 | 2024-08-01 | 0 | 0 | 15.7363 | 5.5337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.27
S24014-0102D | 2024-09-01 | 2025-09-30 | 0 | 0 | 0 | 0.57873 | 1.7748 | 1.7362 | 1.7555 | 1.7748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.62
S24014-0103D | 2024-09-01 | 2025-09-30 | 0 | 0 | 0 | 0.48304 | 1.4813 | 1.4491 | 1.4652 | 1.4813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.36
S24014-0104D | 2024-09-01 | 2025-09-30 | 0 | 0 | 0 | 0.91367 | 2.8019 | 2.741 | 2.7715 | 2.8019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.03
S22058-0700D | 2024-07-01 | 2025-09-30 | 0 | 0 | 0 | 1.2079 | 1.2079 | 1.1816 | 1.1947 | 1.2079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
AN24185-0100R | 2024-10-01 | 2026-03-31 | 0 | 0 | 0 | 0 | 0.67276 | 0.65814 | 0.66545 | 0.67276 | 0.67276 | 0.65814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
AN24135-0100R | 2024-10-01 | 2027-03-31 | 0 | 0 | 0 | 0 | 0.40351 | 0.39474 | 0.39912 | 0.40351 | 0.40351 | 0.39474 | 0.39912 | 0.40351 | 0.40351 | 0.39474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
AN23232-0100D | 2024-01-01 | 2024-09-30 | 0 | 0.99635 | 0.99635 | 1.0073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
AN23108-0100R | 2025-02-01 | 2027-06-30 | 0 | 0 | 0 | 0 | 0 | 0.13409 | 0.20682 | 0.20909 | 0.20909 | 0.20455 | 0.20682 | 0.20909 | 0.20909 | 0.20455 | 0.20682 | 0 | 0 | 0 | 0 | 0 | 0 | 2
TA24246-0200R | 2025-02-01 | 2027-06-30 | 0 | 0 | 0 | 0 | 0 | 0.067045 | 0.10341 | 0.10455 | 0.10455 | 0.10227 | 0.10341 | 0.10455 | 0.10455 | 0.10227 | 0.10341 | 0 | 0 | 0 | 0 | 0 | 0 | 1
S22058-0900D | 2024-04-01 | 2024-09-30 | 0 | 0 | 0.12432 | 0.12568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
S22058-0400D | 2024-01-01 | 2024-03-31 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
Proposals 25 | 2025-01-01 | 2025-12-31 | 0 | 0 | 0 | 0 | 0 | 0.46849 | 0.4737 | 0.4789 | 0.4789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9
Chargable Proposals 25 | 2025-07-01 | 2025-09-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
AD23051-0101D | 2024-01-01 | 2024-03-31 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
AN21146-0100R | 2024-03-01 | 2024-09-30 | 0 | 0.43458 | 1.2757 | 1.2897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
N23106-0100D | 2024-03-01 | 2024-09-30 | 0 | 0.7243 | 2.1262 | 2.1495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
OM23030-0100D | 2024-03-01 | 2024-06-30 | 0 | 0.063525 | 0.18648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
Chargable Proposals 24 | 2024-01-01 | 2024-12-31 | 0 | 0.55943 | 0.55943 | 0.56557 | 0.56557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25
Proposals 24 | 2024-01-01 | 2024-12-31 | 0 | 0.2735 | 0.2735 | 0.2765 | 0.2765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1
S23204-0100D | 2024-01-01 | 2024-03-31 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5
S24100-0100D | 2024-07-01 | 2024-12-31 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
TA23011-0100R | 2024-01-01 | 2024-03-31 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1
AL25148-0100D | 2027-01-01 | 2027-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4658 | 2.4932 | 2.5205 | 2.5205 | 0 | 0 | 0 | 0 | 10
Chargable Proposals 26 | 2026-01-01 | 2026-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55479 | 0.56096 | 0.56712 | 0.56712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Proposals 26 | 2026-01-01 | 2026-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.09863 | 0.099726 | 0.10082 | 0.10082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  | 0 | 6.1517 | 21.2783 | 16.6909 | 11.2439 | 9.4582 | 11.2763 | 15.3366 | 9.5617 | 12.8015 | 11.1155 | 12.8585 | 8.0538 | 4.3985 | 4.0482 | 3.7791 | 3.7791 | 1.2449 | 1.2449 | 0.62927 | 0.62927 | 165.58
PLANNED MM — OVERRIDE (leave blank to use the auto spread; type a value to force a quarter)
Code |  |  | Opening | Q1-24 | Q2-24 | Q3-24 | Q4-24 | Q1-25 | Q2-25 | Q3-25 | Q4-25 | Q1-26 | Q2-26 | Q3-26 | Q4-26 | Q1-27 | Q2-27 | Q3-27 | Q4-27 | Q1-28 | Q2-28 | Q3-28 | Q4-28 | Total
N25178-0100D | [23 empty] | 0
E26084-0100D | [23 empty] | 0
N25185-0100D | [23 empty] | 0
AN22137-0100D | [23 empty] | 0
D26058-0100D | [23 empty] | 0
AD24217-0100D | [23 empty] | 0
AN23207-0500D | [23 empty] | 0
AN23276-0100D | [23 empty] | 0
AN24073-0100D | [23 empty] | 0
AN24140-0100R | [23 empty] | 0
CS24035-0100D | [23 empty] | 0
E24181-0100D | [23 empty] | 0
J23152-0100D | [23 empty] | 0
Q25008-0100D | [23 empty] | 0
S24014-0101D | [23 empty] | 0
S24014-0102D | [23 empty] | 0
S24014-0103D | [23 empty] | 0
S24014-0104D | [23 empty] | 0
S22058-0700D | [23 empty] | 0
AN24185-0100R | [23 empty] | 0
AN24135-0100R | [23 empty] | 0
AN23232-0100D | [23 empty] | 0
AN23108-0100R | [23 empty] | 0
TA24246-0200R | [23 empty] | 0
S22058-0900D | [23 empty] | 0
S22058-0400D | [23 empty] | 0
Proposals 25 | [23 empty] | 0
Chargable Proposals 25 | [23 empty] | 0
AD23051-0101D | [23 empty] | 0
AN21146-0100R | [23 empty] | 0
N23106-0100D | [23 empty] | 0
OM23030-0100D | [23 empty] | 0
Chargable Proposals 24 | [23 empty] | 0
Proposals 24 | [23 empty] | 0
S23204-0100D | [23 empty] | 0
S24100-0100D | [23 empty] | 0
TA23011-0100R | [23 empty] | 0
AL25148-0100D | [23 empty] | 0
Chargable Proposals 26 | [23 empty] | 0
0
Proposals 26 | [23 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PLANNED MM — IN USE (override where entered, otherwise auto)
Code |  |  | Opening | Q1-24 | Q2-24 | Q3-24 | Q4-24 | Q1-25 | Q2-25 | Q3-25 | Q4-25 | Q1-26 | Q2-26 | Q3-26 | Q4-26 | Q1-27 | Q2-27 | Q3-27 | Q4-27 | Q1-28 | Q2-28 | Q3-28 | Q4-28 | Total
N25178-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4
E26084-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.60394 | 0.60394 | 0.59081 | 0.59737 | 0.60394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
N25185-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.2341 | 5.1204 | 5.1772 | 5.2341 | 5.2341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26
AN22137-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6156 | 0.62244 | 0.62927 | 0.62927 | 0.62244 | 0.62244 | 0.62927 | 0.62927 | 5
D26058-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62927 | 0.62927 | 0.6156 | 0.62244 | 0.62927 | 0.62927 | 0.62244 | 0.62244 | 0 | 0 | 5
AD24217-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.4516 | 1.5484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
AN23207-0500D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.15
AN23276-0100D |  |  | 0 | 0 | 0 | 0.55961 | 0.55961 | 0.54745 | 0.55353 | 0.55961 | 0.55961 | 0.54745 | 0.55353 | 0.55961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
AN24073-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25164 | 0.25164 | 0.24617 | 0.24891 | 0.25164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25
AN24140-0100R |  |  | 0 | 0 | 0 | 0 | 0 | 0.080311 | 0.23575 | 0.23834 | 0.23834 | 0.23316 | 0.23575 | 0.23834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5
CS24035-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.80525 | 0.78775 | 0.7965 | 0.80525 | 0.80525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
E24181-0100D |  |  | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
J23152-0100D |  |  | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
Q25008-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1127 | 2.1362 | 0.75117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
S24014-0101D |  |  | 0 | 0 | 15.7363 | 5.5337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.27
S24014-0102D |  |  | 0 | 0 | 0 | 0.57873 | 1.7748 | 1.7362 | 1.7555 | 1.7748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.62
S24014-0103D |  |  | 0 | 0 | 0 | 0.48304 | 1.4813 | 1.4491 | 1.4652 | 1.4813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.36
S24014-0104D |  |  | 0 | 0 | 0 | 0.91367 | 2.8019 | 2.741 | 2.7715 | 2.8019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.03
S22058-0700D |  |  | 0 | 0 | 0 | 1.2079 | 1.2079 | 1.1816 | 1.1947 | 1.2079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
AN24185-0100R |  |  | 0 | 0 | 0 | 0 | 0.67276 | 0.65814 | 0.66545 | 0.67276 | 0.67276 | 0.65814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
AN24135-0100R |  |  | 0 | 0 | 0 | 0 | 0.40351 | 0.39474 | 0.39912 | 0.40351 | 0.40351 | 0.39474 | 0.39912 | 0.40351 | 0.40351 | 0.39474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
AN23232-0100D |  |  | 0 | 0.99635 | 0.99635 | 1.0073 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
AN23108-0100R |  |  | 0 | 0 | 0 | 0 | 0 | 0.13409 | 0.20682 | 0.20909 | 0.20909 | 0.20455 | 0.20682 | 0.20909 | 0.20909 | 0.20455 | 0.20682 | 0 | 0 | 0 | 0 | 0 | 0 | 2
TA24246-0200R |  |  | 0 | 0 | 0 | 0 | 0 | 0.067045 | 0.10341 | 0.10455 | 0.10455 | 0.10227 | 0.10341 | 0.10455 | 0.10455 | 0.10227 | 0.10341 | 0 | 0 | 0 | 0 | 0 | 0 | 1
S22058-0900D |  |  | 0 | 0 | 0.12432 | 0.12568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
S22058-0400D |  |  | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
Proposals 25 |  |  | 0 | 0 | 0 | 0 | 0 | 0.46849 | 0.4737 | 0.4789 | 0.4789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9
Chargable Proposals 25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
AD23051-0101D |  |  | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
AN21146-0100R |  |  | 0 | 0.43458 | 1.2757 | 1.2897 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
N23106-0100D |  |  | 0 | 0.7243 | 2.1262 | 2.1495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
OM23030-0100D |  |  | 0 | 0.063525 | 0.18648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
Chargable Proposals 24 |  |  | 0 | 0.55943 | 0.55943 | 0.56557 | 0.56557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25
Proposals 24 |  |  | 0 | 0.2735 | 0.2735 | 0.2765 | 0.2765 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1
S23204-0100D |  |  | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5
S24100-0100D |  |  | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
TA23011-0100R |  |  | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1
AL25148-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4658 | 2.4932 | 2.5205 | 2.5205 | 0 | 0 | 0 | 0 | 10
Chargable Proposals 26 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55479 | 0.56096 | 0.56712 | 0.56712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Proposals 26 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.09863 | 0.099726 | 0.10082 | 0.10082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  | 0 | 6.1517 | 21.2783 | 16.6909 | 11.2439 | 9.4582 | 11.2763 | 15.3366 | 9.5617 | 12.8015 | 11.1155 | 12.8585 | 8.0538 | 4.3985 | 4.0482 | 3.7791 | 3.7791 | 1.2449 | 1.2449 | 0.62927 | 0.62927 | 165.58
NOW CALCULATED FROM THE TIMESHEET - do not type in the grid below.
Each cell sums Timesheet Raw hours for that project code (or proposal job type and year) and that engineer, within the quarter, divided by hours per man-month. Project and proposal hours count; HOLIDAY, LEAVE, LATE and EXCUSE do not. Quarters earlier than your loaded timesheet history read zero - paste the fuller exports into the TS sheets to fill them. The grid as it was previously typed is preserved on the sheet 'Phasing Actual (typed backup)'.
ACTUAL MM BOOKED - by project and engineer, per quarter (CALCULATED from the timesheet)
Code | Engineer |  | Opening | Q1-24 | Q2-24 | Q3-24 | Q4-24 | Q1-25 | Q2-25 | Q3-25 | Q4-25 | Q1-26 | Q2-26 | Q3-26 | Q4-26 | Q1-27 | Q2-27 | Q3-27 | Q4-27 | Q1-28 | Q2-28 | Q3-28 | Q4-28 | Total
N25178-0100D | Ahmed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
N25178-0100D | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
N25178-0100D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E26084-0100D | Ahmed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E26084-0100D | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22568
E26084-0100D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
N25185-0100D | Ahmed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6284 | 1.6838 | 2.7189 | 0.6973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7284
N25185-0100D | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6541 | 1.8095 | 2.5162 | 1.0932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.073
N25185-0100D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71622 | 0.7973 | 0.99324 | 1.2081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7149
AN22137-0100D | Ahmed |  | 0 | 0 | 0.17162 | 0.50946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.68108
AN22137-0100D | Osama |  | 0 | 0 | 0.23514 | 0.2527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48784
AN22137-0100D | Kirolos |  | 0 | 0 | 0 | 0.23243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23243
D26058-0100D | Ahmed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D26058-0100D | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D26058-0100D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AD24217-0100D | Ahmed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.24865 | 0.010811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25946
AD24217-0100D | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.30135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30135
AD24217-0100D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0.11622 | 1.2392 | 0.58243 | 0.10135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0392
AN23207-0500D | Ahmed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AN23207-0500D | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AN23207-0500D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AN23276-0100D | Ahmed |  | 0 | 0 | 0.037838 | 0.2027 | 0 | 0 | 0.010811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25135
AN23276-0100D | Osama |  | 0 | 0 | 0 | 0.54324 | 0 | 0 | 0.094595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.63784
AN23276-0100D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AN24073-0100D | Ahmed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.010811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.010811
AN24073-0100D | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.067568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.067568
AN24073-0100D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.83243 | 0.013514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84595
AN24140-0100R | Ahmed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0054054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0054054
AN24140-0100R | Osama |  | 0 | 0 | 0 | 0 | 0 | 0.17568 | 0.055405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23108
AN24140-0100R | Kirolos |  | 0 | 0 | 0 | 0 | 0.067568 | 0.082432 | 0.094595 | 0 | 0 | 0.021622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26622
CS24035-0100D | Ahmed |  | 0 | 0.032432 | 0 | 0 | 0 | 0.027027 | 0 | 0 | 1.0068 | 0.10676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.173
CS24035-0100D | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CS24035-0100D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4959 | 0.10405 | 0.35946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9595
E24181-0100D | Ahmed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E24181-0100D | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E24181-0100D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J23152-0100D | Ahmed |  | 0.094595 | 0 | 0 | 0 | 0 | 0 | 0 | 0.016216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11081
J23152-0100D | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J23152-0100D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Q25008-0100D | Ahmed |  | 0 | 0 | 0 | 0 | 0 | 0.032432 | 0 | 0 | 0.045946 | 0.14595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22432
Q25008-0100D | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Q25008-0100D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.037838 | 0.86081 | 0.64459 | 0.16216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7054
S24014-0101D | Ahmed |  | 0 | 1.0459 | 1.2068 | 0.18919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4419
S24014-0101D | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S24014-0101D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S24014-0102D | Ahmed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.98108 | 1.2554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2365
S24014-0102D | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26486
S24014-0102D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15405
S24014-0103D | Ahmed |  | 0 | 0 | 0 | 0.44189 | 2.1635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6054
S24014-0103D | Osama |  | 0 | 0 | 0 | 0 | 1.7446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7446
S24014-0103D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S24014-0104D | Ahmed |  | 0 | 0 | 0 | 0.25541 | 0.28919 | 0.043243 | 0.41892 | 0.20946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2162
S24014-0104D | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S24014-0104D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S22058-0700D | Ahmed |  | 0 | 0 | 0 | 0.021622 | 0.087838 | 0.82568 | 0.068919 | 0.010811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0149
S22058-0700D | Osama |  | 0 | 0 | 0.093243 | 0 | 0.23784 | 1.4635 | 0.20405 | 0.36216 | 0.032432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3932
S22058-0700D | Kirolos |  | 0 | 0 | 0 | 0 | 0.2527 | 0.91216 | 0.041892 | 0.33243 | 0.16892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7081
AN24185-0100R | Ahmed |  | 0 | 0 | 0 | 0 | 0.039189 | 0 | 0 | 0.010811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05
AN24185-0100R | Osama |  | 0 | 0 | 0 | 0 | 0.50811 | 0.22432 | 0.13919 | 0.13514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0068
AN24185-0100R | Kirolos |  | 0 | 0 | 0 | 0 | 0.58378 | 0.51486 | 0.13378 | 0.43784 | 0.1 | 0.13378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9041
AN24135-0100R | Ahmed |  | 0 | 0 | 0 | 0 | 0.037838 | 0.0054054 | 0.0054054 | 0.014865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.063514
AN24135-0100R | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.13514 | 0.11351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24865
AN24135-0100R | Kirolos |  | 0 | 0 | 0 | 0 | 0.43243 | 0.55405 | 0.18243 | 0.32297 | 0.027027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5189
AN23232-0100D | Ahmed |  | 1.0878 | 1.2351 | 0.15676 | 0.10135 | 0 | 0 | 0.041892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.623
AN23232-0100D | Osama |  | 0 | 0.53514 | 0.14459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67973
AN23232-0100D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AN23108-0100R | Ahmed |  | 0 | 0 | 0 | 0 | 0 | 0.091892 | 0.0054054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.097297
AN23108-0100R | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AN23108-0100R | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.044595 | 0.2473 | 0.35946 | 0.078378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72973
TA24246-0200R | Ahmed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.016216 | 0.068919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.085135
TA24246-0200R | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.48919 | 0.69865 | 0.045946 | 0.077027 | 0.021622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3324
TA24246-0200R | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S22058-0900D | Ahmed |  | 0 | 0 | 0 | 0 | 0.021622 | 0.074324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095946
S22058-0900D | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S22058-0900D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S22058-0400D | Ahmed |  | 0.010811 | 0.018919 | 0 | 0 | 0 | 0 | 0.010811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.040541
S22058-0400D | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S22058-0400D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Proposals 25 | Ahmed |  | 0 | 0 | 0 | 0 | 0 | 0.44865 | 0.13649 | 0.45946 | 0.027027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0716
Proposals 25 | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.091892 | 0.24865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.34054
Proposals 25 | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.051351 | 0.62027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67162
Chargable Proposals 25 | Ahmed |  | 0 | 0 | 0 | 0 | 0 | 0.67568 | 0.12703 | 0.18243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.98514
Chargable Proposals 25 | Osama |  | 0 | 0 | 0 | 0 | 0 | 0.69865 | 0.63514 | 1.3568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6905
Chargable Proposals 25 | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0.26757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26757
AD23051-0101D | Ahmed |  | 0.021622 | 0.12027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14189
AD23051-0101D | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AD23051-0101D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AN21146-0100R | Ahmed |  | 0 | 0 | 0.044595 | 0.063514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10811
AN21146-0100R | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AN21146-0100R | Kirolos |  | 0 | 0 | 0 | 0.41081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41081
N23106-0100D | Ahmed |  | 0 | 0 | 0.15811 | 0.63919 | 0 | 0 | 0 | 0 | 0 | 0.18919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.98649
N23106-0100D | Osama |  | 0 | 0 | 0 | 1.1284 | 0.3473 | 0 | 0 | 0 | 0.032432 | 0.25135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7595
N23106-0100D | Kirolos |  | 0 | 0 | 0 | 0.57568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57568
OM23030-0100D | Ahmed |  | 0 | 0.1473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1473
OM23030-0100D | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OM23030-0100D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chargable Proposals 24 | Ahmed |  | 0 | 0.21216 | 0.42297 | 0 | 0.095946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73108
Chargable Proposals 24 | Osama |  | 0 | 0.25541 | 0.53108 | 0 | 0.093243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87973
Chargable Proposals 24 | Kirolos |  | 0 | 0 | 0 | 0 | 0.24324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24324
Proposals 24 | Ahmed |  | 0 | 0.016216 | 0.095946 | 0.016216 | 0.037838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16622
Proposals 24 | Osama |  | 0 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05
Proposals 24 | Kirolos |  | 0 | 0 | 0 | 0 | 0.32027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32027
S23204-0100D | Ahmed |  | 0 | 0.045946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.045946
S23204-0100D | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S23204-0100D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S24100-0100D | Ahmed |  | 0 | 0 | 0.043243 | 0.29865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.34189
S24100-0100D | Osama |  | 0 | 0 | 0.14054 | 0 | 0.074324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21486
S24100-0100D | Kirolos |  | 0 | 0 | 0 | 0.048649 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.44865
TA23011-0100R | Ahmed |  | 0.032432 | 0.021622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.054054
TA23011-0100R | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TA23011-0100R | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AL25148-0100D | Ahmed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AL25148-0100D | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AL25148-0100D | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chargable Proposals 26 | Ahmed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.072973 | 0.036486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10946
Chargable Proposals 26 | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chargable Proposals 26 | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.072973 | 0.14865 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22162
0
0
0
Proposals 26 | Ahmed |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.07027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.07027
Proposals 26 | Osama |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Proposals 26 | Kirolos |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
TOTAL BOOKED |  |  | 1.2473 | 3.7365 | 3.4824 | 5.9311 | 8.0784 | 7.2338 | 5.9608 | 8.7851 | 8.1784 | 6.6446 | 7.7986 | 3.4649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.5419
ACTUAL MM BY PROJECT (rollup of the grid above)
Code |  |  | Opening | Q1-24 | Q2-24 | Q3-24 | Q4-24 | Q1-25 | Q2-25 | Q3-25 | Q4-25 | Q1-26 | Q2-26 | Q3-26 | Q4-26 | Q1-27 | Q2-27 | Q3-27 | Q4-27 | Q1-28 | Q2-28 | Q3-28 | Q4-28 | Total
N25178-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E26084-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22568
N25185-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9986 | 4.2905 | 6.2284 | 2.9986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.5162
AN22137-0100D |  |  | 0 | 0 | 0.40676 | 0.99459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4014
D26058-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AD24217-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0.11622 | 1.7892 | 0.59324 | 0.10135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6
AN23207-0500D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AN23276-0100D |  |  | 0 | 0 | 0.037838 | 0.74595 | 0 | 0 | 0.10541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88919
AN24073-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.91081 | 0.013514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92432
AN24140-0100R |  |  | 0 | 0 | 0 | 0 | 0.067568 | 0.25811 | 0.15 | 0.0054054 | 0 | 0.021622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5027
CS24035-0100D |  |  | 0 | 0.032432 | 0 | 0 | 0 | 0.027027 | 0 | 0 | 2.5027 | 0.21081 | 0.35946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1324
E24181-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J23152-0100D |  |  | 0.094595 | 0 | 0 | 0 | 0 | 0 | 0 | 0.016216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11081
Q25008-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0.032432 | 0 | 0 | 0.083784 | 1.0068 | 0.64459 | 0.16216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9297
S24014-0101D |  |  | 0 | 1.0459 | 1.2068 | 0.18919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4419
S24014-0102D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.98108 | 1.6743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6554
S24014-0103D |  |  | 0 | 0 | 0 | 0.44189 | 3.9081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.35
S24014-0104D |  |  | 0 | 0 | 0 | 0.25541 | 0.28919 | 0.043243 | 0.41892 | 0.20946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2162
S22058-0700D |  |  | 0 | 0 | 0.093243 | 0.021622 | 0.57838 | 3.2014 | 0.31486 | 0.70541 | 0.20135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.1162
AN24185-0100R |  |  | 0 | 0 | 0 | 0 | 1.1311 | 0.73919 | 0.27297 | 0.58378 | 0.1 | 0.13378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9608
AN24135-0100R |  |  | 0 | 0 | 0 | 0 | 0.47027 | 0.55946 | 0.32297 | 0.45135 | 0.027027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8311
AN23232-0100D |  |  | 1.0878 | 1.7703 | 0.30135 | 0.10135 | 0 | 0 | 0.041892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3027
AN23108-0100R |  |  | 0 | 0 | 0 | 0 | 0 | 0.091892 | 0.0054054 | 0 | 0.044595 | 0.2473 | 0.35946 | 0.078378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82703
TA24246-0200R |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.50541 | 0.76757 | 0.045946 | 0.077027 | 0.021622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4176
S22058-0900D |  |  | 0 | 0 | 0 | 0 | 0.021622 | 0.074324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.095946
S22058-0400D |  |  | 0.010811 | 0.018919 | 0 | 0 | 0 | 0 | 0.010811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.040541
Proposals 25 |  |  | 0 | 0 | 0 | 0 | 0 | 0.44865 | 0.27973 | 1.3284 | 0.027027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0838
Chargable Proposals 25 |  |  | 0 | 0 | 0 | 0 | 0 | 1.6419 | 0.76216 | 1.5392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.9432
AD23051-0101D |  |  | 0.021622 | 0.12027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14189
AN21146-0100R |  |  | 0 | 0 | 0.044595 | 0.47432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51892
N23106-0100D |  |  | 0 | 0 | 0.15811 | 2.3432 | 0.3473 | 0 | 0 | 0 | 0.032432 | 0.44054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3216
OM23030-0100D |  |  | 0 | 0.1473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1473
Chargable Proposals 24 |  |  | 0 | 0.46757 | 0.95405 | 0 | 0.43243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8541
Proposals 24 |  |  | 0 | 0.066216 | 0.095946 | 0.016216 | 0.35811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.53649
S23204-0100D |  |  | 0 | 0.045946 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.045946
S24100-0100D |  |  | 0 | 0 | 0.18378 | 0.3473 | 0.47432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0054
TA23011-0100R |  |  | 0.032432 | 0.021622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.054054
AL25148-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chargable Proposals 26 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14595 | 0.18514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33108
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Proposals 26 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.07027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.07027
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  | 1.2473 | 3.7365 | 3.4824 | 5.9311 | 8.0784 | 7.2338 | 5.9608 | 8.7851 | 8.1784 | 6.6446 | 7.7986 | 3.4649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.5419
EARNED MM BY PROJECT (value delivered, spread in proportion to actual time booked)
Code |  |  | Opening | Q1-24 | Q2-24 | Q3-24 | Q4-24 | Q1-25 | Q2-25 | Q3-25 | Q4-25 | Q1-26 | Q2-26 | Q3-26 | Q4-26 | Q1-27 | Q2-27 | Q3-27 | Q4-27 | Q1-28 | Q2-28 | Q3-28 | Q4-28 | Total
N25178-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E26084-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4875
N25185-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.218 | 1.9038 | 2.7637 | 1.3306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.216
AN22137-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D26058-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AD24217-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0.1341 | 2.0644 | 0.68451 | 0.11694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
AN23207-0500D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AN23276-0100D |  |  | 0 | 0 | 0.19149 | 3.7751 | 0 | 0 | 0.53343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5
AN24073-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1086 | 0.016447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.125
AN24140-0100R |  |  | 0 | 0 | 0 | 0 | 0.020161 | 0.077016 | 0.044758 | 0.0016129 | 0 | 0.0064516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15
CS24035-0100D |  |  | 0 | 0.035203 | 0 | 0 | 0 | 0.029336 | 0 | 0 | 2.7165 | 0.22882 | 0.39016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4
E24181-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J23152-0100D |  |  | 0.42683 | 0 | 0 | 0 | 0 | 0 | 0 | 0.073171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
Q25008-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0.084034 | 0 | 0 | 0.21709 | 2.6085 | 1.6702 | 0.42017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
S24014-0101D |  |  | 0 | 9.1107 | 10.5114 | 1.6479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.27
S24014-0102D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2.8153 | 4.8047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.62
S24014-0103D |  |  | 0 | 0 | 0 | 0.64608 | 5.7139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.36
S24014-0104D |  |  | 0 | 0 | 0 | 2.5263 | 2.8605 | 0.42773 | 4.1437 | 2.0718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.03
S22058-0700D |  |  | 0 | 0 | 0.10935 | 0.025357 | 0.67829 | 3.7544 | 0.36926 | 0.82726 | 0.23613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
AN24185-0100R |  |  | 0 | 0 | 0 | 0 | 1.5281 | 0.99863 | 0.36878 | 0.78868 | 0.1351 | 0.18074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
AN24135-0100R |  |  | 0 | 0 | 0 | 0 | 0.10273 | 0.12221 | 0.070554 | 0.098598 | 0.0059041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4
AN23232-0100D |  |  | 0.98813 | 1.608 | 0.27373 | 0.092062 | 0 | 0 | 0.038052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
AN23108-0100R |  |  | 0 | 0 | 0 | 0 | 0 | 0.022222 | 0.0013072 | 0 | 0.010784 | 0.059804 | 0.086928 | 0.018954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2
TA24246-0200R |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.21392 | 0.32488 | 0.019447 | 0.032602 | 0.0091516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6
S22058-0900D |  |  | 0 | 0 | 0 | 0 | 0.056338 | 0.19366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
S22058-0400D |  |  | 0.13333 | 0.23333 | 0 | 0 | 0 | 0 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
Proposals 25 |  |  | 0 | 0 | 0 | 0 | 0 | 0.40908 | 0.25506 | 1.2112 | 0.024643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9
Chargable Proposals 25 |  |  | 0 | 0 | 0 | 0 | 0 | 1.2491 | 0.57985 | 1.171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
AD23051-0101D |  |  | 0.07619 | 0.42381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5
AN21146-0100R |  |  | 0 | 0 | 0.25781 | 2.7422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
N23106-0100D |  |  | 0 | 0 | 0.238 | 3.5273 | 0.52278 | 0 | 0 | 0 | 0.04882 | 0.66314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
OM23030-0100D |  |  | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
Chargable Proposals 24 |  |  | 0 | 0.56742 | 1.1578 | 0 | 0.52478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25
Proposals 24 |  |  | 0 | 0.13577 | 0.19673 | 0.033249 | 0.73426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1
S23204-0100D |  |  | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5
S24100-0100D |  |  | 0 | 0 | 0.54839 | 1.0363 | 1.4153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
TA23011-0100R |  |  | 0.06 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1
AL25148-0100D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chargable Proposals 26 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49592 | 0.62908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.125
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Proposals 26 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  | 1.6845 | 13.9042 | 13.4847 | 16.0518 | 14.1571 | 7.5015 | 11.6317 | 13.166 | 5.7658 | 6.3798 | 5.5491 | 2.2572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.5335
ACTUAL MM BY ENGINEER
Engineer |  |  | Opening | Q1-24 | Q2-24 | Q3-24 | Q4-24 | Q1-25 | Q2-25 | Q3-25 | Q4-25 | Q1-26 | Q2-26 | Q3-26 | Q4-26 | Q1-27 | Q2-27 | Q3-27 | Q4-27 | Q1-28 | Q2-28 | Q3-28 | Q4-28 | Total
Ahmed |  |  | 1.2473 | 2.8959 | 2.3378 | 2.7392 | 2.773 | 2.2243 | 2.0716 | 2.2554 | 2.7081 | 2.2689 | 2.7554 | 0.6973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.9743
Osama |  |  | 0 | 0.84054 | 1.1446 | 1.9243 | 3.0054 | 2.5622 | 2.1459 | 3.2473 | 2.7649 | 2.1378 | 2.5378 | 1.3189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.6297
Kirolos |  |  | 0 | 0 | 0 | 1.2676 | 2.3 | 2.4473 | 1.7432 | 3.2824 | 2.7054 | 2.2378 | 2.5054 | 1.4486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.9378
TOTAL |  |  | 1.2473 | 3.7365 | 3.4824 | 5.9311 | 8.0784 | 7.2338 | 5.9608 | 8.7851 | 8.1784 | 6.6446 | 7.7986 | 3.4649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.5419

## Analysis
ANALYSIS — EFFICIENCY & PROFITABILITY BY QUARTER AND YEAR
Year | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028
Quarter | Opening | Q1-24 | Q2-24 | Q3-24 | Q4-24 | Q1-25 | Q2-25 | Q3-25 | Q4-25 | Q1-26 | Q2-26 | Q3-26 | Q4-26 | Q1-27 | Q2-27 | Q3-27 | Q4-27 | Q1-28 | Q2-28 | Q3-28 | Q4-28 | Total
IN-HAND — ACTIVE + NOT STARTED (what the team must actually deliver)
Planned MM (in use) | 0 | 0 | 0 | 0 | 0 | 0.080311 | 0.23575 | 0.84228 | 6.0764 | 6.5977 | 6.6711 | 9.7736 | 6.5314 | 3.6969 | 3.738 | 3.7791 | 3.7791 | 1.2449 | 1.2449 | 0.62927 | 0.62927 | 55.55
Actual MM booked | 0 | 0 | 0.40676 | 0.99459 | 0.067568 | 0.25811 | 0.15 | 0.0054054 | 4.9986 | 4.5284 | 6.4135 | 3.2243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.0473
Earned MM (value delivered) | 0 | 0 | 0 | 0 | 0.020161 | 0.077016 | 0.044758 | 0.0016129 | 2.218 | 2.6062 | 3.3927 | 1.8181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.1785
Profit / (Loss) in quarter | 0 | 0 | -0.40676 | -0.99459 | -0.047406 | -0.18109 | -0.10524 | -0.0037925 | -2.7807 | -1.9222 | -3.0208 | -1.4063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -10.8688
Cumulative actual MM | 0 | 0 | 0.40676 | 1.4014 | 1.4689 | 1.727 | 1.877 | 1.8824 | 6.8811 | 11.4095 | 17.823 | 21.0473 | 21.0473 | 21.0473 | 21.0473 | 21.0473 | 21.0473 | 21.0473 | 21.0473 | 21.0473 | 21.0473 | 21.0473
Cumulative earned MM | 0 | 0 | 0 | 0 | 0.020161 | 0.097177 | 0.14194 | 0.14355 | 2.3615 | 4.9677 | 8.3604 | 10.1785 | 10.1785 | 10.1785 | 10.1785 | 10.1785 | 10.1785 | 10.1785 | 10.1785 | 10.1785 | 10.1785 | 10.1785
Cumulative profit / (loss) | 0 | 0 | -0.40676 | -1.4014 | -1.4488 | -1.6298 | -1.7351 | -1.7389 | -4.5195 | -6.4417 | -9.4625 | -10.8688 | -10.8688 | -10.8688 | -10.8688 | -10.8688 | -10.8688 | -10.8688 | -10.8688 | -10.8688 | -10.8688 | -10.8688
OVERALL — ALL PROJECTS REGARDLESS OF STATUS
Planned MM (in use) | 0 | 6.1517 | 21.2783 | 16.6909 | 11.2439 | 9.4582 | 11.2763 | 15.3366 | 9.5617 | 12.8015 | 11.1155 | 12.8585 | 8.0538 | 4.3985 | 4.0482 | 3.7791 | 3.7791 | 1.2449 | 1.2449 | 0.62927 | 0.62927 | 165.58
Actual MM booked | 1.2473 | 3.7365 | 3.4824 | 5.9311 | 8.0784 | 7.2338 | 5.9608 | 8.7851 | 8.1784 | 6.6446 | 7.7986 | 3.4649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.5419
Earned MM (value delivered) | 1.6845 | 13.9042 | 13.4847 | 16.0518 | 14.1571 | 7.5015 | 11.6317 | 13.166 | 5.7658 | 6.3798 | 5.5491 | 2.2572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.5335
Profit / (Loss) in quarter | 0.43719 | 10.1677 | 10.0023 | 10.1207 | 6.0787 | 0.26774 | 5.6709 | 4.3809 | -2.4126 | -0.26478 | -2.2495 | -1.2077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.9916
Cumulative profit / (loss) | 0.43719 | 10.6049 | 20.6072 | 30.7279 | 36.8066 | 37.0744 | 42.7453 | 47.1262 | 44.7136 | 44.4488 | 42.1993 | 40.9916 | 40.9916 | 40.9916 | 40.9916 | 40.9916 | 40.9916 | 40.9916 | 40.9916 | 40.9916 | 40.9916 | 40.9916
TEAM CAPACITY, UTILISATION & EFFICIENCY
Capacity MM (availability x months) | 0 | 7.05 | 7.05 | 7.05 | 7.05 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 172.2
Actual MM booked | 1.2473 | 3.7365 | 3.4824 | 5.9311 | 8.0784 | 7.2338 | 5.9608 | 8.7851 | 8.1784 | 6.6446 | 7.7986 | 3.4649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70.5419
Utilisation vs capacity |  | 53% | 49.4% | 84.13% | 114.6% | 80.38% | 66.23% | 97.61% | 90.87% | 73.83% | 86.65% | 38.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 40.97%
Over / (Under) capacity (MM) | 1.2473 | -3.3135 | -3.5676 | -1.1189 | 1.0284 | -1.7662 | -3.0392 | -0.21486 | -0.82162 | -2.3554 | -1.2014 | -5.5351 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -9 | -101.6581
Plan adherence (actual vs planned) |  | 60.74% | 16.37% | 35.53% | 71.85% | 76.48% | 52.86% | 57.28% | 85.53% | 51.9% | 70.16% | 26.95% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 42.6%
Efficiency — CPI (earned vs actual) | 1.3505 | 3.7212 | 3.8722 | 2.7064 | 1.7525 | 1.037 | 1.9514 | 1.4987 | 0.705 | 0.96015 | 0.71155 | 0.65145 | [9 empty] | 1.5811
Schedule — SPI (earned vs planned) |  | 2.2602 | 0.63373 | 0.96171 | 1.2591 | 0.79312 | 1.0315 | 0.85847 | 0.60301 | 0.49837 | 0.49923 | 0.17554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67359
Elapsed fraction of quarter (to as-at date) | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 68.48% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 51.31%
Capacity MM to date | 0 | 7.05 | 7.05 | 7.05 | 7.05 | 9 | 9 | 9 | 9 | 9 | 9 | 6.163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88.363
Planned MM to date | 0 | 6.1517 | 21.2783 | 16.6909 | 11.2439 | 9.4582 | 11.2763 | 15.3366 | 9.5617 | 12.8015 | 11.1155 | 8.8052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133.7198
ANNUAL SUMMARY — ALL PROJECTS
| Opening | 2024 | 2025 | 2026 | 2027 | 2028 | Total
Planned MM | 0 | 55.3647 | 45.6329 | 44.8292 | 16.0049 | 3.7483 | 165.58
Actual MM booked | 1.2473 | 21.2284 | 30.1581 | 17.9081 | 0 | 0 | 70.5419
Earned MM (value delivered) | 1.6845 | 57.5978 | 38.0651 | 14.1861 | 0 | 0 | 111.5335
Profit / (Loss) in year | 0.43719 | 36.3694 | 7.9069 | -3.722 | 0 | 0 | 40.9916
Capacity MM | 0 | 28.2 | 36 | 36 | 36 | 36 | 172.2
Utilisation vs capacity |  | 75.28% | 83.77% | 49.74% | 0% | 0% | 40.97%
Plan adherence |  | 38.34% | 66.09% | 39.95% | 0% | 0% | 42.6%
Efficiency — CPI | 1.3505 | 2.7132 | 1.2622 | 0.79216 |  |  | 1.5811
Cumulative profit / (loss) | 0.43719 | 36.8066 | 44.7136 | 40.9916 | 40.9916 | 40.9916 | 40.9916
Profit / (Loss) in quarter measures value delivered against time burned in that period (Earned MM less Actual MM). It is a performance measure, not the forecast profit at completion — that sits on the Inputs sheet as Budget less Cost at Completion.

## Project Types
PROJECT TYPE LIBRARY
The one setup decision. Edit the cream cells to agree the group standard, then lock this sheet.
Type Code | Project Type | Measurement Basis | Earning Trigger (data source) | Portfolio Weight | Include in CPI? | Notes / rationale
DD | Detailed Design | Man-hour weighted deliverables | Deliverable issue status in EDMS | 1 | Yes | Baseline type. Full production of drawings, models and calculations.
CD | Concept / Preliminary Design | Stage gates | Gate acceptance recorded in EDMS | 1.1 | Yes | High engineering content, low document count. Weighted above DD for option-development effort.
FS | Feasibility / Master Planning | Stage gates | Report issue and comment closeout | 1 | Yes | Study work ending in a report rather than a drawing set.
SA | Specialist Analysis & Modelling | Weighted milestones | Model, run and report milestones | 1.2 | Yes | Mooring, berthing, dynamic and geotechnical analysis. Highest weight - specialist, non-substitutable skill.
DR | Design Review / Third-Party Check | Units complete | Comment sheet transmittal | 0.75 | Yes | Checking another party's design. Real skill, but consumes rather than creates deliverables.
TD | Tender Documentation | Man-hour weighted deliverables | Tender issue and addenda closeout | 0.85 | Yes | BOQ, specifications and tender drawings assembled from completed design.
CS | Construction Phase Support | Units complete (queries closed) | RFI / site query response transmittal | 0.8 | Yes | Reactive scope. Measured on closed queries, not on time at desk.
PP | Proposals & Bids | Level of effort | Submission date | 0.7 | No | Necessary but unmeasurable against a budget. Excluded from CPI by design.
OH | On Hold / Standby | Level of effort | n/a - earns nothing | 0.5 | No | Dormant scope. Earns no value; time booked here should be minimal and visible.
Weighting basis: | Detailed Design = 1.00 is the reference. Weights are applied to earned MM for PERSONAL SCORING ONLY (Engineer Scorecard). They are never applied to project financials.
Assumption: | Starting weights proposed by Marine Structures Unit for group agreement; not derived from a published standard. Agree once, then freeze.

## Rules of Credit
RULES OF CREDIT — EARNING STEPS BY PROJECT TYPE
Cumulative credit earned when a deliverable reaches each step. Only steps that leave a date stamp in a system should be used.
Type Code | Step No. | Step Name (choose this on the Deliverable Register) | Cumulative Credit | Data Source | Key (Type¦Step)
DD | 1 | Design started | 10% | Manual (capped) | DD¦1
DD | 2 | Issued for internal check (IDC/IFR) | 40% | EDMS status | DD¦2
DD | 3 | Checked and back-checked | 60% | EDMS status | DD¦3
DD | 4 | Transmitted to client (IFA/IFC) | 85% | Transmittal register | DD¦4
DD | 5 | Returned Code 1 / accepted | 100% | Client return code | DD¦5
CD | 1 | Design basis and criteria agreed | 15% | EDMS status | CD¦1
CD | 2 | Options developed | 40% | EDMS status | CD¦2
CD | 3 | Option selected and frozen | 65% | Minuted decision | CD¦3
CD | 4 | Concept report and drawings issued | 90% | Transmittal register | CD¦4
CD | 5 | Client acceptance | 100% | Client return code | CD¦5
FS | 1 | Data collection complete | 15% | EDMS status | FS¦1
FS | 2 | Analysis complete | 45% | EDMS status | FS¦2
FS | 3 | Draft report issued | 75% | Transmittal register | FS¦3
FS | 4 | Client comments closed | 90% | Comment register | FS¦4
FS | 5 | Final report issued | 100% | Transmittal register | FS¦5
SA | 1 | Design basis and criteria agreed | 15% | EDMS status | SA¦1
SA | 2 | Model built and validated | 40% | Model file / EDMS | SA¦2
SA | 3 | Analysis runs complete | 65% | Model file / EDMS | SA¦3
SA | 4 | Report issued | 90% | Transmittal register | SA¦4
SA | 5 | Comments closed | 100% | Comment register | SA¦5
DR | 1 | Documents received and logged | 10% | EDMS receipt | DR¦1
DR | 2 | Review complete internally | 60% | EDMS status | DR¦2
DR | 3 | Comment sheet transmitted | 90% | Transmittal register | DR¦3
DR | 4 | Comment closeout confirmed | 100% | Comment register | DR¦4
TD | 1 | Draft prepared | 30% | EDMS status | TD¦1
TD | 2 | Internal check complete | 55% | EDMS status | TD¦2
TD | 3 | Issued for tender | 85% | Transmittal register | TD¦3
TD | 4 | Tender queries and addenda closed | 100% | Query register | TD¦4
CS | 1 | Query received and logged | 10% | Query register | CS¦1
CS | 2 | Response prepared and checked | 60% | EDMS status | CS¦2
CS | 3 | Response transmitted | 100% | Transmittal register | CS¦3
PP | 1 | Proposal in preparation | 50% | Manual (capped) | PP¦1
PP | 2 | Proposal submitted | 100% | Submission log | PP¦2
OH | 1 | On hold - no earning | 0% | n/a | OH¦1
Offices may collapse steps (e.g. 10 / 85 / 100) but may not add steps that have no date stamp in a system.

## Work Calendar
WORK CALENDAR - SETTINGS
These settings drive the Timesheet Daily and Deliverable Actuals sheets. Blue cells are inputs you can change.
WORKING WEEK | 1 = normal working day, 0 = weekend |  | PUBLIC HOLIDAYS / CLOSURES | Optional. Holidays already charged as HOLIDAY are detected automatically; use this list for future dates.
Weekday no. | Day | Working? | Date | Name
1 | Sunday | 1
2 | Monday | 1
3 | Tuesday | 1
4 | Wednesday | 1
5 | Thursday | 1
6 | Friday | 0
7 | Saturday | 0
Standard hours per working day | 8.5
Analysis start date | 2026-01-01
Analysis end date | 2026-12-31
Last date found in timesheet data | 2026-08-16
ENGINEERS | Pattern is matched against FullName on Timesheet Raw. Keep the asterisks.
Short name | Match pattern | Available hrs / month
Engineer 1 | *Engineer 1* | 185
Engineer 2 | *Engineer 2* | 185
Engineer 3 | *Engineer 3* | 185
NON-PROJECT CHARGE CODES | JobNumber values that mean the engineer was not doing project work
Code | Meaning | Treat as
HOLIDAY | Public holiday or company closure | Day off
LEAVE | Annual or sick leave | Day off
EXCUSE.PER | Personal excuse, part of a day | Partial absence
LATE | Late arrival, part of a day | Partial absence
Weekend code for working-day maths | 0000110 | Built from the working week above (Mon..Sun, 1 = non-working)
Gap that counts as a real stoppage (working days) | 3
DATA CHECK - RUN YOUR EYE OVER THIS AFTER EVERY MONTHLY PASTE
Rows detected | 7682
First date in data | 2014-09-22
Last date in data | 2026-08-16
Total hours in data | 39389.5
Rows matched to Ahmed | 5822
Rows matched to Osama | 923
Rows matched to Kirolos | 937
Rows matched to nobody | 0
Verdict | All rows matched to an engineer
HOW TO UPDATE EACH MONTH
1. Open TS Ahmed, TS Osama and TS Kirolos. On each, select row 4 down to the last row of data and delete the rows.
2. Paste each person's new export into cell A4 of their own sheet. Include every column in the same order, but not the export's own header rows.
3. Timesheet Raw rebuilds itself from those three sheets - never type on it.
4. Come back here and check the DATA CHECK block above: row count, date range, and that no rows are unmatched.
5. If a new engineer joins, add a sheet for them, add their match pattern in the ENGINEERS block, and add them to the formula in Timesheet Raw cell A4.
6. Update progress on the Deliverables register and milestone dates on Deliverable Actuals. Actual MM on Phasing now calculates itself - do not type in that grid.
7. Only revisit the TS Phase column on Deliverable Actuals if a new deliverable is added to the register. Support Plan and Proposals need no monthly work.

## Deliverable Actuals
DELIVERABLE ACTUALS - REAL DATES, REAL HOURS, AND TIME SPENT DORMANT
Columns A-R are derived from the timesheet. The mid-blue block (W-AB) is yours to type into: real milestone dates from the DCN / register. Start and finish variance compare what you typed against what the timesheet actually shows, so a register that disagrees with the timesheet is flagged rather than hidden. "Longest stoppage" and "Activity spells" show whether a deliverable ran continuously or stopped and restarted - a submitted-then-waiting-for-comments deliverable will show 2 or more spells.
Project Number | Deliverable / Phase | Type | Register status | TS Phase (set once) | Started? | Phase hours (all) | Rows sharing | Actual hours | Actual MM | First charge | Last charge | Calendar days | Working days | Days charged | Dormant days | Dormant % | Activity status | Longest stoppage (working days) | Stoppage started | Stoppage ended | Activity spells | MANUAL: Actual start | MANUAL: Actual finish | MANUAL: Submitted to client | MANUAL: Comments received | MANUAL: Resubmitted | MANUAL: Completed | Start variance (days) | Finish variance (days) | Working days awaiting client | Internal idle days | Date check | First row of its phase group? | SUMMARY (counted once per phase group, not per berth)
N25178-0100D | Concept Design | CD | Option selected and frozen |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | Never charged | 0 | [12 empty] | 0 | no manual dates | 1 | Deliverables in register | 64
E26084-0100D | Schematic Design | CD | Option selected and frozen |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | Never charged | 0 | [12 empty] | 0 | no manual dates | 1 | Linked to a timesheet phase | 64
E26084-0100D | Final Design | DD | not started |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | Never charged | 0 | [12 empty] | 0 | no manual dates | 1 | Phase groups charged | 33
N25185-0100D | Concept Design | CD | Client acceptance |  | 1 | 1650.75 | 1 | 1650.75 | 8.923 | 2025-10-01 | 2026-03-18 | 169 | 121 | 110 | 11 | 9.091% | Dormant since 2026-03-18 | 2 | 2025-12-30 | 2026-01-04 | 1 | [9 empty] | 11 | no manual dates | 1 | Phase groups never charged | 11
N25185-0100D | Final Design - Tin Can Berth 1 | DD | not started |  | 0 | 1774.75 | 9 | 0 | 0 | 2026-03-24 | 2026-08-16 | 146 | 104 | 93 | 11 | 10.58% | Active | 4 | 2026-05-25 | 2026-06-01 | 2 | [9 empty] | 11 | no manual dates | 1 | Phase groups currently dormant | 31
N25185-0100D | Final Design - Tin Can Berth 2 | DD | not started |  | 0 | 1774.75 | 9 | 0 | 0 | 2026-03-24 | 2026-08-16 | 146 | 104 | 93 | 11 | 10.58% | Active | 4 | 2026-05-25 | 2026-06-01 | 2 | [9 empty] | 11 | no manual dates | 0 | Total actual hours attributed | 11970
N25185-0100D | Final Design - Tin Can Berth 3 | DD | not started |  | 0 | 1774.75 | 9 | 0 | 0 | 2026-03-24 | 2026-08-16 | 146 | 104 | 93 | 11 | 10.58% | Active | 4 | 2026-05-25 | 2026-06-01 | 2 | [9 empty] | 11 | no manual dates | 0 | Total working days awaiting client | 0
N25185-0100D | Final Design - Tin Can Berth 4 | DD | not started |  | 0 | 1774.75 | 9 | 0 | 0 | 2026-03-24 | 2026-08-16 | 146 | 104 | 93 | 11 | 10.58% | Active | 4 | 2026-05-25 | 2026-06-01 | 2 | [9 empty] | 11 | no manual dates | 0 | Total internal idle working days | 4788
N25185-0100D | Final Design - Tin Can Berth 5 | DD | Transmitted to client (IFA/IFC) |  | 1 | 1774.75 | 9 | 197.1944 | 1.0659 | 2026-03-24 | 2026-08-16 | 146 | 104 | 93 | 11 | 10.58% | Active | 4 | 2026-05-25 | 2026-06-01 | 2 | [9 empty] | 11 | no manual dates | 0 | Phase groups that stopped and restarted | 23
N25185-0100D | Final Design - Tin Can Berth 6 | DD | Transmitted to client (IFA/IFC) |  | 1 | 1774.75 | 9 | 197.1944 | 1.0659 | 2026-03-24 | 2026-08-16 | 146 | 104 | 93 | 11 | 10.58% | Active | 4 | 2026-05-25 | 2026-06-01 | 2 | [9 empty] | 11 | no manual dates | 0 | Longest single stoppage (working days) | 381
N25185-0100D | Final Design - Tin Can Berth 7 | DD | Transmitted to client (IFA/IFC) |  | 1 | 1774.75 | 9 | 197.1944 | 1.0659 | 2026-03-24 | 2026-08-16 | 146 | 104 | 93 | 11 | 10.58% | Active | 4 | 2026-05-25 | 2026-06-01 | 2 | [9 empty] | 11 | no manual dates | 0 | Rows where your dates disagree with timesheet | 0
N25185-0100D | Final Design - Tin Can Berth 8 | DD | Transmitted to client (IFA/IFC) |  | 1 | 1774.75 | 9 | 197.1944 | 1.0659 | 2026-03-24 | 2026-08-16 | 146 | 104 | 93 | 11 | 10.58% | Active | 4 | 2026-05-25 | 2026-06-01 | 2 | [9 empty] | 11 | no manual dates | 0
N25185-0100D | Final Design - Tin Can Berth 9 | DD | Design started |  | 1 | 1774.75 | 9 | 197.1944 | 1.0659 | 2026-03-24 | 2026-08-16 | 146 | 104 | 93 | 11 | 10.58% | Active | 4 | 2026-05-25 | 2026-06-01 | 2 | [9 empty] | 11 | no manual dates | 0
N25185-0100D | Final Design - Tin Can Berth 10 | DD | Design started |  | 1 | 1774.75 | 9 | 197.1944 | 1.0659 | 2026-03-24 | 2026-08-16 | 146 | 104 | 93 | 11 | 10.58% | Active | 4 | 2026-05-25 | 2026-06-01 | 2 | [9 empty] | 11 | no manual dates | 0
N25185-0100D | Final Design - Apapa Berth 4 | DD | not started |  | 0 | 1774.75 | 9 | 0 | 0 | 2026-03-24 | 2026-08-16 | 146 | 104 | 93 | 11 | 10.58% | Active | 4 | 2026-05-25 | 2026-06-01 | 2 | [9 empty] | 11 | no manual dates | 0
N25185-0100D | Final Design - Apapa Berth 5 | DD | not started |  | 0 | 1774.75 | 9 | 0 | 0 | 2026-03-24 | 2026-08-16 | 146 | 104 | 93 | 11 | 10.58% | Active | 4 | 2026-05-25 | 2026-06-01 | 2 | [9 empty] | 11 | no manual dates | 0
N25185-0100D | Final Design - Apapa Berth 6 | DD | not started |  | 0 | 1774.75 | 9 | 0 | 0 | 2026-03-24 | 2026-08-16 | 146 | 104 | 93 | 11 | 10.58% | Active | 4 | 2026-05-25 | 2026-06-01 | 2 | [9 empty] | 11 | no manual dates | 0
N25185-0100D | Final Design - Apapa Berth 7 | DD | not started |  | 0 | 1774.75 | 9 | 0 | 0 | 2026-03-24 | 2026-08-16 | 146 | 104 | 93 | 11 | 10.58% | Active | 4 | 2026-05-25 | 2026-06-01 | 2 | [9 empty] | 11 | no manual dates | 0
N25185-0100D | Final Design - Apapa Berth 8 | DD | not started |  | 0 | 1774.75 | 9 | 0 | 0 | 2026-03-24 | 2026-08-16 | 146 | 104 | 93 | 11 | 10.58% | Active | 4 | 2026-05-25 | 2026-06-01 | 2 | [9 empty] | 11 | no manual dates | 0
N25185-0100D | Final Design - Apapa Berth 9 | DD | not started |  | 0 | 1774.75 | 9 | 0 | 0 | 2026-03-24 | 2026-08-16 | 146 | 104 | 93 | 11 | 10.58% | Active | 4 | 2026-05-25 | 2026-06-01 | 2 | [9 empty] | 11 | no manual dates | 0
N25185-0100D | Final Design - Apapa Berth 10 | DD | not started |  | 0 | 1774.75 | 9 | 0 | 0 | 2026-03-24 | 2026-08-16 | 146 | 104 | 93 | 11 | 10.58% | Active | 4 | 2026-05-25 | 2026-06-01 | 2 | [9 empty] | 11 | no manual dates | 0
N25185-0100D | Final Design - Apapa Berth 11 | DD | not started |  | 0 | 1774.75 | 9 | 0 | 0 | 2026-03-24 | 2026-08-16 | 146 | 104 | 93 | 11 | 10.58% | Active | 4 | 2026-05-25 | 2026-06-01 | 2 | [9 empty] | 11 | no manual dates | 0
N25185-0100D | Final Design - Apapa Berth 12 | DD | Design started |  | 1 | 1774.75 | 9 | 197.1944 | 1.0659 | 2026-03-24 | 2026-08-16 | 146 | 104 | 93 | 11 | 10.58% | Active | 4 | 2026-05-25 | 2026-06-01 | 2 | [9 empty] | 11 | no manual dates | 0
N25185-0100D | Final Design - Apapa Berth 13 | DD | Design started |  | 1 | 1774.75 | 9 | 197.1944 | 1.0659 | 2026-03-24 | 2026-08-16 | 146 | 104 | 93 | 11 | 10.58% | Active | 4 | 2026-05-25 | 2026-06-01 | 2 | [9 empty] | 11 | no manual dates | 0
N25185-0100D | Final Design - Apapa Berth 14 | DD | Design started |  | 1 | 1774.75 | 9 | 197.1944 | 1.0659 | 2026-03-24 | 2026-08-16 | 146 | 104 | 93 | 11 | 10.58% | Active | 4 | 2026-05-25 | 2026-06-01 | 2 | [9 empty] | 11 | no manual dates | 0
AN22137-0100D | Schematic Design | CD | not started |  | 0 | 259.25 | 1 | 0 | 0 | 2024-04-30 | 2024-08-29 | 122 | 88 | 26 | 62 | 70.45% | Dormant since 2024-08-29 | 49 | 2024-05-22 | 2024-07-31 | 3 | [9 empty] | 62 | no manual dates | 1
D26058-0100D | Concept Design | CD | not started |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | Never charged | 0 | [12 empty] | 0 | no manual dates | 1
D26058-0100D | Schematic Design | CD | not started |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | Never charged | 0 | [12 empty] | 0 | no manual dates | 1
D26058-0100D | Final Design | CD | not started |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | Never charged | 0 | [12 empty] | 0 | no manual dates | 1
AD24217-0100D | Concept Design | CD | Client acceptance |  | 1 | 363.75 | 1 | 363.75 | 1.9662 | 2025-03-05 | 2025-09-28 | 208 | 148 | 42 | 106 | 71.62% | Dormant since 2025-09-28 | 51 | 2025-03-09 | 2025-05-20 | 8 | [9 empty] | 106 | no manual dates | 1
E24181-0100D | Report | SA | Comments closed |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | Never charged | 0 | [12 empty] | 0 | no manual dates | 1
J23152-0100D | Specifications | TD | Tender queries and addenda closed |  | 1 | 17.5 | 1 | 17.5 | 0.094595 | 2023-11-07 | 2023-11-12 | 6 | 4 | 2 | 2 | 50% | Dormant since 2023-11-12 | 2 | 2023-11-07 | 2023-11-12 | 1 | [9 empty] | 2 | no manual dates | 1
Q25008-0100D | Tender Design | TD | Tender queries and addenda closed |  | 1 | 357 | 1 | 357 | 1.9297 | 2025-01-28 | 2026-08-05 | 555 | 397 | 48 | 349 | 87.91% | Active | 212 | 2025-02-18 | 2025-12-14 | 11 | [9 empty] | 349 | no manual dates | 1
S24014-0101D | Report | SA | Comments closed |  | 1 | 451.75 | 1 | 451.75 | 2.4419 | 2024-02-26 | 2024-07-07 | 133 | 95 | 72 | 23 | 24.21% | Dormant since 2024-07-07 | 9 | 2024-04-07 | 2024-04-21 | 5 | [9 empty] | 23 | no manual dates | 1
S24014-0102D | Concept Design | CD | Client acceptance |  | 1 | 491.25 | 1 | 491.25 | 2.6554 | 2025-04-09 | 2025-09-24 | 169 | 121 | 72 | 49 | 40.5% | Dormant since 2025-09-24 | 16 | 2025-04-17 | 2025-05-12 | 6 | [9 empty] | 49 | no manual dates | 1
S24014-0103D | Concept Design | CD | Client acceptance |  | 1 | 804.75 | 1 | 804.75 | 4.35 | 2024-09-02 | 2024-12-17 | 107 | 77 | 66 | 11 | 14.29% | Dormant since 2024-12-17 | 5 | 2024-09-02 | 2024-09-10 | 2 | [9 empty] | 11 | no manual dates | 1
S24014-0104D | Report | SA | Comments closed |  | 1 | 225 | 1 | 225 | 1.2162 | 2024-09-04 | 2025-09-03 | 365 | 261 | 74 | 187 | 71.65% | Dormant since 2025-09-03 | 45 | 2025-06-25 | 2025-08-28 | 13 | [9 empty] | 187 | no manual dates | 1
S22058-0700D | Concept Design | CD | Client acceptance |  | 1 | 946.5 | 1 | 946.5 | 5.1162 | 2024-05-13 | 2025-11-06 | 543 | 389 | 95 | 294 | 75.58% | Dormant since 2025-11-06 | 80 | 2024-08-18 | 2024-12-09 | 13 | [9 empty] | 294 | no manual dates | 1
AN24185-0100R | Design Review | DR | Comment closeout confirmed |  | 1 | 547.75 | 1 | 547.75 | 2.9608 | 2024-10-20 | 2026-03-31 | 528 | 378 | 77 | 301 | 79.63% | Dormant since 2026-03-31 | 82 | 2025-10-26 | 2026-02-18 | 27 | [9 empty] | 301 | no manual dates | 1
AN23232-0100D | Concept Design | CD | Client acceptance |  | 1 | 403.75 | 1 | 403.75 | 2.1824 | 2023-11-20 | 2024-06-23 | 217 | 155 | 53 | 102 | 65.81% | Dormant since 2024-06-23 | 69 | 2024-01-30 | 2024-05-07 | 5 | [9 empty] | 102 | no manual dates | 1
S22058-0400D | Concept Design | CD | Client acceptance |  | 1 | 7.5 | 1 | 7.5 | 0.040541 | 2023-12-19 | 2025-04-29 | 498 | 356 | 7 | 349 | 98.03% | Dormant since 2025-04-29 | 306 | 2024-02-25 | 2025-04-29 | 3 | [9 empty] | 349 | no manual dates | 1
Proposals 25 | Proposals | PP | Proposal submitted |  | 1 | 385.5 | 1 | 385.5 | 2.0838 | 2025-02-19 | 2025-12-11 | 296 | 212 | 0 | 212 | 100% | Dormant since 2025-12-11 | 0 |  |  | 1 | [9 empty] | 212 | no manual dates | 1
Chargable Proposals 25 | Proposals | PP | Proposal submitted |  | 1 | 729.5 | 1 | 729.5 | 3.9432 | 2025-01-02 | 2025-09-08 | 250 | 178 | 0 | 178 | 100% | Dormant since 2025-09-08 | 0 |  |  | 1 | [9 empty] | 178 | no manual dates | 1
AN21146-0100R | Design Review | DR | Comment closeout confirmed |  | 1 | 96 | 1 | 96 | 0.51892 | 2024-05-14 | 2024-09-29 | 139 | 99 | 18 | 81 | 81.82% | Dormant since 2024-09-29 | 42 | 2024-06-23 | 2024-08-21 | 7 | [9 empty] | 81 | no manual dates | 1
N23106-0100D | Concept Design | CD | Client acceptance |  | 1 | 217.75 | 1 | 217.75 | 1.177 | 2024-05-28 | 2026-03-08 | 650 | 464 | 36 | 428 | 92.24% | Dormant since 2026-03-08 | 381 | 2024-09-01 | 2026-02-17 | 10 | [9 empty] | 428 | no manual dates | 1
OM23030-0100D | Tender Design | TD | Tender queries and addenda closed |  | 1 | 27.25 | 1 | 27.25 | 0.1473 | 2024-02-12 | 2024-02-25 | 14 | 10 | 10 | 0 | 0% | Dormant since 2024-02-25 | 0 |  |  | 1 | [9 empty] | 0 | no manual dates | 1
Chargable Proposals 24 | Proposals | PP | Proposal submitted |  | 1 | 343 | 1 | 343 | 1.8541 | 2024-02-01 | 2024-12-30 | 334 | 238 | 0 | 238 | 100% | Dormant since 2024-12-30 | 0 |  |  | 1 | [9 empty] | 238 | no manual dates | 1
Proposals 24 | Proposals | PP | Proposal submitted |  | 1 | 99.25 | 1 | 99.25 | 0.53649 | 2024-02-05 | 2024-12-18 | 318 | 228 | 0 | 228 | 100% | Dormant since 2024-12-18 | 0 |  |  | 1 | [9 empty] | 228 | no manual dates | 1
S23204-0100D | Concept Design | CD | Client acceptance |  | 1 | 8.5 | 1 | 8.5 | 0.045946 | 2024-01-31 | 2024-01-31 | 1 | 1 | 1 | 0 | 0% | Dormant since 2024-01-31 | 0 |  |  | 1 | [9 empty] | 0 | no manual dates | 1
S24100-0100D | Concept Design | CD | Client acceptance |  | 1 | 186 | 1 | 186 | 1.0054 | 2024-06-25 | 2024-10-16 | 114 | 82 | 22 | 60 | 73.17% | Dormant since 2024-10-16 | 33 | 2024-08-13 | 2024-09-30 | 4 | [9 empty] | 60 | no manual dates | 1
TA23011-0100R | Design Review | DR | Comment closeout confirmed |  | 1 | 10 | 1 | 10 | 0.054054 | 2023-12-18 | 2024-01-04 | 18 | 14 | 3 | 11 | 78.57% | Dormant since 2024-01-04 | 7 | 2023-12-25 | 2024-01-04 | 3 | [9 empty] | 11 | no manual dates | 1
AN23207-0500D | Concept Design | CD | Option selected and frozen |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | Never charged | 0 | [12 empty] | 0 | no manual dates | 1
AN23276-0100D | Concept Design | CD | Concept report and drawings issued |  | 1 | 164.5 | 1 | 164.5 | 0.88919 | 2024-06-13 | 2025-04-10 | 302 | 216 | 16 | 200 | 92.59% | Dormant since 2025-04-10 | 187 | 2024-07-21 | 2025-04-09 | 6 | [9 empty] | 200 | no manual dates | 1
AN24073-0100D | Concept Design | CD | Concept report and drawings issued |  | 1 | 171 | 1 | 171 | 0.92432 | 2025-07-28 | 2025-10-01 | 66 | 48 | 30 | 18 | 37.5% | Dormant since 2025-10-01 | 7 | 2025-09-21 | 2025-10-01 | 4 | [9 empty] | 18 | no manual dates | 1
AN24140-0100R | Design Review | DR | Documents received and logged |  | 1 | 93 | 1 | 93 | 0.5027 | 2024-12-05 | 2026-02-04 | 427 | 305 | 12 | 293 | 96.07% | Dormant since 2026-02-04 | 155 | 2025-07-01 | 2026-02-04 | 7 | [9 empty] | 293 | no manual dates | 1
CS24035-0100D | Detailed Design | DD | Transmitted to client (IFA/IFC) |  | 1 | 568.5 | 1 | 568.5 | 3.073 | 2025-10-27 | 2026-06-25 | 242 | 174 | 56 | 118 | 67.82% | Dormant since 2026-06-25 | 76 | 2026-01-22 | 2026-05-11 | 6 | [9 empty] | 118 | no manual dates | 1
AN24135-0100R | Design Review | DR | Documents received and logged |  | 1 | 338.75 | 1 | 338.75 | 1.8311 | 2024-10-15 | 2025-10-15 | 366 | 262 | 51 | 211 | 80.53% | Dormant since 2025-10-15 | 57 | 2025-04-17 | 2025-07-08 | 22 | [9 empty] | 211 | no manual dates | 1
AN23108-0100R | Design Review | DR | Documents received and logged |  | 1 | 153 | 1 | 153 | 0.82703 | 2025-02-05 | 2026-07-12 | 523 | 373 | 26 | 347 | 93.03% | Dormant since 2026-07-12 | 110 | 2025-05-08 | 2025-10-12 | 13 | [9 empty] | 347 | no manual dates | 1
TA24246-0200R | Design Review | DR | Review complete internally |  | 1 | 262.25 | 1 | 262.25 | 1.4176 | 2025-04-15 | 2026-04-06 | 357 | 255 | 43 | 212 | 83.14% | Dormant since 2026-04-06 | 112 | 2025-10-02 | 2026-03-10 | 9 | [9 empty] | 212 | no manual dates | 1
S22058-0900D | Concept Design | CD | Client acceptance |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | Never charged | 0 | [12 empty] | 0 | no manual dates | 1
AD23051-0101D | Concept Design | CD | Client acceptance |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | Never charged | 0 | [12 empty] | 0 | no manual dates | 1
AL25148-0100D | Concept Design | CD | not started |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | Never charged | 0 | [12 empty] | 0 | no manual dates | 1
Chargable Proposals 26 | Proposals | PP | Proposal in preparation |  | 1 | 61.25 | 1 | 61.25 | 0.33108 | 2026-02-25 | 2026-05-14 | 79 | 57 | 0 | 57 | 100% | Dormant since 2026-05-14 | 0 |  |  | 1 | [9 empty] | 57 | no manual dates | 1
Proposals 26 | Proposals | PP | Proposal in preparation |  | 1 | 13 | 1 | 13 | 0.07027 | 2026-01-19 | 2026-03-12 | 53 | 39 | 0 | 39 | 100% | Dormant since 2026-03-12 | 0 |  |  | 1 | [9 empty] | 39 | no manual dates | 1
Formulas:
Working days = IF([First charge]="","",IF(COUNT('Work Calendar'!$E6:E200)=0,NETWORKDAYS.INTL([First charge],[Last charge],'Work Calendar'!$B31),NETWORKDAYS.INTL([First charge],[Last charge],'Work Calendar'!$B31,'Work Calendar'!$E6:E200)))
Working days awaiting client = IF(OR([MANUAL: Submitted to client]="",[MANUAL: Comments received]=""),"",MAX(0,NETWORKDAYS.INTL([MANUAL: Submitted to client],[MANUAL: Comments received],'Work Calendar'!$B31)-2))
Stoppage started = IF(OR([Longest stoppage (working days)]="",[Longest stoppage (working days)]=0),"",IFERROR(INDEX('Timesheet Raw'!$BW4:BW8000,MATCH(1,INDEX(('Timesheet Raw'!$B4:B8000=[Project Number])*('Timesheet Raw'!$M4:M8000=[TS Phase (set once)])*('Timesheet Raw'!$BX4:BX8000=[Longest stoppage (working days)]),0),0)),""))
Stoppage ended = IF(OR([Longest stoppage (working days)]="",[Longest stoppage (working days)]=0),"",IFERROR(INDEX('Timesheet Raw'!$L4:L8000,MATCH(1,INDEX(('Timesheet Raw'!$B4:B8000=[Project Number])*('Timesheet Raw'!$M4:M8000=[TS Phase (set once)])*('Timesheet Raw'!$BX4:BX8000=[Longest stoppage (working days)]),0),0)),""))

## Timesheet Daily
TIMESHEET DAILY - WHO CHARGED WHAT, AND WHICH DAYS NOBODY WORKED
Every date in the analysis window from Work Calendar. "IDLE - no charge" means a normal working day with no timesheet entry at all. "Day off" means HOLIDAY or LEAVE was charged for the full day. The Absence / Late column also picks up part-day LATE and EXCUSE.PER charges.
|  | Match pattern > | *Ahmed* | [7 empty] | *Osama* | [7 empty] | *Kirolos*
Date | Day | Calendar | Ahmed Project | Ahmed Proposal | Ahmed Absence / Late | Ahmed Other | Ahmed Overtime | Ahmed Total | Ahmed Manual status | Ahmed Status | Osama Project | Osama Proposal | Osama Absence / Late | Osama Other | Osama Overtime | Osama Total | Osama Manual status | Osama Status | Kirolos Project | Kirolos Proposal | Kirolos Absence / Late | Kirolos Other | Kirolos Overtime | Kirolos Total | Kirolos Manual status | Kirolos Status
2026-01-01 | Thu | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-01-02 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-01-03 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-01-04 | Sun | Working | 7.25 | 0 | 1.25 | 0 | 0 | 8.5 |  | Charged | 7.5 | 0 | 1 | 0 | 0 | 8.5 |  | Charged | 6.25 | 0 | 2.25 | 0 | 0 | 8.5 |  | Charged
2026-01-05 | Mon | Working | 6.25 | 0 | 2.25 | 0 | 0 | 8.5 |  | Charged | 8 | 0 | 0.5 | 0 | 0 | 8.5 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-01-06 | Tue | Working | 7.5 | 0 | 1 | 0 | 0 | 8.5 |  | Charged | 7 | 0 | 1.5 | 0 | 0 | 8.5 |  | Charged | 6.75 | 0 | 1.75 | 0 | 0 | 8.5 |  | Charged
2026-01-07 | Wed | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-01-08 | Thu | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-01-09 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-01-10 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-01-11 | Sun | Working | 7 | 0 | 1.5 | 0 | 0 | 8.5 |  | Charged | 8.5 | 0 | 0.25 | 0 | 0.25 | 8.75 |  | Charged | 8 | 0 | 0.5 | 0 | 0 | 8.5 |  | Charged
2026-01-12 | Mon | Working | 6.75 | 0 | 1.75 | 0 | 0 | 8.5 |  | Charged | 8.5 | 0 | 0.25 | 0 | 0.25 | 8.75 |  | Charged | 7.5 | 0 | 1.5 | 0 | 0.5 | 9 |  | Charged
2026-01-13 | Tue | Working | 8.25 | 0 | 0.75 | 0 | 0.5 | 9 |  | Charged | 9.25 | 0 | 0 | 0 | 0.75 | 9.25 |  | Charged | 8.5 | 0 | 0.75 | 0 | 0.75 | 9.25 |  | Charged
2026-01-14 | Wed | Working | 7.5 | 0 | 1 | 0 | 0 | 8.5 |  | Charged | 8.5 | 0 | 0.25 | 0 | 0.25 | 8.75 |  | Charged | 7.25 | 0 | 1.25 | 0 | 0 | 8.5 |  | Charged
2026-01-15 | Thu | Working | 12 | 0 | 0.75 | 0 | 4.25 | 12.75 |  | Charged | 12.75 | 0 | 0 | 0 | 4.25 | 12.75 |  | Charged | 12 | 0 | 0.75 | 0 | 4.25 | 12.75 |  | Charged
2026-01-16 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-01-17 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-01-18 | Sun | Working | 6.25 | 0 | 2.25 | 0 | 0 | 8.5 |  | Charged | 8 | 0 | 0.5 | 0 | 0 | 8.5 |  | Charged | 7.25 | 0 | 1.25 | 0 | 0 | 8.5 |  | Charged
2026-01-19 | Mon | Working | 6.25 | 1 | 1.25 | 0 | 0 | 8.5 |  | Charged | 9.25 | 0 | 0 | 0 | 0.75 | 9.25 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-01-20 | Tue | Working | 6.75 | 0 | 1.75 | 0 | 0 | 8.5 |  | Charged | 9.25 | 0 | 0 | 0 | 0.75 | 9.25 |  | Charged | 7.5 | 0 | 1 | 0 | 0 | 8.5 |  | Charged
2026-01-21 | Wed | Working | 9 | 0 | 0.5 | 0 | 1 | 9.5 |  | Charged | 9.25 | 0 | 0 | 0 | 0.75 | 9.25 |  | Charged | 9.5 | 0 | 0 | 0 | 1 | 9.5 |  | Charged
2026-01-22 | Thu | Working | 7.5 | 0 | 1 | 0 | 0 | 8.5 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 8.25 | 0 | 0.25 | 0 | 0 | 8.5 |  | Charged
2026-01-23 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-01-24 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-01-25 | Sun | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 9.25 | 0 | 0 | 0 | 0.75 | 9.25 |  | Charged | 9.25 | 0 | 0 | 0 | 0.75 | 9.25 |  | Charged
2026-01-26 | Mon | Working | 9 | 0 | 0 | 0 | 0 | 9 |  | Charged | 6.75 | 0 | 1.75 | 0 | 0 | 8.5 |  | Charged | 8 | 0 | 0.5 | 0 | 0 | 8.5 |  | Charged
2026-01-27 | Tue | Working | 9 | 0 | 0 | 0 | 0 | 9 |  | Charged | 8.75 | 0 | 0.5 | 0 | 0.75 | 9.25 |  | Charged | 7.75 | 0 | 0.75 | 0 | 0 | 8.5 |  | Charged
2026-01-28 | Wed | Working | 9 | 0 | 0 | 0 | 0 | 9 |  | Charged | 9.25 | 0 | 0 | 0 | 0.75 | 9.25 |  | Charged | 9.25 | 0 | 0.25 | 0 | 1 | 9.5 |  | Charged
2026-01-29 | Thu | Working | 9 | 0 | 0 | 0 | 0 | 9 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-01-30 | Fri | Weekend | 9 | 0 | 0 | 0 | 0 | 9 |  | Worked weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-01-31 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-02-01 | Sun | Working | 8.5 | 0 | 0.5 | 0 | 0.5 | 9 |  | Charged | 9.25 | 0 | 0 | 0 | 0.75 | 9.25 |  | Charged | 8.75 | 0 | 0.5 | 0 | 0.75 | 9.25 |  | Charged
2026-02-02 | Mon | Working | 8.75 | 0 | 0.75 | 0 | 1 | 9.5 |  | Charged | 9 | 0 | 0.25 | 0 | 0.75 | 9.25 |  | Charged | 9 | 0 | 0.75 | 0 | 1.25 | 9.75 |  | Charged
2026-02-03 | Tue | Working | 8.75 | 0 | 0.75 | 0 | 1 | 9.5 |  | Charged | 8.75 | 0 | 0.5 | 0 | 0.75 | 9.25 |  | Charged | 9 | 0 | 0.5 | 0 | 1 | 9.5 |  | Charged
2026-02-04 | Wed | Working | 8.5 | 0 | 1 | 0 | 1 | 9.5 |  | Charged | 8.5 | 0 | 0.5 | 0 | 0.5 | 9 |  | Charged | 9.25 | 0 | 0.5 | 0 | 1.25 | 9.75 |  | Charged
2026-02-05 | Thu | Working | 9.25 | 0 | 1 | 0 | 1.75 | 10.25 |  | Charged | 10.75 | 0 | 0 | 0 | 2.25 | 10.75 |  | Charged | 10 | 0 | 0.5 | 0 | 2 | 10.5 |  | Charged
2026-02-06 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-02-07 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-02-08 | Sun | Working | 12.25 | 0 | 0.5 | 0 | 4.25 | 12.75 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 11 | 0 | 0 | 0 | 2.5 | 11 |  | Charged
2026-02-09 | Mon | Working | 14 | 0 | 0.75 | 0 | 6.25 | 14.75 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 8.75 | 0 | 0.75 | 0 | 1 | 9.5 |  | Charged
2026-02-10 | Tue | Working | 8.5 | 0 | 1.25 | 0 | 1.25 | 9.75 |  | Charged | 9.75 | 0 | 0 | 0 | 1.25 | 9.75 |  | Charged | 9.25 | 0 | 0.5 | 0 | 1.25 | 9.75 |  | Charged
2026-02-11 | Wed | Working | 8 | 0 | 1 | 0 | 0.5 | 9 |  | Charged | 9 | 0 | 0.25 | 0 | 0.75 | 9.25 |  | Charged | 9 | 0 | 0.25 | 0 | 0.75 | 9.25 |  | Charged
2026-02-12 | Thu | Working | 8 | 0 | 1.25 | 0 | 0.75 | 9.25 |  | Charged | 8.75 | 0 | 0.25 | 0 | 0.5 | 9 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-02-13 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-02-14 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-02-15 | Sun | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 7.5 | 0 | 1 | 0 | 0 | 8.5 |  | Charged
2026-02-16 | Mon | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 8 | 0 | 0.75 | 0 | 0.25 | 8.75 |  | Charged | 8.25 | 0 | 0.5 | 0 | 0.25 | 8.75 |  | Charged
2026-02-17 | Tue | Working | 8.75 | 0 | 0.25 | 0 | 0.5 | 9 |  | Charged | 6 | 0 | 2.5 | 0 | 0 | 8.5 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-02-18 | Wed | Working | 9.25 | 0 | 1.25 | 0 | 2 | 10.5 |  | Charged | 8.75 | 0 | 0.25 | 0 | 0.5 | 9 |  | Charged | 10.5 | 0 | 0.25 | 0 | 2.25 | 10.75 |  | Charged
2026-02-19 | Thu | Working | 7 | 0 | 0.5 | 0 | 0 | 7.5 |  | Charged | 0 | 0 | 7.5 | 0 | 0 | 7.5 |  | Leave (not charged) | 7.5 | 0 | 0.25 | 0 | 0.25 | 7.75 |  | Charged
2026-02-20 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-02-21 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-02-22 | Sun | Working | 0 | 0 | 7.5 | 0 | 0 | 7.5 |  | Leave (not charged) | 6.75 | 0 | 0.75 | 0 | 0 | 7.5 |  | Charged | 7.5 | 0 | 0.5 | 0 | 0.5 | 8 |  | Charged
2026-02-23 | Mon | Working | 7 | 0 | 0.5 | 0 | 0 | 7.5 |  | Charged | 6.75 | 0 | 0.75 | 0 | 0 | 7.5 |  | Charged | 7.25 | 0 | 0.25 | 0 | 0 | 7.5 |  | Charged
2026-02-24 | Tue | Working | 8.5 | 1 | 1 | 0 | 3 | 10.5 |  | Charged | 7 | 0 | 0.5 | 0 | 0 | 7.5 |  | Charged | 6.5 | 0 | 1 | 0 | 0 | 7.5 |  | Charged
2026-02-25 | Wed | Working | 5 | 2 | 0.5 | 0 | 0 | 7.5 |  | Charged | 6.75 | 0 | 0.75 | 0 | 0 | 7.5 |  | Charged | 0 | 7 | 0.5 | 0 | 0 | 7.5 |  | Charged
2026-02-26 | Thu | Working | 0 | 6.5 | 1 | 0 | 0 | 7.5 |  | Charged | 7.25 | 0 | 0.25 | 0 | 0 | 7.5 |  | Charged | 0 | 6.5 | 1 | 0 | 0 | 7.5 |  | Charged
2026-02-27 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-02-28 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-03-01 | Sun | Working | 0 | 0 | 7.5 | 0 | 0 | 7.5 |  | Leave (not charged) | 7 | 0 | 0.5 | 0 | 0 | 7.5 |  | Charged | 6.25 | 0 | 1.25 | 0 | 0 | 7.5 |  | Charged
2026-03-02 | Mon | Working | 3.5 | 3 | 1 | 0 | 0 | 7.5 |  | Charged | 7.5 | 0 | 0 | 0 | 0 | 7.5 |  | Charged | 6.5 | 0 | 1 | 0 | 0 | 7.5 |  | Charged
2026-03-03 | Tue | Working | 7.5 | 0 | 0.5 | 0 | 0.5 | 8 |  | Charged | 8.25 | 0 | 0 | 0 | 0.75 | 8.25 |  | Charged | 7.5 | 0 | 0.5 | 0 | 0.5 | 8 |  | Charged
2026-03-04 | Wed | Working | 6.25 | 0 | 1.25 | 0 | 0 | 7.5 |  | Charged | 6.75 | 0 | 0.75 | 0 | 0 | 7.5 |  | Charged | 6.25 | 0 | 1.25 | 0 | 0 | 7.5 |  | Charged
2026-03-05 | Thu | Working | 4.5 | 2 | 1 | 0 | 0 | 7.5 |  | Charged | 6.75 | 0 | 0.75 | 0 | 0 | 7.5 |  | Charged | 6.5 | 0 | 1 | 0 | 0 | 7.5 |  | Charged
2026-03-06 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-03-07 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-03-08 | Sun | Working | 0 | 0 | 7.5 | 0 | 0 | 7.5 |  | Leave (not charged) | 9 | 0 | 0 | 0 | 1.5 | 9 |  | Charged | 8.5 | 0 | 0.25 | 0 | 1.25 | 8.75 |  | Charged
2026-03-09 | Mon | Working | 7 | 0 | 0.75 | 0 | 0.25 | 7.75 |  | Charged | 8 | 0 | 0 | 0 | 0.5 | 8 |  | Charged | 7.75 | 0 | 0 | 0 | 0.25 | 7.75 |  | Charged
2026-03-10 | Tue | Working | 6.5 | 0 | 1 | 0 | 0 | 7.5 |  | Charged | 6.75 | 0 | 0.75 | 0 | 0 | 7.5 |  | Charged | 6.25 | 0 | 1.25 | 0 | 0 | 7.5 |  | Charged
2026-03-11 | Wed | Working | 0 | 0 | 7.5 | 0 | 0 | 7.5 |  | Leave (not charged) | 6.75 | 0 | 0.75 | 0 | 0 | 7.5 |  | Charged | 6 | 0 | 1.5 | 0 | 0 | 7.5 |  | Charged
2026-03-12 | Thu | Working | 3.25 | 4 | 0.5 | 0 | 0.25 | 7.75 |  | Charged | 6.5 | 0 | 1 | 0 | 0 | 7.5 |  | Charged | 7.25 | 0 | 0.5 | 0 | 0.25 | 7.75 |  | Charged
2026-03-13 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-03-14 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-03-15 | Sun | Working | 6.5 | 0 | 1 | 0 | 0 | 7.5 |  | Charged | 7 | 0 | 0.5 | 0 | 0 | 7.5 |  | Charged | 7.25 | 0 | 0.25 | 0 | 0 | 7.5 |  | Charged
2026-03-16 | Mon | Working | 6.75 | 0 | 1 | 0 | 0.25 | 7.75 |  | Charged | 6.75 | 0 | 0.75 | 0 | 0 | 7.5 |  | Charged | 7.75 | 0 | 0.25 | 0 | 0.5 | 8 |  | Charged
2026-03-17 | Tue | Working | 6.75 | 0 | 0.75 | 0 | 0 | 7.5 |  | Charged | 7 | 0 | 0.5 | 0 | 0 | 7.5 |  | Charged | 6.5 | 0 | 1 | 0 | 0 | 7.5 |  | Charged
2026-03-18 | Wed | Working | 6.75 | 0 | 0.75 | 0 | 0 | 7.5 |  | Charged | 5.75 | 0 | 1.75 | 0 | 0 | 7.5 |  | Charged | 6.25 | 0 | 1.25 | 0 | 0 | 7.5 |  | Charged
2026-03-19 | Thu | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-03-20 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-03-21 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-03-22 | Sun | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-03-23 | Mon | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-03-24 | Tue | Working | 2 | 6 | 0.5 | 0 | 0 | 8.5 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 8.5 | 0 | 0.25 | 0 | 0.25 | 8.75 |  | Charged
2026-03-25 | Wed | Working | 6 | 1 | 1.75 | 0 | 0.25 | 8.75 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 8.25 | 0 | 0.5 | 0 | 0.25 | 8.75 |  | Charged
2026-03-26 | Thu | Working | 7.75 | 0 | 1.75 | 0 | 1 | 9.5 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 8.25 | 0 | 0.25 | 0 | 0 | 8.5 |  | Charged
2026-03-27 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-03-28 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-03-29 | Sun | Working | 7.25 | 0 | 1.75 | 0 | 0.5 | 9 |  | Charged | 7.75 | 0 | 1.75 | 0 | 1 | 9.5 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-03-30 | Mon | Working | 13.25 | 0 | 1 | 0 | 5.75 | 14.25 |  | Charged | 8.75 | 0 | 0.25 | 0 | 0.5 | 9 |  | Charged | 8.25 | 0 | 0.75 | 0 | 0.5 | 9 |  | Charged
2026-03-31 | Tue | Working | 8.5 | 0 | 0.75 | 0 | 0.75 | 9.25 |  | Charged | 8.5 | 0 | 1 | 0 | 1 | 9.5 |  | Charged | 8.75 | 0 | 0.5 | 0 | 0.75 | 9.25 |  | Charged
2026-04-01 | Wed | Working | 8.5 | 0 | 0.75 | 0 | 0.75 | 9.25 |  | Charged | 8.75 | 0 | 0.75 | 0 | 1 | 9.5 |  | Charged | 9 | 0 | 0.25 | 0 | 0.75 | 9.25 |  | Charged
2026-04-02 | Thu | Working | 9.25 | 0 | 1 | 0 | 1.75 | 10.25 |  | Charged | 9 | 0 | 0 | 0 | 0.5 | 9 |  | Charged | 10 | 0 | 0.25 | 0 | 1.75 | 10.25 |  | Charged
2026-04-03 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-04-04 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-04-05 | Sun | Working | 7.25 | 0 | 1.75 | 0 | 0.5 | 9 |  | Charged | 9 | 0 | 0 | 0 | 0.5 | 9 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-04-06 | Mon | Working | 11.75 | 0 | 1 | 0 | 4.25 | 12.75 |  | Charged | 8.5 | 0 | 0.5 | 0 | 0.5 | 9 |  | Charged | 14.5 | 0 | 0.5 | 0 | 6.5 | 15 |  | Charged
2026-04-07 | Tue | Working | 12.5 | 0 | 1.25 | 0 | 5.25 | 13.75 |  | Charged | 8.5 | 0 | 0.75 | 0 | 0.75 | 9.25 |  | Charged | 15.25 | 0 | 0 | 0 | 6.75 | 15.25 |  | Charged
2026-04-08 | Wed | Working | 12.25 | 0 | 0.75 | 0 | 4.5 | 13 |  | Charged | 13.25 | 0 | 0.25 | 0 | 5 | 13.5 |  | Charged | 13.75 | 0 | 0 | 0 | 5.25 | 13.75 |  | Charged
2026-04-09 | Thu | Working | 8 | 0 | 1 | 0 | 0.5 | 9 |  | Charged | 9 | 0 | 0 | 0 | 0.5 | 9 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-04-10 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-04-11 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-04-12 | Sun | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-04-13 | Mon | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged)
2026-04-14 | Tue | Working | 9.25 | 0 | 0 | 0 | 0.75 | 9.25 |  | Charged | 8 | 0 | 0.5 | 0 | 0 | 8.5 |  | Charged | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged)
2026-04-15 | Wed | Working | 12.25 | 0 | 0.75 | 0 | 4.5 | 13 |  | Charged | 8.25 | 0 | 0.75 | 0 | 0.5 | 9 |  | Charged | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged)
2026-04-16 | Thu | Working | 9.25 | 0 | 0.5 | 0 | 1.25 | 9.75 |  | Charged | 9 | 0 | 0.5 | 0 | 1 | 9.5 |  | Charged | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged)
2026-04-17 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-04-18 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-04-19 | Sun | Working | 13 | 0 | 0.5 | 0 | 5 | 13.5 |  | Charged | 8.75 | 0 | 0 | 0 | 0.25 | 8.75 |  | Charged | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged)
2026-04-20 | Mon | Working | 14 | 0 | 1 | 0 | 6.5 | 15 |  | Charged | 8 | 0 | 0.75 | 0 | 0.25 | 8.75 |  | Charged | 8.25 | 0 | 1 | 0 | 0.75 | 9.25 |  | Charged
2026-04-21 | Tue | Working | 7.25 | 0 | 1.25 | 0 | 0 | 8.5 |  | Charged | 8.5 | 0 | 0.25 | 0 | 0.25 | 8.75 |  | Charged | 7.25 | 0 | 1.25 | 0 | 0 | 8.5 |  | Charged
2026-04-22 | Wed | Working | 15 | 0 | 0.75 | 0 | 7.25 | 15.75 |  | Charged | 12.25 | 0 | 0 | 0 | 3.75 | 12.25 |  | Charged | 11.75 | 0 | 0.5 | 0 | 3.75 | 12.25 |  | Charged
2026-04-23 | Thu | Working | 10.25 | 0 | 0 | 0 | 1.75 | 10.25 |  | Charged | 8.5 | 0 | 0.25 | 0 | 0.25 | 8.75 |  | Charged | 8.75 | 0 | 0.5 | 0 | 0.75 | 9.25 |  | Charged
2026-04-24 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-04-25 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-04-26 | Sun | Working | 11.25 | 0 | 1.25 | 0 | 4 | 12.5 |  | Charged | 13 | 0 | 0 | 0 | 4.5 | 13 |  | Charged | 10.25 | 0 | 0.25 | 0 | 2 | 10.5 |  | Charged
2026-04-27 | Mon | Working | 12.5 | 0 | 0.5 | 0 | 4.5 | 13 |  | Charged | 9.75 | 0 | 0 | 0 | 1.25 | 9.75 |  | Charged | 9.25 | 0 | 0.5 | 0 | 1.25 | 9.75 |  | Charged
2026-04-28 | Tue | Working | 12.25 | 0 | 0.5 | 0 | 4.25 | 12.75 |  | Charged | 12.75 | 0 | 0 | 0 | 4.25 | 12.75 |  | Charged | 13 | 0 | 0 | 0 | 4.5 | 13 |  | Charged
2026-04-29 | Wed | Working | 14.25 | 0 | 0.5 | 0 | 6.25 | 14.75 |  | Charged | 14.75 | 0 | 0 | 0 | 6.25 | 14.75 |  | Charged | 14.75 | 0 | 0.25 | 0 | 6.5 | 15 |  | Charged
2026-04-30 | Thu | Working | 12.25 | 0 | 0.75 | 0 | 4.5 | 13 |  | Charged | 8.75 | 0 | 1 | 0 | 1.25 | 9.75 |  | Charged | 11.75 | 0 | 0.75 | 0 | 4 | 12.5 |  | Charged
2026-05-01 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-05-02 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-05-03 | Sun | Working | 13.5 | 0 | 1 | 0 | 6 | 14.5 |  | Charged | 12.25 | 0 | 0 | 0 | 3.75 | 12.25 |  | Charged | 11.75 | 0 | 0.25 | 0 | 3.5 | 12 |  | Charged
2026-05-04 | Mon | Working | 14.25 | 0 | 1.5 | 0 | 7.25 | 15.75 |  | Charged | 13.5 | 0 | 0 | 0 | 5 | 13.5 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-05-05 | Tue | Working | 13 | 0 | 0.75 | 0 | 5.25 | 13.75 |  | Charged | 8.5 | 0 | 0.25 | 0 | 0.25 | 8.75 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-05-06 | Wed | Working | 8.5 | 0 | 0.75 | 0 | 0.75 | 9.25 |  | Charged | 14.75 | 0 | 0 | 0 | 6.25 | 14.75 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-05-07 | Thu | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-05-08 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-05-09 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-05-10 | Sun | Working | 9.5 | 0 | 0.25 | 0 | 1.25 | 9.75 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 9.75 | 0 | 0.25 | 0 | 1.5 | 10 |  | Charged
2026-05-11 | Mon | Working | 13.75 | 0 | 0.75 | 0 | 6 | 14.5 |  | Charged | 13.5 | 0 | 0 | 0 | 5 | 13.5 |  | Charged | 13 | 0 | 0.5 | 0 | 5 | 13.5 |  | Charged
2026-05-12 | Tue | Working | 15.5 | 0 | 0.5 | 0 | 7.5 | 16 |  | Charged | 14.75 | 0 | 0.25 | 0 | 6.5 | 15 |  | Charged | 0 | 15 | 0 | 0 | 6.5 | 15 |  | Charged
2026-05-13 | Wed | Working | 12.25 | 0 | 0.25 | 0 | 4 | 12.5 |  | Charged | 13 | 0 | 0 | 0 | 4.5 | 13 |  | Charged | 0 | 12.5 | 0.25 | 0 | 4.25 | 12.75 |  | Charged
2026-05-14 | Thu | Working | 2 | 6.75 | 0.75 | 0 | 1 | 9.5 |  | Charged | 8.5 | 0 | 0 | 0 | 0 | 8.5 |  | Charged | 7.25 | 0 | 2 | 0 | 0.75 | 9.25 |  | Charged
2026-05-15 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-05-16 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-05-17 | Sun | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 8 | 0 | 0.75 | 0 | 0.25 | 8.75 |  | Charged | 8.5 | 0 | 1 | 0 | 1 | 9.5 |  | Charged
2026-05-18 | Mon | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 12.5 | 0 | 0 | 0 | 4 | 12.5 |  | Charged | 12 | 0 | 0.75 | 0 | 4.25 | 12.75 |  | Charged
2026-05-19 | Tue | Working | 10.5 | 0 | 0.5 | 0 | 2.5 | 11 |  | Charged | 8.5 | 0 | 0 | 0 | 0 | 8.5 |  | Charged | 9.75 | 0 | 1 | 0 | 2.25 | 10.75 |  | Charged
2026-05-20 | Wed | Working | 8 | 0 | 1 | 0 | 0.5 | 9 |  | Charged | 9 | 0 | 0.25 | 0 | 0.75 | 9.25 |  | Charged | 8.5 | 0 | 0.75 | 0 | 0.75 | 9.25 |  | Charged
2026-05-21 | Thu | Working | 10.75 | 0 | 1.25 | 0 | 3.5 | 12 |  | Charged | 9.25 | 0 | 0 | 0 | 0.75 | 9.25 |  | Charged | 11.75 | 0 | 0.25 | 0 | 3.5 | 12 |  | Charged
2026-05-22 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-05-23 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-05-24 | Sun | Working | 13 | 0 | 0.75 | 0 | 5.25 | 13.75 |  | Charged | 9 | 0 | 0 | 0 | 0.5 | 9 |  | Charged | 12.5 | 0 | 0 | 0 | 4 | 12.5 |  | Charged
2026-05-25 | Mon | Working | 13.5 | 0 | 0.5 | 0 | 5.5 | 14 |  | Charged | 8.75 | 0 | 0 | 0 | 0.25 | 8.75 |  | Charged | 10.5 | 0 | 0.25 | 0 | 2.25 | 10.75 |  | Charged
2026-05-26 | Tue | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-05-27 | Wed | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-05-28 | Thu | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-05-29 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-05-30 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-05-31 | Sun | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-06-01 | Mon | Working | 4.25 | 0 | 4.25 | 0 | 0 | 8.5 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 8.5 | 0 | 0.25 | 0 | 0.25 | 8.75 |  | Charged
2026-06-02 | Tue | Working | 4.25 | 0 | 4.25 | 0 | 0 | 8.5 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 8.5 | 0 | 0.5 | 0 | 0.5 | 9 |  | Charged
2026-06-03 | Wed | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 6.5 | 0 | 2 | 0 | 0 | 8.5 |  | Charged
2026-06-04 | Thu | Working | 6.25 | 0 | 2.25 | 0 | 0 | 8.5 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 8.75 | 0 | 0.25 | 0 | 0.5 | 9 |  | Charged
2026-06-05 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-06-06 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-06-07 | Sun | Working | 7.25 | 0 | 2 | 0 | 0.75 | 9.25 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 8.75 | 0 | 0.75 | 0 | 1 | 9.5 |  | Charged
2026-06-08 | Mon | Working | 7.75 | 0 | 1.5 | 0 | 0.75 | 9.25 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 7.25 | 0 | 1.25 | 0 | 0 | 8.5 |  | Charged
2026-06-09 | Tue | Working | 9.25 | 0 | 1.75 | 0 | 2.5 | 11 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 7.5 | 0 | 1 | 0 | 0 | 8.5 |  | Charged
2026-06-10 | Wed | Working | 4.25 | 0 | 4.25 | 0 | 0 | 8.5 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 11.25 | 0 | 0.75 | 0 | 3.5 | 12 |  | Charged
2026-06-11 | Thu | Working | 8 | 0 | 0.75 | 0 | 0.25 | 8.75 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 8 | 0 | 0.75 | 0 | 0.25 | 8.75 |  | Charged
2026-06-12 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-06-13 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-06-14 | Sun | Working | 6.5 | 0 | 2 | 0 | 0 | 8.5 |  | Charged | 8.25 | 0 | 0.25 | 0 | 0 | 8.5 |  | Charged | 7.5 | 0 | 1 | 0 | 0 | 8.5 |  | Charged
2026-06-15 | Mon | Working | 7 | 0 | 1.5 | 0 | 0 | 8.5 |  | Charged | 8.5 | 0 | 0.25 | 0 | 0.25 | 8.75 |  | Charged | 6.75 | 0 | 1.75 | 0 | 0 | 8.5 |  | Charged
2026-06-16 | Tue | Working | 6.5 | 0 | 2.25 | 0 | 0.25 | 8.75 |  | Charged | 8.75 | 0 | 0.25 | 0 | 0.5 | 9 |  | Charged | 7.75 | 0 | 1 | 0 | 0.25 | 8.75 |  | Charged
2026-06-17 | Wed | Working | 8.25 | 0 | 1 | 0 | 0.75 | 9.25 |  | Charged | 8.75 | 0 | 0 | 0 | 0.25 | 8.75 |  | Charged | 8.5 | 0 | 0.75 | 0 | 0.75 | 9.25 |  | Charged
2026-06-18 | Thu | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-06-19 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-06-20 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-06-21 | Sun | Working | 6.25 | 0 | 2.5 | 0 | 0.25 | 8.75 |  | Charged | 13.25 | 0 | 0.25 | 0 | 5 | 13.5 |  | Charged | 13 | 0 | 0.25 | 0 | 4.75 | 13.25 |  | Charged
2026-06-22 | Mon | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 9 | 0 | 0 | 0 | 0.5 | 9 |  | Charged | 8 | 0 | 1 | 0 | 0.5 | 9 |  | Charged
2026-06-23 | Tue | Working | 7 | 0 | 1.5 | 0 | 0 | 8.5 |  | Charged | 9 | 0 | 0 | 0 | 0.5 | 9 |  | Charged | 6.75 | 0 | 2.25 | 0 | 0.5 | 9 |  | Charged
2026-06-24 | Wed | Working | 6.5 | 0 | 2.25 | 0 | 0.25 | 8.75 |  | Charged | 8.75 | 0 | 0 | 0 | 0.25 | 8.75 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-06-25 | Thu | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 8.75 | 0 | 0.5 | 0 | 0.75 | 9.25 |  | Charged | 6.25 | 0 | 2.25 | 0 | 0 | 8.5 |  | Charged
2026-06-26 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-06-27 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-06-28 | Sun | Working | 7.75 | 0 | 1.5 | 0 | 0.75 | 9.25 |  | Charged | 9.25 | 0 | 0.75 | 0 | 1.5 | 10 |  | Charged | 7.5 | 0 | 1 | 0 | 0 | 8.5 |  | Charged
2026-06-29 | Mon | Working | 8.25 | 0 | 0.5 | 0 | 0.25 | 8.75 |  | Charged | 9 | 0 | 0 | 0 | 0.5 | 9 |  | Charged | 8.75 | 0 | 0.25 | 0 | 0.5 | 9 |  | Charged
2026-06-30 | Tue | Working | 7.5 | 0 | 1 | 0 | 0 | 8.5 |  | Charged | 8.25 | 0 | 0.25 | 0 | 0 | 8.5 |  | Charged | 7.5 | 0 | 1 | 0 | 0 | 8.5 |  | Charged
2026-07-01 | Wed | Working | 7.75 | 0 | 2 | 0 | 1.25 | 9.75 |  | Charged | 9.75 | 0 | 0.25 | 0 | 1.5 | 10 |  | Charged | 8.75 | 0 | 1.25 | 0 | 1.5 | 10 |  | Charged
2026-07-02 | Thu | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-07-03 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-07-04 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-07-05 | Sun | Working | 7.25 | 0 | 1.25 | 0 | 0 | 8.5 |  | Charged | 8.75 | 0 | 0.25 | 0 | 0.5 | 9 |  | Charged | 8.25 | 0 | 0.5 | 0 | 0.25 | 8.75 |  | Charged
2026-07-06 | Mon | Working | 6.25 | 0 | 2.25 | 0 | 0 | 8.5 |  | Charged | 8.75 | 0 | 0.25 | 0 | 0.5 | 9 |  | Charged | 7.25 | 0 | 1.5 | 0 | 0.25 | 8.75 |  | Charged
2026-07-07 | Tue | Working | 6.25 | 0 | 2.25 | 0 | 0 | 8.5 |  | Charged | 7.75 | 0 | 0.75 | 0 | 0 | 8.5 |  | Charged | 6.75 | 0 | 1.75 | 0 | 0 | 8.5 |  | Charged
2026-07-08 | Wed | Working | 7 | 0 | 1.5 | 0 | 0 | 8.5 |  | Charged | 8.75 | 0 | 0.25 | 0 | 0.5 | 9 |  | Charged | 8.25 | 0 | 0.25 | 0 | 0 | 8.5 |  | Charged
2026-07-09 | Thu | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 10.75 | 0 | 0.25 | 0 | 2.5 | 11 |  | Charged | 9.5 | 0 | 1.25 | 0 | 2.25 | 10.75 |  | Charged
2026-07-10 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-07-11 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-07-12 | Sun | Working | 6.5 | 0 | 2 | 0 | 0 | 8.5 |  | Charged | 9 | 0 | 0 | 0 | 0.5 | 9 |  | Charged | 7.75 | 0 | 0.75 | 0 | 0 | 8.5 |  | Charged
2026-07-13 | Mon | Working | 6 | 0 | 2.5 | 0 | 0 | 8.5 |  | Charged | 8.5 | 0 | 0.25 | 0 | 0.25 | 8.75 |  | Charged | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged)
2026-07-14 | Tue | Working | 7.5 | 0 | 1.25 | 0 | 0.25 | 8.75 |  | Charged | 8.25 | 0 | 0.25 | 0 | 0 | 8.5 |  | Charged | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged)
2026-07-15 | Wed | Working | 4.5 | 0 | 4.25 | 0 | 0.25 | 8.75 |  | Charged | 8.5 | 0 | 0.25 | 0 | 0.25 | 8.75 |  | Charged | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged)
2026-07-16 | Thu | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 8 | 0 | 0.5 | 0 | 0 | 8.5 |  | Charged | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged)
2026-07-17 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-07-18 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-07-19 | Sun | Working | 8.25 | 0 | 0.5 | 0 | 0.25 | 8.75 |  | Charged | 8.5 | 0 | 0.5 | 0 | 0.5 | 9 |  | Charged | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged)
2026-07-20 | Mon | Working | 7 | 0 | 1.5 | 0 | 0 | 8.5 |  | Charged | 9 | 0 | 0 | 0 | 0.5 | 9 |  | Charged | 8.25 | 0 | 0.75 | 0 | 0.5 | 9 |  | Charged
2026-07-21 | Tue | Working | 8.25 | 0 | 1.25 | 0 | 1 | 9.5 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 9 | 0 | 0.75 | 0 | 1.25 | 9.75 |  | Charged
2026-07-22 | Wed | Working | 9.25 | 0 | 0.5 | 0 | 1.25 | 9.75 |  | Charged | 8.75 | 0 | 0 | 0 | 0.25 | 8.75 |  | Charged | 9.5 | 0 | 0.5 | 0 | 1.5 | 10 |  | Charged
2026-07-23 | Thu | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off
2026-07-24 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-07-25 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-07-26 | Sun | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 12.75 | 0 | 0.25 | 0 | 4.5 | 13 |  | Charged | 12 | 0 | 0.75 | 0 | 4.25 | 12.75 |  | Charged
2026-07-27 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged) | 13 | 0 | 0 | 0 | 4.5 | 13 |  | Charged | 12.5 | 0 | 0.5 | 0 | 4.5 | 13 |  | Charged
2026-07-28 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged) | 13.25 | 0 | 0 | 0 | 4.75 | 13.25 |  | Charged | 11.75 | 0 | 1.25 | 0 | 4.5 | 13 |  | Charged
2026-07-29 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged) | 14.75 | 0 | 0 | 0 | 6.25 | 14.75 |  | Charged | 13.75 | 0 | 0.5 | 0 | 5.75 | 14.25 |  | Charged
2026-07-30 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged) | 14.5 | 0 | 2 | 0 | 8 | 16.5 |  | Charged | 15.25 | 0 | 1.25 | 0 | 8 | 16.5 |  | Charged
2026-07-31 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-08-01 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-08-02 | Sun | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged) | 9 | 0 | 0 | 0 | 0.5 | 9 |  | Charged | 10.5 | 0 | 0.25 | 0 | 2.25 | 10.75 |  | Charged
2026-08-03 | Mon | Working | 7.75 | 0 | 2 | 0 | 1.25 | 9.75 |  | Charged | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 8.5 | 0 | 1.25 | 0 | 1.25 | 9.75 |  | Charged
2026-08-04 | Tue | Working | 9 | 0 | 1 | 0 | 1.5 | 10 |  | Charged | 12.5 | 0 | 0 | 0 | 4 | 12.5 |  | Charged | 11 | 0 | 1.75 | 0 | 4.25 | 12.75 |  | Charged
2026-08-05 | Wed | Working | 10.75 | 0 | 0.5 | 0 | 2.75 | 11.25 |  | Charged | 8.75 | 0 | 0.25 | 0 | 0.5 | 9 |  | Charged | 10.5 | 0 | 0.75 | 0 | 2.75 | 11.25 |  | Charged
2026-08-06 | Thu | Working | 9.75 | 0 | 1.25 | 0 | 2.5 | 11 |  | Charged | 9 | 0 | 0 | 0 | 0.5 | 9 |  | Charged | 14.25 | 0 | 0.75 | 0 | 6.5 | 15 |  | Charged
2026-08-07 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-08-08 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-08-09 | Sun | Working | 0 | 0 | 8.5 | 0 | 0 | 8.5 |  | Day off | 13.5 | 0 | 0 | 0 | 5 | 13.5 |  | Charged | 11.5 | 0 | 1.25 | 0 | 4.25 | 12.75 |  | Charged
2026-08-10 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged) | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged) | 9.5 | 0 | 1.5 | 0 | 2.5 | 11 |  | Charged
2026-08-11 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged) | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged) | 12.25 | 0 | 1 | 0 | 4.75 | 13.25 |  | Charged
2026-08-12 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged) | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged) | 9.25 | 0 | 1.25 | 0 | 2 | 10.5 |  | Charged
2026-08-13 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged) | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged) | 9.75 | 0 | 1.5 | 0 | 2.75 | 11.25 |  | Charged
2026-08-14 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-08-15 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | Weekend
2026-08-16 | Sun | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged) | 0 | 0 | 0 | 0 | 0 | 0 |  | Leave (not charged) | 12.5 | 0 | 1.75 | 0 | 5.75 | 14.25 |  | Charged
2026-08-17 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-08-18 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-08-19 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-08-20 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-08-21 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-08-22 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-08-23 | Sun | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-08-24 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-08-25 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-08-26 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-08-27 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-08-28 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-08-29 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-08-30 | Sun | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-08-31 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-01 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-02 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-03 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-04 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-05 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-06 | Sun | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-07 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-08 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-09 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-10 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-11 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-12 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-13 | Sun | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-14 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-15 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-16 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-17 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-18 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-19 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-20 | Sun | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-21 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-22 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-23 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-24 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-25 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-26 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-27 | Sun | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-28 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-29 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-09-30 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-01 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-02 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-03 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-04 | Sun | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-05 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-06 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-07 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-08 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-09 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-10 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-11 | Sun | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-12 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-13 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-14 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-15 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-16 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-17 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-18 | Sun | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-19 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-20 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-21 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-22 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-23 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-24 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-25 | Sun | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-26 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-27 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-28 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-29 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-30 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-10-31 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-01 | Sun | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-02 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-03 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-04 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-05 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-06 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-07 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-08 | Sun | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-09 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-10 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-11 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-12 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-13 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-14 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-15 | Sun | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-16 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-17 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-18 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-19 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-20 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-21 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-22 | Sun | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-23 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-24 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-25 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-26 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-27 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-28 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-29 | Sun | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-11-30 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-01 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-02 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-03 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-04 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-05 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-06 | Sun | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-07 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-08 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-09 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-10 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-11 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-12 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-13 | Sun | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-14 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-15 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-16 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-17 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-18 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-19 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-20 | Sun | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-21 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-22 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-23 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-24 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-25 | Fri | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-26 | Sat | Weekend | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-27 | Sun | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-28 | Mon | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-29 | Tue | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-30 | Wed | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
2026-12-31 | Thu | Working | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet | 0 | 0 | 0 | 0 | 0 | 0 |  | No data yet
Formulas:
Date = IF([Date, row above]="","",IF([Date, row above]+1>'Work Calendar'!$B16,"",[Date, row above]+1))

## Timesheet Raw
TIMESHEET RAW - CONSOLIDATED VIEW. Do not type here. This sheet stacks the three per-engineer sheets automatically. Paste each person's export into TS Ahmed, TS Osama or TS Kirolos instead.
Built automatically from TS Ahmed + TS Osama + TS Kirolos by the formula in cell A4. Each source sheet is read from row 4 to row 6000, so up to about 18,000 rows in total. Helper columns BU:BX are used by the dormancy and stoppage calculations.
Job Type | JobNumber | FullName | Total MM | % | WorkAreaCode | EmployeeAreaCode | DepartmentABR | EmployeeID | RegularHours | OvertimeHours | Date | Phase | Task | WorkScope | TotalHours | MappedDepartmentABR | Grade | DCNID | Budget | BudgetStatus | PercentProgress | ProgressDepBudget | JobDept | BudgetedDeptABR | OfficeCode | AreaDept | EmployeeOffice | CurrentUnitDesc | CurrentUnitId | JobDeptUnit | JobStatus | RegularHoursSubmitted | OvertimeHoursSubmitted | SourceID | TimesheetStatusId | TotalTimesheetHours | EmployeeWeek | EmployeeDay | Expenditure Type | DeliverableID | InOut | EAC | ETC | BudgetAtProgressDate | SpentAtProgressDate | InOutSourcing | WkSummarykey | WKeyOffice | DeliverableDescription | CPI_New | EAC1_New | EAC2_New | ETC1_New | ETC2_New | EV_New | MaximumEAC | MinimumEAC | PercentPlanedWork_New | PV_New | SPI_New | EV_New_MM | EV_without99 | EAC1without99 | ETC1Without99 | CumulativeSpent | CumulativeSpentMM | EAC1 Based on CumulativeSpent | ETC1 Based on CumulativeSpent | EAC2 Based on Cumulative Spent | IsLatestProgressDate | IsMaximumdate | DayKey (helper) | FirstLineForDay (helper) | PrevChargeDate (helper) | GapWorkingDays (helper)
1-Projects | AN22137-0100D | Ahmed Mitwally | 0.1054 | 2.2941 | 39-0 | 39-0 | SB | 063381 | 8.5 | 11 | 2024-08-28 | 1 | 1 | HO Design | 19.5 | [56 empty] | AN22137-0100D¦1¦45532 | 1 | 2024-08-27 | 0
Formulas:
PrevChargeDate (helper) = IF([DayKey (helper)]="","",IFERROR(MAXIFS(L4:L8000,B4:B8000,[JobNumber],M4:M8000,[Phase],L4:L8000,"<"&[Date]),""))
GapWorkingDays (helper) = IF(OR([PrevChargeDate (helper)]="",[PrevChargeDate (helper)]=0),"",MAX(0,NETWORKDAYS.INTL([PrevChargeDate (helper)],[Date],'Work Calendar'!$B31)-2))

## TS Engineer 1
TIMESHEET - ENGINEER 1 ¦ PASTE TARGET. Delete row 4 downward, then paste this person's export into A4. Do not touch row 3.
Job Type | JobNumber | FullName | Total MM | % | WorkAreaCode | EmployeeAreaCode | DepartmentABR | EmployeeID | RegularHours | OvertimeHours | Date | Phase | Task | WorkScope | TotalHours | MappedDepartmentABR | Grade | DCNID | Budget | BudgetStatus | PercentProgress | ProgressDepBudget | JobDept | BudgetedDeptABR | OfficeCode | AreaDept | EmployeeOffice | CurrentUnitDesc | CurrentUnitId | JobDeptUnit | JobStatus | RegularHoursSubmitted | OvertimeHoursSubmitted | SourceID | TimesheetStatusId | TotalTimesheetHours | EmployeeWeek | EmployeeDay | Expenditure Type | DeliverableID | InOut | EAC | ETC | BudgetAtProgressDate | SpentAtProgressDate | InOutSourcing | WkSummarykey | WKeyOffice | DeliverableDescription | CPI_New | EAC1_New | EAC2_New | ETC1_New | ETC2_New | EV_New | MaximumEAC | MinimumEAC | PercentPlanedWork_New | PV_New | SPI_New | EV_New_MM | EV_without99 | EAC1without99 | ETC1Without99 | CumulativeSpent | CumulativeSpentMM | EAC1 Based on CumulativeSpent | ETC1 Based on CumulativeSpent | EAC2 Based on Cumulative Spent | IsLatestProgressDate | IsMaximumdate

## TS Engineer 2
TIMESHEET - ENGINEER 2 ¦ PASTE TARGET. Delete row 4 downward, then paste this person's export into A4. Do not touch row 3.
Job Type | JobNumber | FullName | Total MM | % | WorkAreaCode | EmployeeAreaCode | DepartmentABR | EmployeeID | RegularHours | OvertimeHours | Date | Phase | Task | WorkScope | TotalHours | MappedDepartmentABR | Grade | DCNID | Budget | BudgetStatus | PercentProgress | ProgressDepBudget | JobDept | BudgetedDeptABR | OfficeCode | AreaDept | EmployeeOffice | CurrentUnitDesc | CurrentUnitId | JobDeptUnit | JobStatus | RegularHoursSubmitted | OvertimeHoursSubmitted | SourceID | TimesheetStatusId | TotalTimesheetHours | EmployeeWeek | EmployeeDay | Expenditure Type | DeliverableID | InOut | EAC | ETC | BudgetAtProgressDate | SpentAtProgressDate | InOutSourcing | WkSummarykey | WKeyOffice | DeliverableDescription | CPI_New | EAC1_New | EAC2_New | ETC1_New | ETC2_New | EV_New | MaximumEAC | MinimumEAC | PercentPlanedWork_New | PV_New | SPI_New | EV_New_MM | EV_without99 | EAC1without99 | ETC1Without99 | CumulativeSpent | CumulativeSpentMM | EAC1 Based on CumulativeSpent | ETC1 Based on CumulativeSpent | EAC2 Based on Cumulative Spent | IsLatestProgressDate | IsMaximumdate

## TS Engineer 3
TIMESHEET - ENGINEER 3 ¦ PASTE TARGET. Delete row 4 downward, then paste this person's export into A4. Do not touch row 3.
Job Type | JobNumber | FullName | Total MM | % | WorkAreaCode | EmployeeAreaCode | DepartmentABR | EmployeeID | RegularHours | OvertimeHours | Date | Phase | Task | WorkScope | TotalHours | MappedDepartmentABR | Grade | DCNID | Budget | BudgetStatus | PercentProgress | ProgressDepBudget | JobDept | BudgetedDeptABR | OfficeCode | AreaDept | EmployeeOffice | CurrentUnitDesc | CurrentUnitId | JobDeptUnit | JobStatus | RegularHoursSubmitted | OvertimeHoursSubmitted | SourceID | TimesheetStatusId | TotalTimesheetHours | EmployeeWeek | EmployeeDay | Expenditure Type | DeliverableID | InOut | EAC | ETC | BudgetAtProgressDate | SpentAtProgressDate | InOutSourcing | WkSummarykey | WKeyOffice | DeliverableDescription | CPI_New | EAC1_New | EAC2_New | ETC1_New | ETC2_New | EV_New | MaximumEAC | MinimumEAC | PercentPlanedWork_New | PV_New | SPI_New | EV_New_MM | EV_without99 | EAC1without99 | ETC1Without99 | CumulativeSpent | CumulativeSpentMM | EAC1 Based on CumulativeSpent | ETC1 Based on CumulativeSpent | EAC2 Based on Cumulative Spent | IsLatestProgressDate | IsMaximumdate